PROJECT PROPOSAL

Protection of Nomad Children against STIs and Hepatitis B

Background:

Pakistan Paediatric Association (PPA) is a registered professional body and the sole representative of more than 1,500 paediatricians of the country. It is affiliated with International Paediatric Association and SAARC Paediatric Association. Its Child Rights & Abuse Committee (CRAC) is working for the rights of children as enshrined in the UN Convention on the Rights of the Child (CRC, 1989).  For the past fifteen years, its focus of work is child abuse prevention and management. CRAC-PPA is the implementing partner of Save the Children Sweden and has conducted trainings, consultancies, and research for UNICEF, Save the Children UK, Groupe Developpemente, and the Government of Pakistan. It is affiliated with ECPAT International (End Child Prostitution and Trafficking) and ISPCAN (International Society for Prevention against Child Abuse and Neglect).

CRAC-PPA works for the better care of children against physical, sexual, and emotional abuse. Its main target groups are children working in brick kilns of Batapur (Lahore), children in hospitals, children in schools, and children living on the street. It is currently focusing on the training of teachers, doctors, and other service providers to detect, report, manage, and rehabilitate cases of child abuse. It also works closely with other NGOs in Lahore for their capacity building on child protection issues. Other groups of children that CRAC-PPA has worked with in the past include Children in conflict with the law, Child laborers, Abandoned children, Truck workers, Street children, Sexually exploited girls/boys, Refugee children, Hotel workers, Trash pickers, Workshop boys, Runaway children, Special children, Massage workers, Children involved in substance abuse, Children vulnerable to HIV/AIDS and STIs(, and Children in alternate care institutes.

CRAC-PPA has collaborated with another NGO (Godh) for the healthcare of nomad children. Detailed Focus Group Discussions and secondary data indicates the following main findings:

- Unpublished reports of data collected from secondary sources confirm the presence of about 34,800 nomad( families in the city of Lahore and its surroundings(.

- Anonymity and loneliness as a community have definitely affected the permissiveness level of the nomads, as they do not feel bound by the social controls normally influencing a person or family. The nomads feel that they are a stigmatized group, as they are perceived as a threat by the local population. Therefore, opportunities for earning a livelihood are further reduced due to this prejudice in an already indigent world. In such a situation, the vulnerability factors for indulging in risky behaviors for economic gains are further increased.

- Apart from begging and laboring, the most commonly adopted means of earning a living include cane-making, singing and dancing, working as acrobats, making mud toys, snake-charming, working as quacks, bangle-selling, garbage collecting, and working as behrupia (imposters). There is a large number of children involved in these activities, as it is customary for all family members to work.

- There is no knowledge about HIV/AIDS or the consequences of unsafe abortions and unsanitary births. Contraception is out of the question, primarily because of a lack of awareness.

- Although medical services are available to neighboring communities, the nomads are reluctant to use these facilities because of economic and social constraints. No government authority supports these nomads as they are not considered as citizens of one particular geographic area.

- Drug abuse is an everyday reality in this community. They use opium, hashish, heroin, alcohol, and intravenous drugs.

- Speaking about vulnerability to Commercial Sexual Exploitation of Children (CSEC), the children said that it was quite common for people to attempt sodomy with the boys who participate in public performances, especially when these children are dressed up like girls. ‘We are usually 15-20 boys, so we try and save our companions from the lust of other people, but that is not always possible’.

Hepatitis B and C, along with HIV/AIDS are transmitted through sexual contact. The incidence of hepatitis B and C is on the rise, with almost 10% of the population carrying the virus in its blood. Hepatitis B vaccination is an effective method of prevention against this disease. The public campaigns against hepatitis B have already raised awareness in the communities but its cost is a hindering factor in wide coverage. Providing hepatitis B vaccination to these vulnerable children will be an effective method for gaining their confidence and will also serve as a community awareness mechanism where they can be made aware about prevention of other STIs, including hepatitis C and HIV/AIDS.

In view of the above, CRAC-PPA feels an urgent need to provide awareness about HIV/AIDS and STIs to the community, especially the adolescent population of nomads. Because of the vulnerability of the Pakistani population to Hepatitis B, it is essential that an effective program be designed to protect this target group against the spread of STIs, hepatitis B, and HIV/AIDS.

Objectives:

- To educate 200 vulnerable children on protection against preventable diseases through community seminars

- To vaccinate 200 vulnerable children against Hepatitis B

- To advocate for a sustainable plan for extended coverage through soliciting the support of pharmaceutical companies

Time Frame:

4 weeks (1st August 2005 – 29th August 2005)

An additional one week after a period of 1 month to give second dose

An additional one week after a period of 6 months to give booster dose

Activity Plan:

- Week 1: Project Orientation:

This would include visits to the offices of CRAC-PPA and Godh for capacity building on the issue. Visits to project site for informal interaction with the community will also be undertaken during this week.

- Week 2-5: Community Seminars and Vaccination Campaign:

Four community cohorts of 50 adolescents each will be made for convenience. One seminar per cohort, followed by vaccination of the entire cohort will take place each week. In total, four community seminars will be held for 200 adolescent boys and girls of the nomad community. A community mobilizer will deliver a talk and answer any queries that the adolescents have regarding HIV/AIDS, STIs, and hepatitis B. The discussions will be simple, easy to understand, and will include practical tips for prevention.

A total of two hundred adolescent boys and girls of the nomad community will be given the first dose of hepatitis B. They will be given vaccination record cards and reminded to have their second dose after one month.

The second and booster dose will be administered by CRAC-PPA. However, for financial clarity, the vaccines will be purchased before the end of the project.

Week 6:

One to one meetings will be held with various pharmaceutical companies to try and convince them for financing CRAC-PPA for extended coverage of the project to make more adolescents immunized against hepatitis B.

Monitoring & Follow up:

External monitoring will be conducted by ADP while follow up of the project would be by CRAC-PPA. If the pharmaceutical companies agree to further fund the project, CRAC-PPA will collaborate with NGOs like Godh to provide coverage to the target groups.

Budget:

Vaccination cost (PKR 230 x 3 doses x 200 adolescents) =			PKR138,000

Disposable syringes (PKR 8 x 3 doses x 200 adolescents) = 		PKR    4,800

Methylated alcohol swabs (PKR 1 x 3 doses x 200 adolescents) =		PKR       600

Vaccination record cards (PKR 5 x 200 adolescents) =			PKR    1,000

Honorarium to vaccinator (PKR 10 x 3 doses x 200 adolescents) =		PKR	6,000

Refreshment at community seminars (PKR 20 x 6 seminars x 100 persons) PKR  12,000

Banners for community seminars (PKR 500 x 3 types of banners) =	PKR    1,500

Honorarium for Community mobilizer (PKR 500 x 6 seminars) =		PKR 	3,000

Total 									        PKR   166,900

US$ 2,782

Conversion rate 1 US$ = 60PKR (Rounded to nearest 10).

Schedule:

1st Aug – 7th Aug:

Mon:		Field Visit

Tue:		Material Development

Wed-Fri:	Survey Development; Consent Forms; Develop record cards; registration

8th Aug – 14th Aug:

Mon-Wed:	50 person survey

Thurs-Fri:	Questionnaire revised

15th Aug – 21st Aug:

Seminar and first dose 	200 Children

# Footnotes

( STI: Sexually Transmitted Infection

( The terms gypsy and nomad are interchangeable in this document

( Research conducted by Godh, an NGO exclusively working on gypsy communities in Lahore