## Sheet2
Reporting requirements need to be discussed and agreed upon
Receipts must be maintained for all expenses above Rs. 1,000;
|  | Receipts will be provided to ADP by |  | Month-end | via | designated agent |  | from | CFO (SFL) | to | Person B (ADP)
|  | Reports will be provided to ADP by |  | Month-end | via | email |  | from | GM (SFL) | to | Project Team
Project timeline needs to be determined in detail, so as to determine reporting requirements and format;
Sample Project Timeline
[5 empty] | Start Date | 2011-01-12
|  | Benchmarks / Week |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
|  | Formulation of Local Committee |  |  |  | On November 12, 2011, a committee of 7 Local Members is formulated to facilitate to SFLT team for identification of beneficiaries. This committee will also facilitate to beneficiaries to construct houses in stipulated time.
|  | Survey for identification of beneficiaries |  |  |  | Sahara For life Trust’s team conducted a survey of 46 flood affectees in Garibabad of district Muzaffargah . This survey was completed on November 13-14,2011
|  | Scrutiny of beneficiaries |  |  |  | Meeting of local Committee was held on dated November 15,2011 for scrutiny of identified beneficiaries in term of their most vulnerability and completion of desired document i.e., ID cards & Fard-e- malkiat etc. After verification of the document and discussion committee selected 21 beneficiaries among 46 for onward submission in final meeting with high-up of SFLT for final selection.
| Pre-Funding Stage | Evaluation & Finalization of Beneficiaries |  |  |  | On November 16, 2011 a detail meeting between Excutive Director pf SFLT, General Manager of SFLT and local Cmmittee was held for finalization of beneficiaries.
|  | Obtain land ownership verification from beneficiaries |  |  |  | On November 16, 2011 land ownership documents were reviewed & verified. These documents were received from finalized beneficiaries and placed in record.
|  | Project limits and modalities sharing with beneficiaries |  |  |  | After verification of documents and field visit 12 beneficaries were finalized & and project limits and modalities were shared with them in detail.
|  | Conclude participation agreements with beneficiaries |  |  |  | On November 22, 2011 agreements were signed with 12 finalized beneficiaries.
Finalized work plan and budget allocation
Tender notice issued for procurement of materials
Bid finalized for procurement of materials
| Disbursement of Tranche 1 (20% of total) |  |  |  |  | Sahara For Life Trust received 20% of the total budget as 1st Tranche on December 08, 2011.
| Implementation Stage | Establishment of Warehouse
Supply of construction material to construction site
Preparation of Construction materials and construction site
Hiring/engagement of labor
Identification/hiring of specialized labor (for masonry etc.)
Construction of Batch X
Laying of foundation
Setting up walls
Putting roof in place
Finishing stage - install sanitary fittings, window frames, doors
Quality screening for completed batch
Disbursement of Tranche 2 (15% of total)
| Post-implementation Stage | Project completion report
Transfer of possession and issuance of handing-over certificates
Other post-implementation surveys
Contract needs to be restated to incorporate monitoring requirements