## Project Summary
| Project Steps |  |  |  |  | Legend
EC = Evaluation Committee
GC = General Counsel
OD = Operations Director
SM = Screening Manager
PEC = Permanent EC member
PT = Project Team
| Process Description / Responsibilities |  |  |  |  | PTL = Project Team Leader
|  | Primary | Oversight | Timetable | Expected time to complete task | VM = Volunteer Manager
1. Screening | [5 empty] | FT = Fundraising Team
1 | Project Sourced and Added to Pipeline | OD |  | 0 |  | DM = Diligence Manager
2 | Initial NGO - ADP correspondence to complete form according to ADP requirements | OD | DM | 7 | 7
3 | Email Project to EC for evaluation | OD | DM | 8 | 1
3 | EC Evaluates the proposal and makes a call on the project | EC | OD | 22 | 14
4 | Submit Initial Project Summary & Considerations for EC Screening Call | EC | OD / DM | 23 | 1
5 | EC screening call between PECs and ECs. EC submit screening checklist 2 weeks prior to the call to OD | PEC | OD / DM | 37 | 14
37
2. Kick Off
1 | Staff Permanent Evaluation Committee (PEC); EC continue involvement from screening phase | OD | DM | 38 | 1
2 | Staff project team (PT) and Project Team Lead (PTL) once PEC / EC are aligned on project | VM | OD | 41 | 3
3 | Email project details to the entire team (Project PEC, EC, PTL, PT) | EC | OD | 42 | 1
4 | Create project online forum | VM | OD | 42 | 1
5 | Schedule project kick-off call | VM | EC | 42 | 1
5 | Project Team Training & Project Orientation Call | PTL | OD / DM / VM | 47 | 5
6 | EC / PEC convenes prior to kick-off call to reach agreement on key issues | EC | PEC | 49 | 7
7 | Project kick-off call conducted to outline key diligence issues | EC | PEC | 49 | 7
11
2. Diligence
1 | Contact NGO with initial question list | PT | PTL | 56 | 7
2 | Report findings on project forums and prepare project summary form | PT | PTL | 63 | 7
3 | Arrange and conduct site visit and fill out site visit form | PT/VM | PTL | 84 | 21
4 | 1-3 EC calls to discuss findings, open items and follow-up work | PTL | PTL/EC/PEC | 84 | 21
5 | Give project update after every EC call to leadership team and PEC | PEC | EC
6 | Conduct follow-up diligence on key issues (if needed) | PT | PTL | 91 | 7
7 | Report project status/discuss any policy issues with PEC committee during monthly calls | PEC | EC
8 | Develop and finalize key performance metrics and monitoring plan | PTL | EC/PEC | 98 | 7
42
3. Legal
1 | Email project details to ADP's GC for review. (GC's contact information is in the Working Group List tab) | PTL | EC/PEC | 56 | 1
2 | Start drafting project contract which should include monitoring provisions for key operating metrics | PTL | EC/PEC | 86 | 30
31
4. Approval
1 | Project team and ECs conduct final EC call to decide on "go - no go" decision | EC | PEC | 98
5. Closing
1 | Communicate final conclusion to PEC committee,leadership team and ADP treasurer | PEC |  | 99 | 1
2 | Finalize project funds flow and timings. Note that ADP strongly prefers tiered funding | PTL | EC/PEC | 100 | 1
3 | Discuss project with fundraising team and develop fundraising strategy | PTL | EC/PEC | 101 | 1
4 | Create project webpage and e-mail with web team and FT | PTL | EC/PEC | 102 | 1
5 | Finalize project contract and execute | PTL | EC/PEC/OD | 103 | 1
6 | Ensure smooth transfer of funds to NGO; Wire transfer form available online | Treas | PEC/PTL | 104 | 1
7 | Get project, EC and team feedback. Feedback form available on ADP website | VM | PEC | 105 | 1
6. Monitoring
1 | Monitor project performance against key operating metrics developed in the diligence phase | PTL | EC/PEC
2 | Approve subsequent tiered fundings | EC | PEC
1. Screening
3. Legal
2. Diligence
4. Approval
6. Monitoring
5. Closing
2. Kick Off

## Key Contacts
Key Contacts
Title | Name | ( | *
Leadership Team
President | Mubarik Imam |  | mubarik@gmail.com
Operations Director | Haleema Raheel |  | haleema.raheel@developpakistan.org
Volunteer Manager | Khurram Owais |  | khurram.owais@gmail.com
General Counsel | Jessica Hirschfelder |  | jessica@mail.cern.ch; jh@penguinphysics.net
Treasurer | Tarim Wasim |  | twasim@gmail.com
Fundraising Chair | Usman Hassan |  | usmanh@gmail.com
Web Lead | Farhan Ahmed |  | insha@mac.com
Diligence Manager | Shahan Zafar |  | shahan.zafar@gmail.com
Knowledge Capture Manager | Waleed Saraf |  | waleed.safar@gmail.com
Project Screening, Evaluation & Execution
PEC Member | Tarim Wasim |  | twasim@gmail.com
PEC Member | Mubarik Imam |  | mubarik@gmail.com
PEC Member | Saad Hassan |  | saad@hf.com
PEC Member | Waleed Saraf |  | waleed.saraf@gmail.com
PEC Member | Akbar Bhaidani |  | abhaidani@gmail.com
PEC Member | Natasha Qureshi |  | natasha.qureshi@gmail.com
PEC Member | Shahan Zafar |  | shahan.zafar@gmail.com
PTL Member | Farzal Dojki |  | farzal@gmail.com
PTL Member | Owais Rafiq |  | orafiq@gmail.com
PTL Member | Arifa Khandwalla |  | khandwalla.arifa@gmail.com
PTL Member | Waqas Satti |  | waqas.ali.satti@citi.com
PTL Member | Uzaib Saya |  | uzaibsaya@gmail.com
PTL Member | Nabeel Hasnain |  | nabeel541@hotmail.com
PTL Member | Ahmed Makani |  | amakani@vectorcapital.com
EC Member | Mohsin Gadit |  | mohsin.gadit@gmail.com
EC Member | Sheba Najmi |  | shebanajmi@yahoo.com
EC Member | Omar Biabani |  | obiabani@gmail.com
EC Member | AbdurRahim Syed |  | baagarbilla@gmail.com
EC Member | Faris Rahman |  | farisrahman81@gmail.com
EC Member | Tehniyet Kardar |  | tehniyetkardar@gmail.com
EC Member | Aisha Raees |  | aisharaees@gmail.com
EC Member | Minhaj Patel |  | minhaj.patel@gmail.com
EC Member | Ali Farid |  | AliFarid.Khwaja@berenberg.de
EC Member | Qasim Ashraf |  | qasim.ashraf0@gmail.com
EC Member | Janet Southern |  | janet.southern@gmail.com
EC Member | Hiba Rahim |  | hsr137@mail.harvard.edu