## Cover
Association for the Development of Pakistan
Monthly Report
July 2009

## Proposals
Association for the Development of Pakistan | [7 empty] | July 2009
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screening Decision made/ expected?
| CEWS - Health centre | Children Education and Welfare Society | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Lahore | To follow up with NGO and reach screening decision | 2009-04-07 | End of August
| CEWS - IT & job centre | Children Education and Welfare Society | 9075 | Computer training and employment bureau for youth of underprivileged district | Lahore | To follow up with NGO and reach screening decision | 2009-04-14 | End of August
| The Care | The Care | 3570 | Hand pumps installation | Sanghar | To follow up with NGO and reach screening decision | 2009-05-07 | End of August
| RDO - Livestock | Rural Development Organization | 9422.75 | Livestock Community Participation | Gojra | To follow up with NGO and reach screening decision | 2009-07-23 | Pending
| Alif Laila - Book Bus | Alif Laila Book Bus Society | 9556.25 | Mobile Book Bus | Lahore | To follow up with NGO and reach screening decision | 2009-07-27 | Pending
| NEEDS - Poultry | Network for Education & Economic Development Services | 7725 | Sustainable livelihood creation through poultry | Charsadda | Approved from screening, project currently on hold | 2009-05-31 | Approved
|  | Current Month | Previous Month
| Proposals | 5 | 6

## Under Review
Association for the Development of Pakistan | [10 empty] | July 2009
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Project team drafting contract for NGO. | 2008-11-04 | August 2009
| Alqasim | Alqasim Foundation | Distt. Khushab | 9375 | Sustainable Energy - Biogas plants for soon valley community | Sadia Ahmad, Nida Alavi, Ahmad Chaudhary | Natasha Qureshi, Saad Hasan, Waleed Saraf | Incorporating revised terms into the contract. NGO to sign final contract. | 2009-02-27 | August 2009
| SDWA | Sahkar Dost Welfare Association | Naushahro Feroze, Sindh | $9906 | Equipment and supplies for a Thalessimia treatment centre | Arifa Khandwalla, Muahammad Bilal, Farhan Khan | Shahan Zafar, Abdur-Rahim Syed, Hassan Shah | 2ND EC call to be held at the end of August. | 2009-03-15 | September 2009
|  | Current Month | Previous Month
| Total Under Review | 3 | 3
| Expected Disbursements | 13675 | 13675

## In Progress
Association for the Development of Pakistan | [9 empty] | July 2009
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Notes (next milestone, issues etc.)
| Arshad Public School | Arshad Trust | Musloondi, AK | 40567 | Reconstruction of school building destroyed in 2005 earthquake | 2007-11-01 | 31-Mar-09 | 40905 | 0 | All funding is disbursed and project is now complete. Opening ceremony expected end of September.
| AHD | Association for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 2280 | 1032 | First phase report from NGO received and is currently under review. One element of the project i.e. kitchen gardening kits has been delayed due to weather conditions.
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | 2972 | 2028 | In the process of recruiting a volunteer for site visit to assess. This will be followed by disbursement of the next tranche if progress is satisfactory.
| Nilore Science Lab | Ibtida | Nilore, Punjab | 2900 | Equipment and one year's teacher's salary for science lab | 2007-06-01 | TBC | 1500 | 1400 | Awaiting final funding request from NGO.
| Sohb | Sohb Development Society | Lasbela | TBD | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 1245 | n/a | Second tranche to be disbursed, subject to satisfactory site visit.
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17000 | 400 | NGO to purchase final equipment for eye hospital. We are expecting to disburse additional $400 next month.
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 1300 | 2950 | First tranche of funding released in August 09.
| Projects In Progress | 7
| Remaining Funding | 7810

## Volunteers
Association for the Development of Pakistan | [6 empty] | July 2009
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 6 | 3 | 3 | 4 | 4 | 0
| Screening | 6 | 6 | 0 | 0 | 0 | 2
| Project Teams | 9 | 12 | 0 | 6 | 0 | 6
| Evaluation Committee | 6 | 9 | 0 | 6 | 0 | 0
| Fundraising | 8 | 7 | 0 | 0 | 1 | 0
| Web team | 4 | 2 | 0 | 0 | 2 | 0
|  | 39 | 39 | 3 | 16 | 7 | 8
| Sign-ups | 14
| Leads Converted | 9

## Financial
Association for the Development of Pakistan | [5 empty] | July 2009
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations
| Recurring (gross) | 327.51 | 365 | 4102.55 | Lost one donor
| # donors | 11 | 12 | 18
| One-time | 100 | 4916.33 | 9331.33
| # Donations | 1 | 4 | 17
| Total | 427.51 | 5281.33 | 13433.88
| # donors | 12 | 16 | 35
Project Disbursements
| Arshad Public School |  |  | 11429.67
| Sohb |  |  | 1245
| Mansehra Eye Hospital |  |  | 17000
| Total | 0 | 0 | 29674.67
Expenses
| Salaries | 500 | 666.6667 | 4897.6667 | Includes YTD accrued salaries
| Other | 91.39 | 2214 | 2752.88 | Calling Card + PO Box fees
| Total | 591.39 | 2880.6667 | 7650.5467
Available Funds
| General |  |  | 39.6
| Earthquake Redevelopment |  |  | 1.7