## Cover
Association for the Development of Pakistan
Monthly Report
June 2009

## Proposals
Association for the Development of Pakistan | [7 empty] | June 2009
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screening Decision made/ expected?
| CEWS - Health centre | Children Education and Welfare Society | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Lahore | To follow up with NGO and reach screening decision | 2009-04-07 | End of July
| CEWS - IT & job centre | Children Education and Welfare Society | 9075 | Computer training and employment bureau for youth of underprivileged district | Lahore | To follow up with NGO and reach screening decision | 2009-04-14 | End of July
| SDI-PK | SDI-PK | 10000 | Water supply installation for neglected village | Islamabad | More Infromation Requested from NGO | 2009-04-15 | End of July
| The Care | The Care | 3570 | Hand pumps installation | Sanghar | To follow up with NGO and reach screening decision | 2009-05-07 | End of July
| NEEDS - Training | Network for Education & Economic Development Services | 9581.25 | Self-employment through enterprise based training | Charsadda | To follow up with NGO and reach screening decision | 2009-05-23 | Pending
| NEEDS - Poultry | Network for Education & Economic Development Services | 7725 | Sustainable livelihood creation through poultry | Charsadda | To follow up with NGO and reach screening decision | 2009-05-31 | Pending
|  | Current Month | Previous Month
| Proposals | 6 | 11

## Under Review
Association for the Development of Pakistan | [10 empty] | June 2009
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final EC call to be held after consideration of recently revised budget | 2008-11-04 | August 2009
| Alqasim | Alqasim Foundation | Distt. Khushab | 9375 | Sustainable Energy - Biogas plants for soon valley community | Sadia Ahmad, Nida Alavi, Ahmad Chaudhary | Natasha Qureshi, Saad Hasan, Waleed Saraf | First project call - May 16th | 2009-02-27 | August 2009
| SDWA | Sahkar Dost Welfare Association | Naushahro Feroze, Sindh | $9906 | Equipment and supplies for a Thalessimia treatment centre | Arifa Khandwalla, Muahammad Bilal, Farhan Khan | Shahan Zafar, Abdur-Rahim Syed, Hassan Shah | First project call - 19th July | 2009-03-15 | August 2009
| RDO | Rural Development Organization | Toba Tek Singh, Punjab | $9971 | Plastic bag collection and recycling to produce marketable products | Waqas Satti, Izhar Siddiqui, Shafaq Varghese | Tarim Wasim, Mansoor Qureshi, Nosheen Ali | First project call - 12th July | 2009-03-30 | August 2009
|  | Current Month | Previous Month
| Total Under Review | 4 | 4
| Expected Disbursements | $13,675 | $13,675

## In Progress
Association for the Development of Pakistan | [8 empty] | June 2009
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Notes (next milestone, issues etc.)
| Arshad Public School | Arshad Trust | Musloondi, AK | 40567 | Reconstruction of school building destroyed in 2005 earthquake | 2007-11-01 | 31-Mar-09 | 36967 | Waiting for completion of floors and electrical fittings before funding furniture. Opening ceremony expected end of Summer 2009.
| AHD | Assoc for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 3312 | Site visit volunteer staffed, visit date being agreed with NGO
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | $3750 | To visit NGO and assess progress since last payment, disburse next tranche if satisfactory
| Nilore Science Lab | Ibtida | Nilore, Punjab | 2900 | Equipment and one year's teacher's salary for science lab | 2007-06-01 | TBC | $1500 | Awaiting final funding request from NGO, following completion of project
| Sohb | Sohb Development Society | Lasbela | 5600 | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 5600 | First tranche paid, project being rebudgeted due to increase in material costs and cancellation of training workshops; to be discussed with NGO and reworked.
| LRBT | LRBT | Mansehra | 17000 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17000 | Project approved for funding, first tranche paid out to NGO.
| Kharo Chann | Action for Humanitarian Development | Thatta | 5000 | Model community school | 2009-05-01 | TBC | $0 | Contract finalised, NGO to send final contract.
|  | Current Month | Previous Month
| Projects In Progress | 7 | 7
| Remaining Funding | 16500 | 16500

## Volunteers
Association for the Development of Pakistan | [6 empty] | June 2009
Volunteers
|  | Staffed |  | Openings |  | New Recruits
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 3 | 3 | 4 | 0 | 0 | 3
| Screening | 6 | 6 | 2 | 0 | 2 | 0
| Project Teams | 12 | 15 | 6 | 0 | 6 | 5
| Evaluation Committee | 9 | 11 | 6 | 0 | 0 | 4
| Fundraising | 7 | 6 | 0 | 0 | 0 | 0
| Web team | 2 | 1 | 0 | 0
|  | 39 | 42 | 16 | 0 | 8 | 12

## Financial
Association for the Development of Pakistan | [5 empty] | June 2009
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations
| Recurring (gross) | 365 | 380 | 3775.04 | Lost one donor
| # donors | 12 | 13 | 18
| One-time | 4916.33 | 430 | 9231.33 | Includes E3 donation for Kharo Chan
| # donors | 4 | 5 | 16
| Total | 5281.33 | 810 | 13006.37
| # donors | 16 | 18 | 34
Project Disbursements
| Arshad Public School |  | 3929.67 | 11429.67
| Sohb |  |  | 1245
| Mansehra Eye Hospital |  |  | 17000
| Total | 0 | 3929.67 | 29674.67
Expenses
| Salaries | 666.6667 | 1000 | 4397.6667 | Includes YTD accrued salaries
| Other | 2214 | 35 | 2661.49 | IRS penalty for late 2006 filing - will be covered by specific donation in July
| Total | 2880.6667 | 1035 | 7059.1567
Available Funds
| General |  |  | $40k
| Earthquake Redevelopment |  |  | 1.8