## Cover
Association for the Development of Pakistan
Monthly Report
August 2009

## Proposals
Association for the Development of Pakistan | [7 empty] | August 2009
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screening Decision made/ expected?
| CEWS - Health centre | Children Education and Welfare Society | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Lahore | To follow up with NGO and reach screening decision | 2009-04-07 | End of September
| CEWS - IT & job centre | Children Education and Welfare Society | 9075 | Computer training and employment bureau for youth of underprivileged district | Lahore | To follow up with NGO and reach screening decision | 2009-04-14 | End of September
| The Care | The Care | 3570 | Hand pumps installation | Sanghar | To follow up with NGO and reach screening decision | 2009-05-07 | End of September
| RDO - Livestock | Rural Development Organization | 9422.75 | Livestock Community Participation | Gojra | To follow up with NGO and reach screening decision | 2009-07-23 | Pending
| Alif Laila - Book Bus | Alif Laila Book Bus Society | 9556.25 | Mobile Book Bus | Lahore | To follow up with NGO and reach screening decision | 2009-07-27 | Pending
| NEEDS - Poultry | Network for Education & Economic Development Services | 7725 | Sustainable livelihood creation through poultry | Charsadda | Approved from screening, project currently on hold | 2009-05-31 | Approved
| Qadam | Qadam Organization | 9375 | Health care for affected people in Buner | District Buner | To follow up with NGO and reach screening decision | 2009-07-15 | Pending
| IBP | Institute of Behavioral Psychology School of Special Education | 10000 | Printing press for mentally handicapped and slow learners, targetting lower income groups of Karachi | Karachi | To follow up with NGO and reach screening decision | 2009-09-09 | Pending
| Pakuca | Pak United Christian Association | 6123 | Extension of health projects in Hansa Colony (Kachi Abadi) in Islamabad | Islamabad | To follow up with NGO and reach screening decision | 2009-09-12 | Pending
| YAP | Youth Action for Pakistan | 3325 | Girls access to information through internet facility at Jacobabad city | Jacobabad | To follow up with NGO and reach screening decision | 2009-09-13 | Pending
| Faroog-e-Taleem | Faroog -e- taleem Society | 9969 | 5 Bed awami khidmat mother and child health care center in Latifabad | Latifabad - District Mianwali | To follow up with NGO and reach screening decision | 2009-09-09 | Pending
| Feeder | Federation for Environment, Education, Development and Equal Rights | 9737 | Improving the life status of vulnerable women in the earthquake stricken area of Mansehra through vocational training | Mansehra | To follow up with NGO and reach screening decision | 2009-09-15 | Pending
| CCF | Children Cancer Foundation Pakistan | 7500 | To establish pediatric ICU for infection control in Cancer Hospital | Karachi | To follow up with NGO and reach screening decision | 2009-09-13 | Pending
| Al-Shifa Trust | Al-Shifa Trust Eye Hospital | 9375 | Restoring the Sight of 15 Blind Persons through Corneal Grafting | Rawalpindi | To follow up with NGO and reach screening decision | 2009-09-12 | Pending
| Sahil | Sahil | 10000 | Teachers training in primary schools on Child Body Protection (Meri Hifazat) | Naseerabad, Khairpur, Kasoor, Hari pur | To follow up with NGO and reach screening decision | 2009-09-09 | Pending
| INSAN | Integrated Social Aid Net work ( INSAN) | 9622 | To enhance the economic status of 300 women belonging to union council Satbani, Tehsil Balakot, District Mansehra within one year. | Mansehra | To follow up with NGO and reach screening decision | 2009-09-10 | Pending
| Oxfords Foundation | Oxfords Foundation | 6128 | Computer Lab Up-gradation in Oxfords School & College, University Town Peshawar | Peshawar | To follow up with NGO and reach screening decision | 2009-08-28 | Pending
| MRSTAH | MRSTAH - Swat | 9987 | Computer Training Center for the Marginalized Students of District Swat | Swat | To follow up with NGO and reach screening decision | 2009-08-31 | Pending
|  | Current Month | Previous Month
| Proposals | 18 | 5

## Under Review
Association for the Development of Pakistan | [10 empty] | August 2009
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team | 2008-11-04 | October 2009
| Alqasim | Alqasim Foundation | Distt. Khushab | 9375 | Sustainable Energy - Biogas plants for soon valley community | Sadia Ahmad, Nida Alavi, Ahmad Chaudhary | Natasha Qureshi, Saad Hasan, Waleed Saraf | Incorporating NGO feedback into the contract. Final project call scheduled for 19th September to finalize the contract. | 2009-02-27 | September 2009
| SDWA | Sahkar Dost Welfare Association | Naushahro Feroze, Sindh | $9906 | Equipment and supplies for a Thalessimia treatment centre | Arifa Khandwalla, Muahammad Bilal, Farhan Khan | Shahan Zafar, Abdur-Rahim Syed, Hassan Shah | EC call held in early September. Decsion on project expected by mid-October. | 2009-03-15 | October 2009
|  | Current Month | Previous Month
| Total Under Review | 3 | 3
| Expected Disbursements | 13675 | 13675

## In Progress
Association for the Development of Pakistan | [10 empty] | August 2009
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Notes (next milestone, issues etc.)
| Arshad Public School | Arshad Trust | Musloondi, AK | 40567 | Reconstruction of school building destroyed in 2005 earthquake | 2007-11-01 | 31-Mar-09 | 40905 | 0 |  | All funding is disbursed and project is now complete. Opening ceremony expected on October 1st.
| AHD | Association for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 2280 | 1032 | TBD | First phase report from NGO received and is currently under review. One element of the project i.e. kitchen gardening kits has been delayed due to weather conditions.
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | 2972 | 2028 | TBD | In the process of recruiting a volunteer for site visit to assess. This will be followed by disbursement of the next tranche if progress is satisfactory.
| Nilore Science Lab | Ibtida | Nilore, Punjab | 2900 | Equipment and one year's teacher's salary for science lab | 2007-06-01 | TBC | 1500 | 1400 | TBD | Awaiting final funding request from NGO.
| Sohb | Sohb Development Society | Lasbela | TBD | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 1245 | n/a | TBD | Second tranche to be disbursed, subject to satisfactory site visit.
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17000 | 400 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | NGO to purchase final equipment for eye hospital. We are expecting to disburse additional $400 next month.
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 1300 | 2950 | Progress report to be submitted by AHD on 31st September 2009 | First tranche of funding released in August 09.
| Projects In Progress | 7
| Remaining Funding | 7810

## Volunteers
Association for the Development of Pakistan | [6 empty] | August 2009
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 6 | 6 | Open | 3 | 6 | 4
| Screening | 2 | 6 | 0 | 0 | 0 | 0
| Project Teams | 9 | 9 | 0 | 0 | 0 | 0
| Evaluation Committee | 7 | 6 | 4 | 6 | 0 | 0
| Fundraising | 9 | 8 | Open | 0 | 1 | 1
| Web team | 3 | 2 | 0 | 0 | 1 | 2
|  | 36 | 37 | 4 | 16 | 8 | 7
| Sign-ups | 20
| Leads Converted* | 12
*Refers to volunteers who have been staffed or offered a position to get started

## Financial
Association for the Development of Pakistan | [5 empty] | August 2009
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations
| Recurring (gross) | 385 | 327.51 | 3157 | Added two recurring donors
| # donors | 13 | 11 | 20
| One-time | 11013.91 | 100 | 20345.24 | Includes $1.9k from NY fundraiser for Sohb training project
| # Donations | 20 | 1 | 37
| Total | 11398.91 | 427.51 | 23502.24
| # donors | 33 | 12 | 57
Project Disbursements
| Arshad Public School |  |  | 11429.67
| Kharochan School | 1300 |  | 1300
| Sohb |  |  | 1245
| Mansehra Eye Hospital |  |  | 17000
| Total | 1300 | 0 | 30974.67
Expenses
| Salaries | 813 | 500 | 5710.6667 | Includes YTD accrued salaries
| Other | 58 | 91.39 | 2810.88 | Wire + filing fees
| Total | 871 | 591.39 | 8521.5467
Available Funds
| General |  |  | 50.2
| Earthquake Redevelopment |  |  | 1.7

## Other Initiatives
Association for the Development of Pakistan |  |  |  |  | August 2009
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization and roll out of new website | Technical resources being used: Content Writer to assist with developing a blueprint for the new website | Conceptualization and development of blueprint; to push for new website to go live in the next month | 2009-10-01
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as | Mubarik Imam currently corresponding with the appropriate legislative auhorities to ensure | Mubarik to speak with a lawyer in Karachi to finalize the legal process and push for outcome | 2009-10-01
| Training Materials | Budget Diligence: To be used for brand orientation and for training of future EC's and PT's. Modules: PT and EC training framework that will capture organizational training, project diligence and implementation. | Budget Diligence: Shahan Zafar 11111111111111111111111111111Modules: PEC1111 | Budget diligence being tweaked by Shahan. PEC members currently taking a stab at different modules within the PT and EC training framework. | 2009-10-01
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf | Two volunteers currently recruited for data entry which will be followed by analysis | 2009-10-01
| Volunteer Feedback Survey | Volunteer Feedback Survey rolled out to understand their overall experience and enhance ADP's diligence model (this will help in volunteer retention strategy) | Khurram Owais | Survey rolled out to 6 PTL's. Currently 4 PTL's have taken the survey; to reach out to the remaining folks. Survey results to be analysed by ADP leadership team | 2009-10-01
| SOP for Chapter Commencement | Chapter Orientation Manual: Guidlines for chapter co-ordnators to support chapter evolution, structure and scalability | Khurram Owais | To roll out the manual for discussion/ changes with leadership team; to reach out to chapter co-ordinators and go over the manual with them | 2009-09-01
| Fundraising: Capital Campaign | Capital Campaign:To raise funds for ADP, pushing our 2-3yr growth plans | Usman Hasan | Shahan Zafar to put PEC page together; Shahan and Usman to incorpoarte PEC page link into the capital campaign page. Recruit volunteers in the US to pitch to corporations; Stephen Dimon compiling a list of institutions | 2009-10-01
| Structural Changes | Evaluation Committee members to transition into screeners. Decentralization of roles to add to the efficiency of the process flow. | Shahan Zafar, Waleed Saraf | Shahan, Waleed and Haleema to roll out/ classify the process. Second call with EC's to be scheduled in the third week of September. | 2009-09-01