## Cover
Association for the Development of Pakistan
Monthly Report
September 2009

## Proposals
Association for the Development of Pakistan | [7 empty] | September 2009
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screening Decision made/ expected?
| CEWS - IT & job centre | Children Education and Welfare Society | 9075 | Computer training and employment bureau for youth of underprivileged district | Lahore | To follow up with NGO and reach screening decision | 2009-04-14 | End of September
| RDO - Livestock | Rural Development Organization | 9422.75 | Livestock Community Participation | Gojra | To follow up with NGO and reach screening decision | 2009-07-23 | Pending
| Alif Laila - Book Bus | Alif Laila Book Bus Society | 9556.25 | Mobile Book Bus | Lahore | To follow up with NGO and reach screening decision | 2009-07-27 | Pending
| NEEDS - Poultry | Network for Education & Economic Development Services | 7725 | Sustainable livelihood creation through poultry | Charsadda | Approved from screening, project currently on hold | 2009-05-31 | Approved
| Qadam | Qadam Organization | 9375 | Health care for affected people in Buner | District Buner | To follow up with NGO and reach screening decision | 2009-07-15 | Pending
| Pakuca | Pak United Christian Association | 6123 | Extension of health projects in Hansa Colony (Kachi Abadi) in Islamabad | Islamabad | To follow up with NGO and reach screening decision | 2009-09-12 | Pending
| YAP | Youth Action for Pakistan | 3325 | Girls access to information through internet facility at Jacobabad city | Jacobabad | To follow up with NGO and reach screening decision | 2009-09-13 | Pending
| Faroog-e-Taleem | Faroog -e- taleem Society | 9969 | 5 Bed awami khidmat mother and child health care center in Latifabad | Latifabad - District Mianwali | To follow up with NGO and reach screening decision | 2009-09-09 | Pending
| Feeder | Federation for Environment, Education, Development and Equal Rights | 9737 | Improving the life status of vulnerable women in the earthquake stricken area of Mansehra through vocational training | Mansehra | To follow up with NGO and reach screening decision | 2009-09-15 | Pending
| CCF | Children Cancer Foundation Pakistan | 7500 | To establish pediatric ICU for infection control in Cancer Hospital | Karachi | To follow up with NGO and reach screening decision | 2009-09-13 | Pending
| Al-Shifa Trust | Al-Shifa Trust Eye Hospital | 9375 | Restoring the Sight of 15 Blind Persons through Corneal Grafting | Rawalpindi | To follow up with NGO and reach screening decision | 2009-09-12 | Pending
| Sahil | Sahil | 10000 | Teachers training in primary schools on Child Body Protection (Meri Hifazat) | Naseerabad, Khairpur, Kasoor, Hari pur | To follow up with NGO and reach screening decision | 2009-09-09 | Pending
| INSAN | Integrated Social Aid Net work ( INSAN) | 9622 | To enhance the economic status of 300 women belonging to union council Satbani, Tehsil Balakot, District Mansehra within one year. | Mansehra | To follow up with NGO and reach screening decision | 2009-09-10 | Pending
| Oxfords Foundation | Oxfords Foundation | 6128 | Computer Lab Up-gradation in Oxfords School & College, University Town Peshawar | Peshawar | To follow up with NGO and reach screening decision | 2009-08-28 | Pending
| MRSTAH | MRSTAH - Swat | 9987 | Computer Training Center for the Marginalized Students of District Swat | Swat | To follow up with NGO and reach screening decision | 2009-08-31 | Pending
| SCEI | Special Children's Educational Institute | 3536 | Development of Special Ed school in Karachi | Karachi | To follow up with NGO and reach screening decision | 2009-10-03 | Pending
| KWS | Kuchlak Welfare Society | 9546 | Socio econmic empowerment as a strategy to end violence | Quetta | To follow up with NGO and reach screening decision | 2009-09-30 | Pending
| TWO | Today's Woman Organization | 9875 | Establishment of a womens vocational center in Ziarat | Balochistan | To follow up with NGO and reach screening decision | 2009-10-01 | Pending
| SWS | Sahara Welfare Society | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | District Ghotki, Sindh | To follow up with NGO and reach screening decision | 2009-10-03 | Pending
| NIDA-Pakistan | National Integrated & Development Association | 9756 | Psychosocial Therapy for Conflict affected areas Children and women in 10 Conflict affected UCs of district Shangla | Shangla, NWFP | To follow up with NGO and reach screening decision | 2009-10-03 | Pending
|  | Current Month | Previous Month
| Proposals | 20 | 18

## Under Review
Association for the Development of Pakistan | [10 empty] | September 2009
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team | 2008-11-04 | October 2009
| SDWA | Sahkar Dost Welfare Association | Naushahro Feroze, Sindh | $9906 | Equipment and supplies for a Thalessimia treatment centre | Arifa Khandwalla, Muahammad Bilal, Farhan Khan | Shahan Zafar, Abdur-Rahim Syed, Hassan Shah | EC call held in early September. Decsion on project expected by mid-October. | 2009-03-15 | October 2009
| CEWS-Healthcare | Children Education and Welfare Society | Lahore | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | To be staffed | To be staffed | Teams to be staffed by mid-October | 2009-04-07 | TBD
| CARE | The CARE | Sanghar | 3480 | Hand pump installation in three villages of District Sanghar | To be staffed | To be staffed | Teams to be staffed by mid-October | 2009-05-07 | TBD
|  | Current Month | Previous Month
| Total Under Review | 4 | 3
| Expected Disbursements | 4300 | 4300

## In Progress
Association for the Development of Pakistan | [10 empty] | September 2009
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Notes (next milestone, issues etc.)
| Arshad Public School | Arshad Trust | Musloondi, AK | 40567 | Reconstruction of school building destroyed in 2005 earthquake | 2007-11-01 | 31-Mar-09 | 40905 | 0 |  | All funding is disbursed and project is now complete. Opening ceremony took place in the first week of Oct.
| AHD | Association for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 2280 | 1032 | TBD | First phase report from NGO received and is currently under review. One element of the project i.e. kitchen gardening kits has been delayed due to weather conditions.
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | 2972 | 2028 | TBD | Site visit conducted on 07-Sep. Overall feedback was postive an final tranche will be released in the second week of October.
| Nilore Science Lab | Ibtida | Nilore, Punjab | 2900 | Equipment and one year's teacher's salary for science lab | 2007-06-01 | TBC | 1500 | 1400 | TBD | Awaiting final funding request from NGO.
| Sohb | Sohb Development Society | Lasbela | TBD | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 1245 | n/a | TBD | Second tranche to be disbursed, subject to satisfactory site visit.
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17000 | 400 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | NGO to purchase final equipment for eye hospital. We are expecting to disburse additional $400.
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 1300 | 2950 | Progress report to be submitted by AHD on 31st September 2009 | First tranche of funding released in August 09.
| Al-Qasim | Al Qasim Foundation | District Khushab] | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | First trance expected to be disbursed in the second week of October
| Projects In Progress | 8
| Remaining Funding | 15736

## Volunteers
Association for the Development of Pakistan | [6 empty] | September 2009
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 10 | 6 | Open | Open | 3 | 6
| Screening | 0 | 2 | 0 | 0 | 0 | 0
| Project Teams | 9 | 9 | 0 | 0 | 0 | 0
| Evaluation Committee | 7 | 7 | 5 | 4 | 0 | 0
| Fundraising | 9 | 9 | Open | Open | 1 | 1
| Web team | 3 | 3 | 0 | 0 | 0 | 1
|  | 38 | 36 | 5 | 4 | 4 | 8
| Sign-ups | 19
| Leads Converted* | 10
*Refers to volunteers who have been staffed or offered a position to get started

## Financial
Association for the Development of Pakistan | [5 empty] | September 2009
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations
| Recurring (gross) | 360 | 385 | 3517 | Lost one donor
| # donors | 12 | 13 | 20
| One-time | 2034.45 | 11013.91 | 22379.69 | Includes $1.9k from NY fundraiser for Sohb training project
| # Donations | 5 | 20 | 42
| Total | 2394.45 | 11398.91 | 25896.69
| # donors | 17 | 33 | 62
Project Disbursements
| Arshad Public School |  |  | 11429.67
| Kharochan School |  | 1300 | 1300
| Sohb |  |  | 1245
| Mansehra Eye Hospital |  |  | 17000
| Total | 0 | 1300 | 30974.67
Expenses
| Salaries | 937.5 | 813 | 6648.1667 | Includes YTD accrued salaries
| Other | 63 | 58 | 2873.88 | Wire + filing fees
| Total | 1000.5 | 871 | 9522.0467
Available Funds
| General |  |  | 51.3
| Earthquake Redevelopment |  |  | 1.7

## Other Initiatives
Association for the Development of Pakistan |  |  |  |  | September 2009
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization and roll out of new website | Technical resources being used: Content Writer and graphic Designer to assist with developing a blueprint for the new website | Conceptualization and development of blueprint; to push for new website to go live ASAP | 2009-11-09
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as | Mubarik Imam currently corresponding with the appropriate legislative auhorities | Mubarik to speak with a lawyer in Karachi to finalize the legal process and push for outcome | 2009-10-01
| Training Materials | Budget Diligence: To be used for brand orientation and for training of future EC's and PT's. Modules: PT and EC training framework that will capture organizational training, project diligence and implementation. | Budget Diligence: Shahan Zafar 11111111111111111111111111111Modules: PEC1111 | Budget diligence being tweaked by Shahan. PEC members currently taking a stab at different modules within the PT and EC training framework. | 2009-10-01
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf | Two volunteers currently recruited for data entry which will be followed by analysis | (Nov-Dec)09
| Volunteer Feedback Survey | Volunteer Feedback Survey rolled out to understand their overall experience and enhance ADP's diligence model (this will help in volunteer retention strategy) | Khurram Owais | Survey rolled out to 6 PTL's. Survey results to be analysed by ADP leadership team | 2009-10-01
| SOP for Chapter Commencement | Chapter Orientation Manual: Guidlines for chapter co-ordnators to support chapter evolution, structure and scalability | Khurram Owais | To roll out the manual for discussion/ changes with leadership team; to reach out to chapter co-ordinators and go over the manual with them | 2009-10-09
| Fundraising: Capital Campaign | Capital Campaign:To raise funds for ADP, pushing our 2-3yr growth plans Human Development Founddation: ADP nominated for the HDF annual award, details available at www.hdf.org.pk/ | Usman Hasan | Shahan Zafar to put PEC page together; Shahan and Usman to incorpoarte PEC page link into the capital campaign page. Recruit volunteers in the US to pitch to corporations; Stephen Dimon compiling a list of institutions | 2009-10-01
| Structural Changes | Evaluation Committee members to transition into screeners. Decentralization of roles to add to the efficiency of the process flow. | Shahan Zafar, Waleed Saraf | Shahan, Waleed and Haleema to roll out/ classify the process. EC recruitment is ongoing. We are recruiting fresh EC's as well as transitioning some of our existing volunteers into this role | 2009-10-09