## Cover
Association for the Development of Pakistan
Monthly Report
October 2009

## Proposals
Association for the Development of Pakistan | [8 empty] | October 2009
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| NEEDS - Poultry | Network for Education & Economic Development Services | 7725 | Sustainable livelihood creation through poultry | Charsadda | Approved from screening, project currently on hold | 2009-05-31 | - | Approved
| YAP | Youth Action for Pakistan | 3325 | Girls access to information through internet facility at Jacobabad city | Jacobabad | Approved; Project on hold as feaseability is being considered | 2009-09-13 | Sheba Najmi | Approved
| Oxfords Foundation | Oxfords Foundation | 6128 | Computer Lab Up-gradation in Oxfords School & College, University Town Peshawar | Peshawar | To follow up with NGO and reach screening decision | 2009-08-28 | Natasha Qureshi | Pending
| SCEI | Special Children's Educational Institute | 3536 | Development of Special Ed school in Karachi | Karachi | To follow up with NGO and reach screening decision | 2009-10-03 | Mohsin Gadit | Pending
| KWS | Kuchlak Welfare Society | 9546 | Socio econmic empowerment as a strategy to end violence | Quetta | To follow up with NGO and reach screening decision | 2009-09-30 | Tehniyet Kardar | Pending
| TWO | Today's Woman Organization | 9875 | Establishment of a womens vocational center in Ziarat | Balochistan | To follow up with NGO and reach screening decision | 2009-10-01 | Qasim Ashraf | Pending
| SWS | Sahara Welfare Society | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | District Ghotki, Sindh | Approved; Project on hold as feaseability is being considered | 2009-10-03 | Faris Rahman | Approved
| SEHER | Society for Empowering Human Resource | 8433 | Installation of CCTV's in women's and juvenille prisons in Quetta, Much and Gaddiani Jails | Balochistan | To follow up with NGO and reach screening decision | 2009-10-15 | Minhaj Patel | Pending
|  | Current Month | Previous Month
| Proposals | 8 | 20

## Under Review
Association for the Development of Pakistan | [10 empty] | October 2009
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team; EC considering pre-funding site vist option prior to contract finalization | 2008-11-04 | November 2009
| SDWA | Sahkar Dost Welfare Association | Naushahro Feroze, Sindh | $9906 | Equipment and supplies for a Thalessimia treatment centre | Arifa Khandwalla, Muahammad Bilal, Farhan Khan | Shahan Zafar, Abdur-Rahim Syed, Hassan Shah | EC call held in early November. We expect another EC call in the first week of December. | 2009-03-15 | November 2009
| CEWS-Healthcare | Children Education and Welfare Society | Lahore | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Uzaib Saya, Hassam Hussain, Ahsan Hussain, Ahsan Tanveer | Natasha Qureshi, Aisha Raees | Project kick of call on November 8th; PT carrying out diligence. First project team call scheduled for Nov 29th. | 2009-04-07 | December 2009
| CARE | The CARE | Sanghar | 3480 | Hand pump installation in three villages of District Sanghar | Ahmad Makani, Momin Ali Khan, Shireen Lakhani | Saad Hasan, Faris Rahman | Project kick off call held on November 8th; PT carrying out diligence. First project team call scheduled for Nov 28th. | 2009-05-07 | December 2009
| CCF | Children Cancer Foundation Pakistan | Karachi | 7500 | To establish pediatric ICU for infection control in a Cancer Hospital in karachi | Waqas Satti, Minza Zahid, Asher Safvi | Akbar Bhaidani, Omar Biabani | Project kick off call held on November 19th; PT carrying out diligence. First project team call scheduled for Dec 12th | 2009-09-13 | January 2010
| Alif Laila | Alif Laila | Lahore | 9556 | Mobile book bus - library | To be staffed | To be staffed | Project kick of call to be scheduled for November 29th | 2009-07-27 | -
|  | Current Month | Previous Month
| Total Under Review | 6 | 4
| Expected Disbursements | 4300 | 4300

## In Progress
Association for the Development of Pakistan | [10 empty] | October 2009
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Notes (next milestone, issues etc.)
| AHD | Association for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 2280 | 1032 | TBD | First phase report from NGO received and is currently under review. One element of the project i.e. kitchen gardening kits has been delayed due to weather conditions.
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | 4176 | 0 | TBD | Site visit conducted on 07-Sep. Overall feedback was postive and the final tranche of Rs. 100,000 was released on November 20th.
| Nilore Science Lab | Ibtida | Nilore, Punjab | 2900 | Equipment and one year's teacher's salary for science lab | 2007-06-01 | TBC | 1500 | 1400 | TBD | Awaiting final funding request from NGO.
| Sohb | Sohb Development Society | Lasbela | TBD | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 1245 | n/a | TBD | Site visit conducted in mid-November. We have decided to put the second disbursement on hold as Sohb has not been able to identify a market and train a critical mass of women
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17480 | 0 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | NGO to purchase final equipment for eye hospital: We have disbursed a final tranche of Rs. 37,530 in the first week of November
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 1300 | 2950 | Progress report to be submitted by AHD on 31st September 2009 | Second tranche of funding (Rs. 115,000) disbursed on November 19th.
| Al-Qasim | Al Qasim Foundation | District Khushab] | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | First tranche of RS. 99,000 disbursed in the last week of October.
| Projects In Progress | 7
| Remaining Funding | 13308

## Volunteers
Association for the Development of Pakistan | [6 empty] | October 2009
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 11 | 10 | Open | Open | 1 | 3
| Project Teams | 18 | 9 | 0 | 0 | 9 | 0
| Evaluation Committee | 12 | 7 | 5 | 4 | 5 | 0
| Fundraising | 9 | 9 | Open | Open | 0 | 1
| Web team | 4 | 3 | 0 | 0 | 1 | 0
|  | 54 | 38 | 5 | 4 | 16 | 4
| Sign-ups | 21
| Leads Converted* | 13
*Refers to volunteers who have been staffed or offered a position to get started

## Financial
Association for the Development of Pakistan | [5 empty] | October 2009
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations
| Recurring (gross) | 300.33 | 360 | 3517 | Lost two donors
| # donors | 10 | 12 | 20
| One-time | 0 | 2034.45 | 20345.24
| # Donations | 0 | 5 | 37
| Total | 300.33 | 2394.45 | 23862.24
| # donors | 10 | 17 | 57
Project Disbursements
| Al-Qasim Biogas | 1200 |  | 1200 | First tranche for 2 plants disbursed
| Arshad Public School |  |  | 11429.67
| Kharochan School |  |  | 1300
| Sohb |  |  | 1245
| Mansehra Eye Hospital |  |  | 17000
| Total | 1200 | 0 | 32174.67
Expenses
| Salaries | 987.6543 | 937.5 | 6698.321 | Includes YTD accrued salaries
| Other | -21 | 63 | 2789.88 | Credit from Schwab for wire fees
| Total | 966.6543 | 1000.5 | 9488.201
Available Funds
| General |  |  | 43
| Earthquake Redevelopment |  |  | 1.7

## Initiatives
Association for the Development of Pakistan |  |  |  |  | October 2009
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization and roll out of new website | Technical resources being used: Content Writer: Sana Kazmi, Haleema and Khurram Graphic Designer: Shajee Technical Aspect: Farhan and Mansoor | Content development, design and layout + technical development of new website in progress; Haleema to circulate workplan and montior reporting dates and delivery | 2010-01-01
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP is now registered in Pakistan under the Companies Societies Act-1807. Lawyer in Lahore to send us the registration certificate and attached documents in the week following the 23rd of November | 2009-11-01
| Training Materials | Budget Diligence: To be used for brand orientation and for training of future EC's and PT's. Modules: PT and EC training framework that will capture organizational training, project diligence and implementation. | Budget Diligence: Shahan Zafar 11111111111111111111111111111Modules: PEC1111 | Budget diligence being tweaked by Shahan. PEC members currently taking a stab at different modules within the PT and EC training framework. | 2009-11-01
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf | Two volunteers currently recruited for data entry which will be followed by analysis | 2009-12-09
| Volunteer Feedback Survey | Volunteer Feedback Survey rolled out to understand their overall experience and enhance ADP's diligence model (this will help in volunteer retention strategy) | Khurram Owais | Survey rolled out to 6 PTL's. Survey results to be analysed by ADP leadership team | 2009-11-09
| Fundraising: Capital Campaign | Capital Campaign:To raise funds for ADP, pushing our 2-3yr growth plans; Identification of fundraising leads globally to facilitate the capital campaign. Human Development Foundation: ADP nominated for the HDF annual award, details available at www.hdf.org.pk/ Fundraisng Content Writer: To identify a fundraising content writer that is able to turn up content on short notice | Usman Hasan | Recruit volunteers in the US to pitch to corporations; To mobilize fundraising leads in the US and UK to meet capital campaign objectives; Stephen Dimon compiling a list of institutions Additionally, we are looking at making a decision on assigning a fundraising content writer in the next two weeks | 2009-12-09
| Monthly Volunteer Orientation Call | To have a monthly/ bi-monthly call with a brief induction to be led initially by Tarim Wasim and there on by different members of the leadership team. The particpants of the call will all be fresh volunteer sign ups for that specific month | Tarim Wasim and Leadership Team Members | To schedule the first Volunteer Orientation call on the 9th/10th of January | 2010-01-01
| Policy Changes | To sharpen sourcing strategy and focus on NGO's with more specialized bearings. The desired goal is to work with the best partners (non-profits we are excited to work with). | Sourcing: Haleema Raheel Training: Shahan Zafar | Haleema to gather/ compile data for 20-30 non-profits ADP would be excited to enter into long term partnership with. Shahan to update EC's on new selective strategy plus tweak forms and training materials to reflect selection criteria. | 2009-12-09