## Cover
Association for the Development of Pakistan
Monthly Report
January 2010

## Proposals
Association for the Development of Pakistan | [8 empty] | January 2010
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| NEEDS - Poultry | Network for Education & Economic Development Services | 8352 | Sustainable livelihood creation through poultry | Charsadda | Proposal revised and resent by NGO | 2010-02-20 | - | On hold
| NEEDS - EBT | Network for Education & Economic Development Services | 9125 | Technical skills training for 45 individuals in Charsadda | Charsadda | Project Currently on Hold | 2009-05-31 | - | On hold
| Amir Public School | Nia Ujala | 2409 | Development of a school in Gujranwala (set up of classroom's) | Gujranwala | NGO has revised the proposal and resent it to us | 2010-02-08 | Ali Farid | 2010-02-22
| AWS | Adam Welfare Society | 9302 | Poverty reduction of 80 poor and marginalized families in the remote and back ward area of Hasilpur -District Bahawalpur Punjab Pakistan through goat farming | Bhawalpur | To follow up with NGO and reach screening decision | 2010-02-01 | Tehniyet kardar | 2010-02-22
| RHD | Rural Health and Development Foundation | 6073 | Establishment of a school in Farsash Town (slum in the outskirts of Islamabad) | Islamabad | To follow up with NGO and reach screening decision | 2010-02-01 | Aisha Raees | 2010-02-22
| CCSP | Civil Society Support Programme | 9518 | Establishment of a computer center for unemployed women in Qasimabad (slum) | Hyderabad | To follow up with NGO and reach screening decision | 2009-10-12 | Qasim Ashraf | 2010-02-22
| HELP | Health Education and Legal Protection | 9411 | Poverty reduction of poor and marginalized families in a remote and backward area of Multan District through dairy farming | Multan | To follow up with NGO and reach screening decision | 2010-02-01 | Omar Biabani | 2010-02-22
| FEEDER | Federation for Environment, Education, Development and Equal Rights | 10000 | Community Plantation for Relief to the Communities in Fuel Wood Need. | Mansehra | To follow up with NGO and reach screening decision | 2010-02-04 | Sohaib Arshad | 2010-02-22
| Koohi Goth | Health, Education, Environment & Sustainable Development | 10000 | Training of 25 traditional birth attendants | Deh Landi, Karachi | To follow up with NGO and reach screening decision | 2010-02-17 | To be staffed | Pending
| HEED | Health, Education, Environment & Sustainable Development | 10000 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Laterines in total) | Sokar, AJK | To follow up with NGO and reach screening decision | 2010-02-17 | Janet Southern | 2010-03-01
|  | Current Month | Previous Month
| Proposals | 10 | 9

## Under Review
Association for the Development of Pakistan | [11 empty] | January 2010
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Potential Disbursement (Y/ N)
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team; Site visit pending. | 2008-11-04 | February 2009 | Y
| SDWA | Sahkar Dost Welfare Association | Naushahro Feroze, Sindh | $9906 | Equipment and supplies for a Thalessimia treatment centre | Arifa Khandwalla, Muahammad Bilal, Farhan Khan | Shahan Zafar, Abdur-Rahim Syed, Hassan Shah | DROPPED | 2009-03-15 | January 2009 | N
| CEWS-Healthcare | Children Education and Welfare Society | Lahore | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Uzaib Saya, Hassam Hussain, Ahsan Hussain, Ahsan Tanveer | Natasha Qureshi, Aisha Raees | PT carrying out diligence; Site visit conducted by PT on January 28th. Project call scheduled for 20th Feb. | 2009-04-07 | February 2010 | -
| CCF | Children Cancer Foundation Pakistan | Karachi | 7500 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | Waqas Satti, Minza Zahid, Asher Safvi | Akbar Bhaidani, Omar Biabani | First project call held on 4th Feb. PT considering further talks with CCF management before calling in a decision. Final project call to be held at the end of Feb. | 2009-09-13 | February 2010 | -
| SWS | Sahara Welfare Society | District Ghotki, Sindh | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | Ahmed Makani, Hajra Rizvi, Shireen Lakhani, Momin Ali Khan | Faris Rahman, Waleed Saraf | Project team conducting diligence. First project call to be held on 20th Feb. | 2009-10-03 | March 2010 | -
| AHD | Association for Humanitarian Development | Jatti, Sindh | 28922 | To provide safe drinking water (Nadi Filters) to 30 selected villages in the Jatti area | Laraib Mahar, Shozab Naqvi, Belal Mahfooz, Abdus Samad Parekh, Arslan Memon, Saad Khan | Mohsin Gadit, Faris Rahman, Tarim Wasim | First project meet held on Jan 31st. PT conducting preliminary research. Secnd project meet scheduled for 28th Feb. | 2009-09-01 | May/June 2010 | -
| Oxfords Foundation | Oxfords Foundation | Peshawar | 6128 | Computer Lab Up-gradation in Oxfords School & College | Naveed Ahmad, Yasir Khan, Mustafa Naveed, Owais Rafique | Natasha Qureshi, Hiba Rahim | Project kick off held on the 23rd of January. PT conducting diligence. First Project call to be held in the end of Feb. | 2009-08-28 | 2010-04-01 | -
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Farzal Dojki, Muneeb Irfan, Saira Chaudhry | Shahan Zafar, Janet Southern | Project Kick off call scheduled for 20th Feb 2010 | 2009-12-31 | March 2010
|  | Current Month | Previous Month
| Total Under Review | 7 | 7
| Expected Disbursements | 4300 | 4300

## In Progress
Association for the Development of Pakistan | [11 empty] | January 2010
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| AHD | Association for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 2280 | 1032 | TBD | - | First phase report from NGO received and is currently under review. One element of the project i.e. kitchen gardening kits has been delayed due to weather conditions.
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | 4176 | 0 | TBD | - | Site visit conducted on 07-Sep. Overall feedback was postive and the final tranche of Rs. 100,000 was released on November 20th; Final training report submitted on February 17th.
| Sohb | Sohb Development Society | Lasbela | TBD | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 1245 | n/a | TBD | - | Site visit conducted in mid-November. We have decided to put the second disbursement on hold as Sohb has not been able to identify a market and train a critical mass of women. PT to coordinate with NGO and help them identify a market for their products in Karachi.
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17480 | 0 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | - | NGO to purchase final equipment for eye hospital: We have disbursed a final tranche of Rs. 37,530 in the first week of November
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 2692 | 1558 | Progress report to be submitted by AHD on 31st September 2009 | - | Second tranche of funding (Rs. 115,000) disbursed on November 19th; PT to conduct site visit on (random) school day to assess current project situation. Third tranche to be released if site visit is satisfactory.
| Al-Qasim | Al Qasim Foundation | District Khushab] | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | Y | First phase almost complete. The NGO to update PT with a complete set of materials for their first phase monitoring reports. PT having site visit conducted (scheduled for 19 Feb) to ensure that the NGO is upto speed with our monitoring/ compliance practices. Second tranche to follow if first phase is satisfactory.
| Projects In Progress | 6
| Remaining Funding | 10516

## Volunteers
Association for the Development of Pakistan | [6 empty] | January 2009
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 3 | 8 | Open | Open | 0 | 0
| Project Teams | 21 | 11 | 12 | 8 | 10 | 6
| Evaluation Committee | 13 | 12 | 0 | 0 | 0 | 0
| Fundraising/Marketing | 16 | 9 | Open | Open | 7 | 0
| Web team | 3 | 4 | 0 | 0 | 0 | 0
|  | 56 | 44 | 12 | 8 | 17 | 6
| Sign-ups | 23 | 12
| Leads Converted* | 15 | 5
*Refers to volunteers who have been staffed or offered a position to get started
| Next Bi-monthly call | March 6th (Invitees: Jan/Feb sign-ups)
Leadership team to fill out volunteer request forms by March 1st

## Financial
Association for the Development of Pakistan | [5 empty] | January 2010
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations (net)
| Recurring | 335 | 325 | 335
| # donors | 11 | 11 | 11
| One-time | 891.9 | 723 | 891.9
| # Donations | 4 | 2 | 4
| Total | 1226.9 | 1048 | 1226.9
| # donors | 15 | 13 | 15
Project Disbursements
| Al-Qasim Biogas |  |  | 0
| Kharochan School |  |  | 0
| Total | 0 | 0 | 35256.17
Expenses
| Salaries | 990 | 800 | 6675
| Other | 144 | 145 | 3420 | Constant Contact prepayment
| Total | 1134 | 945 | 10095
Available Funds
| General |  |  | 53.6
| Earthquake Redevelopment |  |  | 1.967

## Initiatives
Association for the Development of Pakistan |  |  |  |  | January 2010
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization and roll out of new website | Technical resources being used: Content Writer: Sana Kazmi, Haleema and Khurram Graphic Designer: Shajee, Rafique Sheikh Technical Aspect: Farhan, Mansoor, Farzal Dojki | Content development, design and layout + technical development of new website in progress; Haleema to montior reporting dates and delivery. First design template circulated to the leadership team for feedback; Content approved, Beta-testing expected to start in the last week of February. | Feb-10
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP is now registered in Pakistan under the Companies Societies Act-1807. Haleema to proceed with local bank a/c opening | 2010-03-10
| Training Materials | Budget Diligence: To be used for brand orientation and for training of future EC's and PT's. Modules: PT and EC training framework that will capture organizational training, project diligence and implementation. New EC training materials: New training materials are being developed | Budget Diligence: Shahan Zafar Modules: PEC | Budget diligence being tweaked by Shahan. PEC members currently taking a stab at different modules within the PT and EC training framework. EC training call to be held and will be led by 2 PEC's. Monthly screening calls also to be led by PEC's. | Feb-10
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf, Shafaq Varghese, Sheharyar Malhi | Data entry which will be followed by analysis; First draft of KM database has been circulated for review. | 2010-02-10
| Project Volunteer Review | Survey being designed for EC's to fill out and and give feedback to volunteers that work on their teams | Haleema Raheel working on draft | To circulate the survey to EC's and have them share it with their PT's | 2010-02-10
| Fundraising: Capital Campaign | Capital Campaign:To raise funds for ADP, pushing our 2-3yr growth plans; Identification of fundraising leads globally to facilitate the capital campaign. Fundraisng Content Writer: To identify a fundraising content writer that is able to turn up content on short notice | Usman Hasan | Recruit volunteers in the US to pitch to corporations; To mobilize fundraising leads in the US and UK to meet capital campaign objectives; Usman to get back to the team with public online launch for the 2010 fundraising campaign (aligning with website timeline). Most likely in the next 1-2 weeks. | 2010-02-10
| Monthly Volunteer Orientation Call | To have a monthly/ bi-monthly call with a brief induction to be led initially by Tarim Wasim and there on by different members of the leadership team. The particpants of the call will all be fresh volunteer sign ups for that specific month | Tarim Wasim and Leadership Team Members | First Volunteer Induction conducted in mid-January and was attended by 16 volunteers; March call - TBD | 2010-02-10
| Outreach Team (NEW) | The outreach team shall assume overall responsibility for dissemination and promotion of activities and information. Key areas of development will be sourcing, volunteer strategy, overall awareness and fundraising | Leads: Naveed Ahmad,Alifia Shabir; Digital/ Social Media/ Blog: Umbreen Tapal, Nabeel Shakeel; Website/ Newsfeed: Morgan Robinson, Rafique Sheikh; Sourcing: Saira Chaudhry | Digital media: Leveraging tools like facebook, twitter, linkedin and blogs to get the word out about ADP; Sourcing:Tapping into NGO networks, targeting our niche NGO's Website: Updating newsfeed and fundraising content writing | Ongoing
| Sourcing | To sharpen sourcing strategy and focus on NGO's with more specialized bearings. The desired goal is to work with the best partners (non-profits we are excited to work with). | Sourcing: Haleema Raheel, Raja Nadeem, Waseef Jamal, Saira Chaudhry, Shayan Rajani | Haleema to gather/ compile data for 20-30 non-profits ADP would be excited to enter into long term partnership with. | Ongoing