## Cover
Association for the Development of Pakistan
Monthly Report
February 2010

## Proposals
Association for the Development of Pakistan | [8 empty] | February 2010
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| Amir Public School | Nia Ujala | 2409 | Development of a school in Gujranwala (set up of classroom's) | Gujranwala | Approved from Screening - Final decision on project to be taken on joint screening call on 03/28/10 | 2010-02-08 | Ali Farid | Approved by EC
| RHD | Rural Health and Development Foundation | 6073 | Establishment of a school in Farsash Town (slum in the outskirts of Islamabad) | Islamabad | To follow up with NGO and reach screening decision | 2010-02-01 | Aisha Raees | 2010-02-22
| RMKF | Raja Mirza Khan Foundation | 6238 | Provision of clean drinking water through the installation of 5 water wells in District Bagh, AJK | Bagh, AJK | To follow up with NGO and reach screening decision | 2010-02-09 | Qasim Ashraf | 2010-03-28
| FEEDER | Federation for Environment, Education, Development and Equal Rights | 10000 | Community Plantation for Relief to the Communities in Fuel Wood Need. | Mansehra | To follow up with NGO and reach screening decision | 2010-02-04 | Haleema Raheel | 2010-03-28
| Koohi Goth | Health, Education, Environment & Sustainable Development | 9761 | Establishment of a laboratory at Koohi Goth Hospital | Deh Landi, Karachi | To follow up with NGO and reach screening decision | 2010-03-09 | Shuaib Siddiqui | 2010-04-01
| AK | Anjuman Khaliqia | 8928 | Grant for furniture and equipment for an orphans home in Sargodha | Sargodha | To follow up with NGO and reach screening decision | 2010-02-22 | Hiba Rahim | 2010-03-28
| KEF | Khyber Eye Foundation | 9411 | Purchase of PNEUMATIC TONOMETER (used to screen cataract and glaucoma. ~85% of all blindness caused by these diseases) | Peshawar | To follow up with NGO and reach screening decision | 2010-03-02 | Shaharyar Ahmed | 2010-03-28
| HOPE | Health Orientation and Poverty Eradication (HOPE) Foundation | 5791 | Water Supply Schemes in 4 locations in AJK | Bagh, AJK | To follow up with NGO and reach screening decision | 9th-Feb-10 | Haleema Raheel | 2010-03-28
| DWDO | Dehleez Welfare and Development Organization | 8576 | Dastakari/ vocational and health centre for women in a small village 17kms from Peshawar | Peshawar | To follow up with NGO and reach screening decision | 2010-02-27 | Haleema Raheel | 2010-04-01
| WASFD | Women Association Struggle for Development | 9176 | Empowerment through enterprise development (providing 100 women with grants to start their own micro enterprises) | Mardan | To follow up with NGO and reach screening decision | 2010-03-03 | Haleema Raheel | 2010-03-28
| Adn | Al-Mustafa Development Network | 6821 | Set up of a computer lab at Kazim M. school (161 students) in AJK | AJK | To follow up with NGO and reach screening decision | 2010-03-09 | Haleema Raheel | 2010-03-28
|  | Current Month | Previous Month
| Proposals | 11 | 10

## Under Review
Association for the Development of Pakistan | [11 empty] | February 2010
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Potential Disbursement (Y/ N)
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team; Site visit pending. | 2008-11-04 | March 2010 | Y
| CEWS-Healthcare | Children Education and Welfare Society | Lahore | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Uzaib Saya, Hassam Hussain, Ahsan Hussain, Ahsan Tanveer | Natasha Qureshi, Aisha Raees | PT had a call with the NGO on 23rd Feb discussing key diligence issues. The PT will take a final vote on the project in the next project call - scheduled for last week of March | 2009-04-07 | March 2010 | N
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | Waqas Satti, Minza Zahid, Asher Safvi | Akbar Bhaidani, Omar Biabani | Project stands approved from diligence. PT drafting contract/ compliance documentation. Fundraising to kick off in the third week of March. | 2009-09-13 | Approved | Y
| SWS | Sahara Welfare Society | District Ghotki, Sindh | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | Ahmed Makani, Hajra Rizvi, Shireen Lakhani, Momin Ali Khan | Faris Rahman, Waleed Saraf | Project team conducting diligence. Second project call held on March 7th. PT to arrange for a site visit. Decision expected within the next 3-4 weeks. | 2009-10-03 | April 2010 | -
| AHD | Association for Humanitarian Development | Jatti, Sindh | 28922 | To provide safe drinking water (Nadi Filters) to 30 selected villages in the Jatti area | Laraib Mahar, Shozab Naqvi, Belal Mahfooz, Abdus Samad Parekh, Arslan Memon, Saad Khan | Mohsin Gadit, Faris Rahman, Tarim Wasim | PT conducting preliminary research. Project call held on March 7th. We are still looking for more volunteers to be assigned to this project. | 2009-09-01 | May/June 2010 | -
| Oxfords Foundation | Oxfords Foundation | Peshawar | 6128 | Computer Lab Up-gradation in Oxfords School & College | Naveed Ahmad, Yasir Khan, Mustafa Naveed, Owais Rafique | Natasha Qureshi, Hiba Rahim | Project kick off held on the 23rd of January. PT conducting diligence. Site visit scheduled for 20th March. | 2009-08-28 | April 2010 | -
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Farzal Dojki, Muneeb Irfan, Saira Chaudhry | Shahan Zafar, Janet Southern | First project call to be held at the end of March. Project site visit put on hold due to heavy rainfall in the area. PT conducting DD and will communicate/ decide the date for the upcoming site visit. | 2009-12-31 | April 2010 | -
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 10000 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Laterines in total) | Nabeel Hasnain, Najaf Shah, Nada Siddiqqi | Shuaib Siddiqui, Janet Southern, Tarim Wasim | Project kick off call held on 14th March. PT conducting due-diligence. | 2010-02-17 | May 2010 | -
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | To be staffed | To be staffed | - | 2010-02-19 | - | -
|  | Current Month | Previous Month
| Total Under Review | 8 | 7
| Expected Disbursements | 11358 | 4300

## In Progress
Association for the Development of Pakistan | [11 empty] | February 2010
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| AHD | Association for Humanitarian Development | Jatti, Sind | 3312 | Water filters, fuel-efficient stoves and kitchen gardening supplies | Jun-08 (2nd phase) | Ongoing | 2280 | 1032 | TBD | - | First phase report from NGO received and is currently under review. One element of the project i.e. kitchen gardening kits has been delayed due to weather conditions.
| NEEDS - YFC | NEEDS | Charsaddha | 5000 | Youth facilitation centre - vocational skills training | 2008-03-01 | 31-Mar-09 | 4176 | 0 | TBD | - | Site visit conducted on 07-Sep. Overall feedback was postive and the final tranche of Rs. 100,000 was released on November 20th; Final training report submitted on February 17th.
| Sohb | Sohb Development Society | Lasbela | TBD | Womens handicrafts skills training centre | 2009-03-01 | Mar-2010 | 1245 | n/a | TBD | - | Site visit conducted in mid-November. We have decided to put the second disbursement on hold as Sohb has not been able to identify a market and train a critical mass of women. Local Karachi chapter volunteers are involved in identifying markets for Sohb's products.
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17480 | 0 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | - | NGO to purchase final equipment for eye hospital: We have disbursed a final tranche of Rs. 37,530 in the first week of November
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 2692 | 1558 | Progress report to be submitted by AHD on 31st September 2009 | - | Second tranche of funding (Rs. 115,000) disbursed on November 19th; Spot check/ site visit conducted on 3rd March and the findings reported to the PT have been favorable. PT to finalize next steps over a call (third weekend or March).
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | Y | PT conducted site visit in the first week od March and reported favorable progress - Al-Qasim has agreed to paper based reporting. PT will decide next steps and timing for next tranche after they receive a comprehensive site visit report from Ahmad Chaudhry (site visit volunteer)
| Projects In Progress | 6
| Remaining Funding | 10516

## Volunteers
Association for the Development of Pakistan | [6 empty] | January 2010
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 3 | 8 | Open | Open | 0 | 0
| Project Teams | 21 | 11 | 12 | 8 | 10 | 6
| Evaluation Committee | 13 | 12 | 0 | 0 | 0 | 0
| Fundraising/Marketing | 16 | 9 | Open | Open | 7 | 0
| Web team | 3 | 4 | 0 | 0 | 0 | 0
|  | 56 | 44 | 12 | 8 | 17 | 6
| Sign-ups | 23 | 12
| Leads Converted* | 15 | 5
*Refers to volunteers who have been staffed or offered a position to get started
| Next Bi-monthly call | March 6th (Invitees: Jan/Feb sign-ups)
Leadership team to fill out volunteer request forms by March 1st

## Financial
Association for the Development of Pakistan | [5 empty] | January 2010
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations (net)
| Recurring | 335 | 325 | 335
| # donors | 11 | 11 | 11
| One-time | 891.9 | 723 | 891.9
| # Donations | 4 | 2 | 4
| Total | 1226.9 | 1048 | 1226.9
| # donors | 15 | 13 | 15
Project Disbursements
| Al-Qasim Biogas |  |  | 0
| Kharochan School |  |  | 0
| Total | 0 | 0 | 35256.17
Expenses
| Salaries | 990 | 800 | 6675
| Other | 144 | 145 | 3420 | Constant Contact prepayment
| Total | 1134 | 945 | 10095
Available Funds
| General |  |  | 53.6
| Earthquake Redevelopment |  |  | 1.967

## Initiatives
Association for the Development of Pakistan |  |  |  |  | February 2010
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization and roll out of new website | Technical resources being used: Content Writer: Sana Kazmi, Haleema and Khurram Graphic Designer: Shajee, Rafique Sheikh Technical Aspect: Farhan, Mansoor, Farzal Dojki | Content development, design and layout + technical development of new website almost complete. Content approved, Beta-testing to start on March 22nd, 2010. | Mar-10
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP is now registered in Pakistan under the Companies Societies Act-1807. Haleema to proceed with local bank a/c opening | 2010-03-10
| Training Materials | Budget Diligence: To be used for brand orientation and for training of future EC's and PT's. Modules: PT and EC training framework that will capture organizational training, project diligence and implementation. New EC training materials: New training materials have been rolled out for training | Budget Diligence: Shahan Zafar Modules: PEC | Budget diligence being tweaked by Shahan. PEC members currently taking a stab at different modules within the PT and EC training framework. EC training call held on March 7th Monthly screening calls also to be led by PEC's. | 2010-04-10
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf, Shafaq Varghese, Sheharyar Malhi | Data entry which will be followed by analysis; First draft of KM database has been circulated for review. | 2010-03-10
| Project Volunteer Review | EC Survey rolled out to the PEC for feedback and review. The survey will be used by EC's to give feedback to volunteers that work on their teams | Haleema Raheel | To circulate the survey to EC's on past projects | 2010-03-10
| Fundraising: Capital Campaign | Capital Campaign:To raise funds for ADP, pushing our 2-3yr growth plans; Identification of fundraising leads globally to facilitate the capital campaign. Fundraisng Content Writer: To identify a fundraising content writer that is able to turn up content on short notice | Usman Hasan | Recruit volunteers in the US to pitch to corporations; To mobilize fundraising leads in the US and UK to meet capital campaign objectives; Usman to get back to the team with public online launch for the 2010 fundraising campaign (aligning with website timeline). Monthly fundraising call held on 20th March. Fundraising for CCF to be kicked off in the last week of March | Ongoing
| Monthly Volunteer Orientation Call | To have a monthly/ bi-monthly call with a brief induction to be led initially by Tarim Wasim and there on by different members of the leadership team. The particpants of the call will all be fresh volunteer sign ups for that specific month | Tarim Wasim and Leadership Team Members | Second Volunteer Induction conducted on March 14th and was led by Tarim Wasim | Ongoing
| Outreach Team | The outreach team shall assume overall responsibility for dissemination and promotion of activities and information. Key areas of development will be sourcing, volunteer strategy, overall awareness and fundraising | Leads: Naveed Ahmad,Alifia Shabir; Digital/ Social Media/ Blog: Umbreen Tapal, Nabeel Shakeel; Website/ Newsfeed: Morgan Robinson, Rafique Sheikh; Sourcing: Saira Chaudhry | Digital media: Leveraging tools like facebook, twitter, linkedin and blogs to get the word out about ADP; Sourcing:Tapping into NGO networks, targeting our niche NGO's Website: Updating newsfeed and fundraising content writing | Ongoing