## Cover
Association for the Development of Pakistan
Monthly Report
March 2010

## Proposals
Association for the Development of Pakistan | [8 empty] | March 2010
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| Amir Public School | Nia Ujala | 2409 | Development of a school in Gujranwala (set up of classroom's) | Gujranwala | Approved from Screening - Ali to revert back with his comments after screening call with Natasha on 3/28/10 | 2010-02-08 | Ali Farid | Pending Final approval
| Adn | Al-Mustafa Development Network | 6821 | Set up of a computer lab at Kazim M. school (161 students) in AJK | AJK | Approved from screening. Waiting for decsion on one of our computer lab projects prior to staffing a project team | 2010-03-09 | Haleema Raheel | Approved on screening call
| RHD | Rural Health and Development Foundation | 6073 | Establishment of a school in Farsash Town (slum in the outskirts of Islamabad) | Islamabad | Received comments from Aisha; Final decision will me made on Screening Call | 2010-02-01 | Aisha Raees | 2010-04-25
| RMKF | Raja Mirza Khan Foundation | 6238 | Provision of clean drinking water through the installation of 5 water wells in District Bagh, AJK | Bagh, AJK | Received comments from Qasim; Final decision will me made on Screening Call | 2010-02-09 | Qasim Ashraf | 2010-04-25
| FEEDER | Federation for Environment, Education, Development and Equal Rights | 10000 | Community Plantation for Relief to the Communities in Fuel Wood Need. | Mansehra | Final decision pending with PEC | 2010-02-04 | Haleema Raheel | 2010-03-28
| Koohi Goth | Health, Education, Environment & Sustainable Development | 9761 | Establishment of a laboratory at Koohi Goth Hospital | Deh Landi, Karachi | To follow up with NGO and reach screening decision | 2010-03-09 | Shuaib Siddiqui | 2010-04-25
| AK | Anjuman Khaliqia | 8928 | Grant for furniture and equipment for an orphans home in Sargodha | Sargodha | To follow up with NGO and reach screening decision | 2010-02-22 | Hiba Rahim | 2010-04-25
| KEF | Khyber Eye Foundation | 9411 | Purchase of PNEUMATIC TONOMETER (used to screen cataract and glaucoma. ~85% of all blindness caused by these diseases) | Peshawar | Received comments from Shaharyar; Final decision to be taken on screening call | 2010-03-02 | Shaharyar Ahmed | 2010-04-25
| HOPE | Health Orientation and Poverty Eradication (HOPE) Foundation | 5791 | Water Supply Schemes in 4 locations in AJK | Bagh, AJK | Final decision to be taken on screening call | 9th-Feb-10 | Haleema Raheel | 2010-04-25
| FESF | Family Educational Services Foundation | 9523 | Deaf Reach program: to set up a computer lab for a school in Hyderabad | Hyderabad | To follow up with NGO and reach screening decision | 2010-03-23 | Qasim Ashraf | 2010-04-25
| FRESC | The Foundation For Rehabilitation & Education of Special Children | 11467 | Development of a resource lab for impoverished children with learning disabilities | Lahore | To follow up with NGO and reach screening decision | 2010-03-26 | Tehniyet Kardar | 2010-04-25
| MRWO | Marrium Rural Welfare organization | 9523 | Improved Livelihoods of Poor Families through Livestock Development | Bhawalpur | To follow up with NGO and reach screening decision | 2010-03-25 | Osman Hashmi | 2010-04-25
| Shama | Shama Social Village Development Organization | 9345 | Small scale revolving grant fund support to low-income women an an income generation scheme through livestock | Charsadda | To follow up with NGO and reach screening decision | 2010-04-07 | Minhaj Patel | 2010-04-25
| DWDO | Dehleez Welfare and Development Organization | 8576 | Dastakari/ vocational and health centre for women in a small village 17kms from Peshawar | Peshawar | To follow up with NGO and reach screening decision | 2010-02-27 | Rameez Dossa | 2010-04-25
|  | Current Month | Previous Month
| Proposals | 12 | 11

## Under Review
Association for the Development of Pakistan | [11 empty] | March 2010
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Potential Disbursement (Y/ N)
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi, Farooq Waraich | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team; Site visit pending. Hasan Saeed to reach out to Lahore ch. Volunteers for the site visit. | 2008-11-04 | April 2010 | Y
| CEWS-Healthcare | Children Education and Welfare Society | Lahore | 10000 | Maternity unit for underprivileged district, only public unit in 10km radius | Uzaib Saya, Hassam Hussain, Ahsan Hussain, Ahsan Tanveer | Natasha Qureshi, Aisha Raees | PT to schedule a final call with the NGO. They have decided to pass on this project as it is not need based and doesn’t measure upto ADP criteria | 2009-04-07 | Rejected | N
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | Waqas Satti, Minza Zahid, Asher Safvi | Akbar Bhaidani, Omar Biabani | Project stands approved from diligence. PT drafting contract/ compliance documentation. Fundraising to kick off in the third week of March. | 2009-09-13 | Approved | Y
| SWS | Sahara Welfare Society | District Ghotki, Sindh | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | Ahmed Makani, Hajra Rizvi, Shireen Lakhani, Momin Ali Khan | Faris Rahman, Waleed Saraf | Project team conducting diligence. Site visit (to be conducted by a rep. from AIE) scheduled for the end of April | 2009-10-03 | April 2010 | -
| AHD | Association for Humanitarian Development | Jatti, Sindh | 28922 | To provide safe drinking water (Nadi Filters) to 30 selected villages in the Jatti area | Laraib Mahar, Shozab Naqvi, Belal Mahfooz, Abdus Samad Parekh, Arslan Memon, Saad Khan | Mohsin Gadit, Faris Rahman, Tarim Wasim | PT conducting research. Project meeting held on Apr 10th. We are still looking for more volunteers to be assigned to this project. | 2009-09-01 | June 2010 | -
| Oxfords Foundation | Oxfords Foundation | Peshawar | 6128 | Computer Lab Up-gradation in Oxfords School & College | Naveed Ahmad, Yasir Khan, Mustafa Naveed, Owais Rafique | Natasha Qureshi, Hiba Rahim | PT conducting diligence. Site visit scheduled for 20th March. PT is still pending additional documents from the NGO (financials etc) | 2009-08-28 | May 2010 | -
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Farzal Dojki, Muneeb Irfan, Saira Chaudhry | Shahan Zafar, Janet Southern | First project call held at the end of March. PT conducting DD; Site visit to be conducted end of Apr or first week of May | 2009-12-31 | May 2010 | -
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 10000 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Laterines in total) | Nabeel Hasnain, Najaf Shah, Nada Siddiqqi | Shuaib Siddiqui, Janet Southern, Tarim Wasim | Project kick off call held on 14th March. PT conducting due-diligence; Site visit to be conducted by Khizar Hayat in first week of May | 2010-02-17 | May 2010 | -
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Arifa Khandwala, Shehryar Khan, Sabeen Shahid, Butool Rizvi | Shuaib Siddiqui, Saad Hasan | Project kick off call held on 14th April. PT conducting diligence and preliminary research | 2010-02-19 | June 2010 | -
|  | Current Month | Previous Month
| Total Under Review | 7 | 8
| Expected Disbursements | 11358 | 4300

## In Progress
Association for the Development of Pakistan | [11 empty] | March 2010
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17400 | 0 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | - | NGO to purchase final equipment for eye hospital: We have disbursed a final tranche of Rs. 37,530 in the first week of November. Last report received in April.
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 2692 | 1558 | Progress report to be submitted by AHD on 31st September 2009 | - | Second tranche of funding (Rs. 115,000) disbursed on November 19th, 2010; Spot check/ site visit conducted on 3rd March and the findings reported to the PT have been favorable. PT to finalize next steps over a call.
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | Y | PT conducted site visit in the first week od March and reported favorable progress - Al-Qasim has agreed to paper based reporting: First phase report has been received and reviewed by the PT. The amount for the second tranche has been calculated at Rs 206k.
| Projects In Progress | 4
| Remaining Funding | 9484

## Volunteers
Association for the Development of Pakistan | [6 empty] | March 2010
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 4 | 3 | Open | Open | 1 | 0
| Project Teams | 23 | 18 | 5 | 4 | 4 | 6 | (Includes site-visit volunteers)
| Evaluation Committee | 10 | 7 | 3 | 2 | 0 | 0
| Fundraising | 11 | 11 | Open | Open | 0 | 0
| Outreach | 9 | 7 | Open | Open | 2 | 0
| Web team | 4 | 3 | 0 | 0 | 2 | 0
|  | 61 | 49 | 8 | 6 | 9 | 6
| Sign-ups | 17
| Leads Converted* | 8
*Refers to volunteers who have been staffed or offered a position to get started
| Next Bi-monthly call | May 9th (Invitees: March/April sign-ups)
Leadership team to fill out volunteer request forms by May 5th

## Financial
Association for the Development of Pakistan | [5 empty] | March 2010
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations (net)
| Recurring | 310 | 310 | 955
| # donors | 10 | 10 | 11
| One-time | 841.61 | 50 | 1783.51 | Includes beginning of CCF fundraise
| # Donations | 4 | 1 | 9
| Total | 1151.61 | 360 | 2738.51
| # donors | 14 | 11 | 20
Project Disbursements
| Al-Qasim Biogas |  |  | 0
| Kharochan School |  |  | 0
| Total | 0 | 0 | 0
Expenses
| Salaries | 990.0096 | 990.0096
| Other | 25 | 176 |  | Wire transfer fee
| Total | 1015.0096 | 1166.0096
Available Funds
| General |  |  | 50.8
| Earthquake Redevelopment |  |  | 1.9

## Initiatives
Association for the Development of Pakistan |  |  |  |  | March 2010
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization | Technical resources being used: Content Writer: Sana Kazmi, Haleema and Khurram Graphic Designer: Shajee, Rafique Sheikh Technical Aspect: Farhan, Mansoor, Farzal Dojki | New website Launched! Content development, testing sign-up forms etc in progress. Last web call hed on 15th Apr: Mansoor to develop guidelines for leadership team to make content changes on website | Ongoing
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP registration certificate being revised by the ministry. Haleema to proceed with local bank a/c opening as soon as she has all the required documentation | 2010-04-10
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf, Shafaq Varghese, Sheharyar Malhi | Data entry which will be followed by analysis; First draft of KM database has been circulated for review. PEC to provide feedback to Waleed and team | 2010-04-10
| Project Volunteer Review | EC Survey rolled out to the PEC for feedback and review. The survey will be used by EC's to give feedback to volunteers that have work on their teams | Haleema Raheel | To circulate the survey to past 4-5 project teams | 2010-03-10
| Fundraising | Capital Campaign:To raise funds for ADP, pushing our 2-3yr growth plans; Identification of fundraising leads globally to facilitate the capital campaign. Fundraisng Content Writer: To identify a fundraising content writer that is able to turn up content on short notice | Usman Hasan | Recruit volunteers in the US to pitch to corporations; To mobilize fundraising leads in the US and UK to meet capital campaign objectives; Usman to get back to the team with public online launch for the 2010 fundraising campaign (aligning with website timeline). Fundraising for CCF kicked off in the last week of March. | Ongoing
| Sector Teams | To assign 5-6 people teams to research the following sectors/ subsectors: Energy, Empowerment, Education and Health | PEC + Sector Volunteers | Sector Team orientation prepared by Mubarik. The sector teams orientation call is scheduled for Sunday 18th April and so far we have 13 interested volunteers | Ongoing
| Outreach Team | The outreach team shall assume overall responsibility for dissemination and promotion of activities and information. Key areas of development will be sourcing, volunteer strategy, overall awareness and fundraising | Leads: Naveed Ahmad Digital/ Social Media/ Blog: Umbreen Tapal, Nabeel Shakeel; Website/ Newsfeed: Morgan Robinson, Rafique Sheikh; Sourcing: Saira Chaudhry | Digital media: Leveraging tools like facebook, twitter, linkedin and blogs to get the word out about ADP; Sourcing:Tapping into NGO networks, targeting our niche NGO's Website: Updating newsfeed and fundraising content writing | Ongoing