## Cover
Association for the Development of Pakistan
Monthly Report
April 2010

## Proposals
Association for the Development of Pakistan | [8 empty] | April 2010
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| Care n Cure | Care n Cure Healthcare Services | 8035 | Construction of a Fiber Glass class for healthcare/ education in the Hub area of Sindh | Hub Area, Sindh | To follow up with NGO and reach screening decision | 2010-04-16 | Dawood Ahmed | 2010-05-16
| YSWO | Young Soomra Welfare Organization | 11904 | Establishment of a community vision center in Hyderabad | Hyderabad | To follow up with NGO and reach screening decision | 2010-04-26 | Dawood Ahmed | 2010-05-28
| RHD | Rural Health and Development Foundation | 6073 | Establishment of a school in Farsash Town (slum in the outskirts of Islamabad) | Islamabad | Received comments from Aisha; Final decision will me made on Screening Call | 2010-02-01 | Aisha Raees | 2010-04-25
| Koohi Goth | Health, Education, Environment & Sustainable Development | 9761 | Establishment of a laboratory at Koohi Goth Hospital | Deh Landi, Karachi | To follow up with NGO and reach screening decision | 2010-03-09 | Rameez Dossa | 2010-05-16
| AK | Anjuman Khaliqia | 8928 | Grant for furniture and equipment for an orphans home in Sargodha | Sargodha | To follow up with NGO and reach screening decision | 2010-02-22 | Hiba Rahim | 2010-05-16
| FRESC | The Foundation For Rehabilitation & Education of Special Children | 11467 | Development of a resource lab for impoverished children with learning disabilities | Lahore | To follow up with NGO and reach screening decision | 2010-03-26 | Tehniyet Kardar | 2010-05-16
| MRWO | Marrium Rural Welfare organization | 9523 | Improved Livelihoods of Poor Families through Livestock Development | Bhawalpur | To follow up with NGO and reach screening decision | 2010-03-25 | Osman Hashmi | 2010-05-16
| FESF | Family Educational Services Foundation | 9523 | Deaf Reach program: to set up a computer lab for a school in Hyderabad | Hyderabad | Approved from Screening- PT being staffed | 2010-03-23 | Qasim Ashraf | 2010-04-25
| Shama | Shama Social Village Development Organization | 9345 | Small scale revolving grant fund support to low-income women an an income generation scheme through livestock | Charsadda | Approved from screening. Waiting for decsion on Needs prior to staffing a project team | 2010-04-07 | Minhaj Patel | 2010-04-25
| Adn | Al-Mustafa Development Network | 6821 | Set up of a computer lab at Kazim M. school (161 students) in AJK | AJK | Approved from screening. Waiting for decsion on one of our computer lab projects prior to staffing a project team | 2010-03-09 | Haleema Raheel | Approved on screening call
|  | Current Month | Previous Month
| Early Stage | 7
| Approved | 3
| Total | 10 | 12

## Under Review
Association for the Development of Pakistan | [12 empty] | April 2010
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage | Potential Disbursement (Y/ N)
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team; Site visit conducted in April. Disbursement expected at the end of May | 2008-11-04 | April 2010 | End | Y
| SWS | Sahara Welfare Society | District Ghotki, Sindh | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | Ahmed Makani, Hajra Rizvi, Shireen Lakhani, Momin Ali Khan | Faris Rahman, Waleed Saraf | Project team conducting diligence. Site visit (to be conducted by a rep. from AIE) scheduled for 18th May | 2009-10-03 | May 2010 | End | -
| AHD | Association for Humanitarian Development | Jatti, Sindh | 28922 | To provide safe drinking water (Nadi Filters) to 30 selected villages in the Jatti area | Laraib Mahar, Shozab Naqvi, Belal Mahfooz, Ali Shahmalak, Shariq Ali, Saad Khan | Mohsin Gadit, Tarim Wasim | PT conducting research. Project meeting held on May 15th. | 2009-09-01 | June 2010 | Mid | -
| Oxfords Foundation | Oxfords Foundation | Peshawar | 6128 | Computer Lab Up-gradation in Oxfords School & College | Naveed Ahmad, Yasir Khan, Mustafa Naveed, Owais Rafique | Natasha Qureshi, Hiba Rahim | PT conducting diligence. Project call held on May 8th. PT verifying some final considerations prior to calling in their decision | 2009-08-28 | June 2010 | Mid | -
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Farzal Dojki, Muneeb Irfan, Saira Chaudhry | Shahan Zafar, Janet Southern | Site visit conducted on May 15th. Initial findings are favourable. PT to convene on call after submission of site visit report | 2009-12-31 | May 2010 | End | -
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 10000 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Laterines in total) | Nabeel Hasnain, Najaf Shah, Nada Siddiqqi | Shuaib Siddiqui, Janet Southern, Tarim Wasim | Project kick off call held on 14th March. PT conducting due-diligence; Site visit conducted on 7th May- PT waiting on report submission | 2010-02-17 | May 2010 | End | -
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Arifa Khandwala, Shehryar Khan, Sabeen Shahid, Butool Rizvi | Shuaib Siddiqui, Saad Hasan | Project kick off call held on 14th April. PT conducting diligence and preliminary research | 2010-02-19 | June 2010 | Mid | -
| Amir Public School | Nia Ujala | Gujaranwala | 2409 | Development of a school in Gujranwala (set up of classroom's) | Tehniyet Kardar, Mughees Butt | Akbar Bhaidani, Khawaja Ali Farid | Project kick off call held on 15th May 2010 | 2010-02-08 | July 2010 | Early | -
| Hope | Health Orientation and Poverty Eradication (HOPE) Foundation | Bagh, AJK | 5791 | Water Supply Schemes in 4 locations in AJK | Waqas Satti, Saba Gul, Muhammad Bilal | Shahan Zafar, Rameez Dossa | Project kick off call held on 1st May 2010 | 2010-02-09 | July 2010 | Early | -
| KEF | Khyber Eye Foundation | Peshawar | 9411 | Purchase of PNEUMATIC TONOMETER (used to screen cataract and glaucoma. ~85% of all blindness caused by these diseases) | PT being Staffed | Mubarik Imam, Shaharyar Ahmed | Project kick off call being scheduled for 22nd May | 2010-03-02 | July 2010 | Early | -
|  | Current Month | Previous Month
| Total Under Review | 11 | 7
| Expected Disbursements | 4300 | 4300
| Early Stage Diligence | 3
| Mid-Stage Diligence | 4
| Final Stage Diligence | 4

## In Progress
Association for the Development of Pakistan | [11 empty] | April 2010
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| LRBT | LRBT | Mansehra | 17400 | Equipment for eye hospital in earthquake stricken area | 2008-01-18 | Mar-2010 | 17400 | 0 | Equipment Utilization Report due monthly until the equipment is ready to be fully utilized | - | NGO to purchase final equipment for eye hospital: We have disbursed a final tranche of Rs. 37,530 in the first week of November. Last report received in April.
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 2692 | 1558 | Progress report to be submitted by AHD on 31st September 2009 | - | Second tranche of funding (Rs. 115,000) disbursed on November 19th, 2010; Spot check/ site visit conducted on 3rd March and the findings reported to the PT have been favorable. PT to finalize next steps over a call.
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | Y | PT conducted site visit in the first week od March and reported favorable progress - Al-Qasim has agreed to paper based reporting: First phase report has been received and reviewed by the PT. The amount for the second tranche has been calculated at Rs 206k; PT also considering sharing the funding with PDBP
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | 2010-04-20 | TBC | 6854 | 0 | Approved | N | Signed contract received from NGO; Submission of equipment utilization report (quarterly) following the equipment set-up period.
| Projects In Progress | 4
| Remaining Funding | 9484

## Volunteers
Association for the Development of Pakistan | [6 empty] | April 2010
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 6 | 4 | Open | Open | 2 | 0
| Project Teams | 29 | 23 | 7 | 5 | 4 | 4 | (Includes site-visit volunteers)
| Evaluation Committee | 13 | 10 | 3 | 3 | 0 | 0
| Fundraising | 11 | 11 | Open | Open | 0 | 0
| Outreach | 9 | 9 | Open | Open | 2 | 0
| Web team | 4 | 4 | 1 | 0 | 0 | 0
|  | 72 | 61 | 11 | 8 | 8 | 4
| Sign-ups | 17
| Leads Converted* | 8
*Refers to volunteers who have been staffed or offered a position to get started
** Sign-up form down from Apr 5-Apr 29 so most Apr sign-ups still need be entered. In process by Azhar Zeeshan
| Next Bi-monthly call | As soon as April sign-ups are entered in to Salesforce

## Financial
Association for the Development of Pakistan | [5 empty] | April 2010
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations (net)
| Recurring | 315 | 310 | 1270
| # donors | 10 | 10 | 11
| One-time | 5665 | 841.61 | 7448.51
| # Donations | 43 | 4 | 52
| Total | 5980 | 1151.61 | 8718.51
| # donors | 53 | 14 | 63
Project Disbursements
| Children's Cancer Hospital | 6854 |  | 6854
| Al-Qasim Biogas |  |  | 0
| Kharochan School |  |  | 0
| Total | 6854 | 0 | 6854
Expenses
| Salaries | 990.0096 | 990.0096
| Other | 2 | 25
| Total | 992.0096 | 1015.0096
Available Funds
| General |  |  | 49
| Earthquake Redevelopment |  |  | 1.9

## Initiatives
Association for the Development of Pakistan |  |  |  |  | April 2010
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| Website | Redevelopment of Website: Migration of historical data, information architechture i.e. content organization | Technical resources being used: Content Writer: Sana Kazmi, Haleema and Khurram Graphic Designer: Shajee, Rafique Sheikh Technical Aspect: Farhan, Mansoor, Farzal Dojki, Azhar Zeeshan | New website Launched! Content development, testing sign-up forms etc in progress. Last web call hed on 15th Apr: Mansoor to develop guidelines for leadership team to make content changes on website | Ongoing
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP registration certificate being revised by the ministry. Haleema to proceed with local bank a/c opening as soon as she has all the required documentation | 2010-05-10
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf, Shafaq Varghese, Sheharyar Malhi | Data entry which will be followed by analysis; First draft of KM database has been circulated for review. PEC to provide feedback to Waleed and team | 2010-05-10
| Project Volunteer Review | EC Survey rolled out to the PEC for feedback and review. The survey will be used by EC's to give feedback to volunteers that have work on their teams | Haleema Raheel, Naveed Ahmad | Naveed working on shortening the length of the survey. Haleema to circulate new version to past 4-5 PT's | Ongoing
| Sector Teams | To assign 5-6 people teams to research the following sectors/ subsectors: Energy, Empowerment, Education and Health | PEC + Sector Volunteers | We have kicked off our sector teams starting with a general orientation followed by launching our 'Health' and 'Education' sectors only | Ongoing
| Outreach Team | The outreach team shall assume overall responsibility for dissemination and promotion of activities and information. Key areas of development will be sourcing, volunteer strategy, overall awareness and fundraising | Leads: Naveed Ahmad Digital/ Social Media/ Blog: Umbreen Tapal, Nabeel Shakeel; Website/ Newsfeed: Morgan Robinson, Rafique Sheikh; Sourcing: Saira Chaudhry Photography: Asim Iqbal, Iffat Almas; Film: Faraz Ali | Digital media: Leveraging tools like facebook, twitter, linkedin and blogs to get the word out about ADP; Sourcing:Tapping into NGO networks, targeting our niche NGO's Website: Updating newsfeed and fundraising content writing | Ongoing
| Volunteer Onboarding | New process for thorougher evaluation of volunteers prior to staffing. | Khurram Owais, Naveed Ahmed | New process outline emailed to leadership team Next step: Finalize and implement | Ongoing
| New VM Recruitment |  | Khurram Owais | Phase II detailed applications submitted 12 candidates shortlisted for interviews on Sat 22nd May | Ongoing