## Cover
Association for the Development of Pakistan
Monthly Report
May 2010

## Proposals
Association for the Development of Pakistan | [8 empty] | May 2010
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| Care n Cure | Care n Cure Healthcare Services | 8035 | Construction of a Fiber Glass class for healthcare/ education in the Hub area of Sindh | Hub Area, Sindh | To follow up with NGO and reach screening decision | 2010-04-16 | Dawood Ahmed | 2010-06-20
| YSWO | Young Soomra Welfare Organization | 11904 | Establishment of a community vision center in Hyderabad | Hyderabad | To follow up with NGO and reach screening decision | 2010-05-26 | Dawood Ahmed | 2010-06-20
| AK | Anjuman Khaliqia | 8928 | Grant for furniture and equipment for an orphans home in Sargodha | Sargodha | To follow up with NGO and reach screening decision | 2010-02-22 | Hiba Rahim | 2010-05-16
| Shama | Shama Social Village Development Organization | 9345 | Small scale revolving grant fund support to low-income women an an income generation scheme through livestock | Charsadda | Approved from screening. Waiting for decsion on Needs prior to staffing a project team | 2010-04-07 | Minhaj Patel | 2010-04-25
| Adn | Al-Mustafa Development Network | 6821 | Set up of a computer lab at Kazim M. school (161 students) in AJK | AJK | Approved from screening. Waiting for decsion on one of our computer lab projects prior to staffing a project team | 2010-03-09 | Haleema Raheel | Approved on screening call
| SEWA | Sindh Educational Welfare Association | 11764 | Vocational IT training through 6-month certificate course for securing employment opportunities through the market in Benazirabad (close to Hyderabad) - training of 100 youths | Benazirabad | To follow up with NGO and reach screening decision | 2010-05-19 | Rameez Dossa | 2010-06-20
| MWT | Message Welfare Trust | 3070 | Vocational training center for a slum community in Lahore | Lahore | To follow up with NGO and reach screening decision | 2010-05-18 | Haleema Raheel | 2010-06-25
| AJBTB | Aziz Jehan Begum Trust for the Blind | 9411 | Expansion of a residential and educational complex for blind children | Jedhoo, Lahore | To follow up with NGO and reach screening decision | 2010-06-02 | Khurram Jamali | 2010-06-25
| FMH | Fatima Memorial Hospital | 9411 | Training of traditional birth attendants for Fatima memorial hospital | Sheikhupura | To follow up with NGO and reach screening decision | 2010-05-11 | Omar Biabani | 2010-06-20
| KDO | Khangiri Development Organization | 7647 | Water supply scheme in Balakot (next to Mansehra) | Mansehra | To follow up with NGO and reach screening decision | 2010-06-09 | Shaharyar Ahmed | 2010-06-25
| CDF | Country Development Foundation | 9411 | Technical education & Vocational training to 150 beneficiaries in Khanewal | Khanewal | To follow up with NGO and reach screening decision | 2010-06-17 | Ali Farid | 2010-07-05
| APS | Arshad Public School | 11619 | Water supply project- installation of water tanks, pipes, etc to provide the school with access to clean water | AJK | To follow up with NGO and reach screening decision | 2010-06-15 | Haleema Raheel | 2010-06-25
|  | Current Month | Previous Month
| Early Stage | 10 | 7
| Approved | 2 | 3
| Total | 12 | 10

## Under Review
Association for the Development of Pakistan | [12 empty] | May 2010
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage | Potential Disbursement (Y/ N)
| Khoj | Khoj Development Society | Sheikhupura | 4300 | Equipment for virtual teaching in remote village school | Meher Jaffri, Butool Rizvi | Waleed Saraf, Mubarik Imam | Final contract being drafted by Project Team; Site visit conducted in April. Disbursement expected asap | 2008-11-04 | April 2010 | End | Y
| SWS | Sahara Welfare Society | District Ghotki, Sindh | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | Ahmed Makani, Hajra Rizvi, Shireen Lakhani, Momin Ali Khan | Faris Rahman, Waleed Saraf | Site visit (conducted by a rep. from AIE) on the 18th of May. PT to have a project call this week and take a final decision on the project | 2009-10-03 | May 2010 | End | -
| AHD | Association for Humanitarian Development | Jatti, Sindh | 28922 | To provide safe drinking water (Nadi Filters) to 30 selected villages in the Jatti area | Laraib Mahar, Shozab Naqvi, Belal Mahfooz, Ali Shahmalak, Shariq Ali, Saad Khan | Mohsin Gadit, Tarim Wasim | PT conducting research. Project site visit conducted on June 20th, 2010. | 2009-09-01 | June 2010 | Mid | -
| Oxfords Foundation | Oxfords Foundation | Peshawar | 6128 | Computer Lab Up-gradation in Oxfords School & College | Naveed Ahmad, Yasir Khan, Mustafa Naveed, Owais Rafique | Natasha Qureshi, Hiba Rahim | Disqualified | 2009-08-28 | June 2010 | Mid | -
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Farzal Dojki, Muneeb Irfan, Saira Chaudhry | Shahan Zafar, Janet Southern | Project stands approved by the EC. PT in the process of drafting contract/ meeting pre-funding requirements | 2009-12-31 | May 2010 | End | -
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 10000 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Laterines in total) | Nabeel Hasnain, Najaf Shah, Nada Siddiqqi | Shuaib Siddiqui, Janet Southern, Tarim Wasim | Project stands approved by the EC. PT in the process of drafting contract/ meeting pre-funding requirements | 2010-02-17 | May 2010 | End | -
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Arifa Khandwala, Shehryar Khan, Sabeen Shahid, Butool Rizvi | Shuaib Siddiqui, Saad Hasan | Project kick off call held on 14th April. PT conducting diligence and preliminary research | 2010-02-19 | July 2010 | Mid | -
| Amir Public School | Nia Ujala | Gujaranwala | 2409 | Development of a school in Gujranwala (set up of classroom's) | Tehniyet Kardar, Mughees Butt | Akbar Bhaidani, Khawaja Ali Farid | Site visit conducted on June 15th- 1st Project call held on 19th June 2010 | 2010-02-08 | July 2010 | Mid | -
| Hope | Health Orientation and Poverty Eradication (HOPE) Foundation | Bagh, AJK | 5791 | Water Supply Schemes in 4 locations in AJK | Waqas Satti, Saba Gul, Muhammad Bilal | Shahan Zafar, Rameez Dossa | Project kick off call held on 1st May 2010. PT conducting diligence. | 2010-02-09 | July 2010 | Early | -
| FESF | Family Educational Services Foundation | Hyderabad | 9523 | Deaf Reach program: to set up a computer lab for a school in Hyderabad | Being Staffed | Waleed Saraf, Qasim Ashraf | Project kick off call being scheduled for June 27th | 2010-04-25 | 2010-08-01 | Early
| KEF | Khyber Eye Foundation | Peshawar | 9411 | Purchase of PNEUMATIC TONOMETER (used to screen cataract and glaucoma. ~85% of all blindness caused by these diseases) | PT being Staffed | Mubarik Imam, Shaharyar Ahmed | DROPPED | 2010-03-02 | July 2010 | Early | -
|  | Current Month | Previous Month
| Total Under Review | 9 | 11
| Expected Disbursements | 4300 | 4300
| Early Stage Diligence | 2
| Mid-Stage Diligence | 3
| Final Stage Diligence | 4

## In Progress
Association for the Development of Pakistan | [11 empty] | May 2010
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 3644 | 606 | Progress report to be submitted by AHD on 31st September 2009 | - | Third tranche of funding (Rs. 81,000) disbursed on June 17th, 2010- Final tranche to be disbursed on PT's instructions
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 1220 | 7926 | Additional funding to be released after compliance/ submission of detailed forms by NGO | Y | Site visit conducted by 2 ADP volunteers on 13th June. Pictures from the visit and the site report has been submitted to the PT. Waiting for final instructions from the PT in order to disburse the next tranche
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | 2010-04-20 | TBC | 6854 | 0 | Approved | N | Signed contract received from NGO; Submission of equipment utilization report (quarterly) following the equipment set-up period.
| Projects In Progress | 3
| Remaining Funding | 8532

## Volunteers
Association for the Development of Pakistan | [6 empty] | May 2010
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 5 | 6 | Open | Open | 0 | 2
| Project Teams | 22 | 29 | 5 | 7 | 5 | 4 | (Includes site-visit volunteers)
| Evaluation Committee | 12 | 13 | 1 | 3 | 1 | 0
| Fundraising | 11 | 11 | Open | Open | 0 | 0
| Outreach | 6 | 9 | Open | Open | 0 | 2
| Web team | 5 | 4 | 1 | 1 | 1 | 0
|  | 61 | 72 | 7 | 11 | 7 | 8
| Sign-ups | 47
| Leads In Process* | 12
*Refers to leads who have been staffed or are currently in the onboarding process
Issues:
1. Salesforce customization
2. Streamline onboarding process with team leads (demand/supply)
3. Next volunteer introduction/general call

## Financial
Association for the Development of Pakistan | [5 empty] | May 2010
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations (net)
| Recurring | 265 | 315 | 1535
| # donors | 9 | 10 | 11
| One-time | 2475 | 5665 | 9923.51
| # Donations | 1 | 43 | 53
| Total | 2740 | 5980 | 11458.51
| # donors | 10 | 53 | 64
Project Disbursements
| Children's Cancer Hospital |  | 6854 | 6854
Al-Qasim Biogas
Kharochan School
| Total | 0 | 6854 | 6854
Expenses
| Salaries | 990.0096 | 990.0096 | 4950.0384
| Other | 25 | 2 | 372
| Total | 1015.0096 | 992.0096 | 5322.0384
Available Funds
| General |  |  | 50.3
| Earthquake Redevelopment |  |  | 1.9

## Fundraising
Association for the Development of Pakistan |  |  |  |  | May 2010
Fundraising
|  | Project Specific | General pool
| Funds raised | 6500 | 9000 | <-- Today
| June | 10000 | 11000 | <-- Projections
| July | 20000 | 16000
| August | 28000 | 20000
| September | 34000 | 24000
| October | 40000 | 40000
| November | 45000 | 45000
| December | 50000 | 50000
| Initiatives | Description | Volunteers | Comments | Timeline
| Canadian Registration | Registering ADP as a non-profit organization in Canada to allow tax deductions to donors | Owais Rafiq and Ammar Ali | Completing the application. Targetting complete submission by June 30. | June 30 submission. Overall process will take 3-4 months (government process takes a long time)
| APPNA conference | ADP is planning to have a table at this year's APPNA conference. APPNA is the Association of Pakistani Physicians of North America | Hassan Baweja | Materials under preparation. Getting enough volunteers to have at least 2-3 individuals present at all times | Conference is June 30 - July 3
| Applications to foundations for Al-Qasim project | Applications to WISIONS. Also applying for Ashden awards | Faraz Shakil, Steve Dimon | WISIONS application to be submitted by June 21. Ashden awards deadline is middle of July | June / July
| New York gig night | Gig night with amateur musicians of Pakistani origin. Looking to bring a wide audience from New York and put ADP's name out | Ahmad Sheikh / New York team | Event was held on June 10 | Completed
| Boston doctor community presentation | Presentation to a small (~15 person) group of doctors in the Boston area. Being arranged by a volunteer close to ADP who is himself a Doctor, at his house | Usman Hassan and Mohammad Arif | Presentation to be prepared | July 31 (tentative date)

## Initiatives
Association for the Development of Pakistan |  |  |  |  | May 2010
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP registration certificate being revised by the ministry. Haleema to proceed with local bank a/c opening as soon as she has all the required documentation | 2010-07-01
| Project Benchmarking/ Knowledge Management | To consolidate project data as part of a knowledge management/ benchmarking exercise. | Waleed Saraf, Shafaq Varghese, Sheharyar Malhi | Data entry which will be followed by analysis; First draft of KM database has been circulated for review. PEC to provide feedback to Waleed and team | Ongoing
| Project Volunteer Review | EC Survey rolled out to the PEC for feedback and review. The survey will be used by EC's to give feedback to volunteers that have work on their teams | Haleema Raheel, Naveed Ahmad | Haleema to shorten the survey to a one page zommerang version. Initial survey circulated to 4 past project teams | Ongoing
| Sector Teams | To assign 5-6 people teams to research the following sectors/ subsectors: Energy, Empowerment, Education and Health | PEC + Sector Volunteers | We have kicked off our sector teams starting with a general orientation followed by launching our 'Health' and 'Education' sectors only | Ongoing
| Outreach Team | The outreach team shall assume overall responsibility for dissemination and promotion of activities and information. Key areas of development will be sourcing, volunteer strategy, overall awareness and fundraising | Leads: Naveed Ahmad Digital/ Social Media/ Blog: Umbreen Tapal, Nabeel Shakeel; Website/ Newsfeed: Morgan Robinson, Rafique Sheikh; Sourcing: Saira Chaudhry Photography: Asim Iqbal, Iffat Almas; Film: Faraz Ali | Digital media: Leveraging tools like facebook, twitter, linkedin and blogs to get the word out about ADP; Sourcing:Tapping into NGO networks, targeting our niche NGO's Website: Updating newsfeed and fundraising content writing | Ongoing
| Volunteer Onboarding | New process for thorougher evaluation of volunteers prior to staffing. | Khurram Owais, Naveed Ahmed | New process outline emailed to leadership team Next step: Finalize and implement | Ongoing
| New VM Recruitment | NEW VM (Hiring) | Khurram Owais | Two applicants shortlisted- Mubarik/ Tarim in final round of interviews | 2010-07-01
| New OD Recruitment | NEW OD (Hiring) | Haleema Raheel | OD Job Announcement e-mail sent out to ADP network. Final date of apllication submission is June 30th, 2010 | 2010-08-01