## Cover
Association for the Development of Pakistan
Monthly Report
June 2010

## Proposals
Association for the Development of Pakistan | [8 empty] | June 2010
New Proposals
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AK | Anjuman Khaliqia | 8928 | Grant for furniture and equipment for an orphans home in Sargodha | Sargodha | To follow up with NGO and reach screening decision | 2010-02-22 | Dawood Ahmed | 2010-07-31
| Shama | Shama Social Village Development Organization | 9345 | Small scale revolving grant fund support to low-income women an an income generation scheme through livestock | Charsadda | Approved from screening. Waiting for decsion on Needs prior to staffing a project team | 2010-04-07 | Minhaj Patel | 2010-04-25
| Adn | Al-Mustafa Development Network | 6821 | Set up of a computer lab at Kazim M. school (161 students) in AJK | AJK | Approved from screening. Waiting for decsion on one of our computer lab projects prior to staffing a project team | 2010-03-09 | Haleema Raheel | Approved on screening call
| SEWA | Sindh Educational Welfare Association | 11764 | Vocational IT training through 6-month certificate course for securing employment opportunities through the market in Benazirabad (close to Hyderabad) - training of 100 youths | Benazirabad | To follow up with NGO and reach screening decision | 2010-05-19 | Janet Southern | 2010-07-31
| AJBTB | Aziz Jehan Begum Trust for the Blind | 9411 | Expansion of a residential and educational complex for blind children | Jedhoo, Lahore | To follow up with NGO and reach screening decision | 2010-06-02 | Khurram Jamali | 2010-07-31
| FMH | Fatima Memorial Hospital | 9411 | Training of traditional birth attendants for Fatima memorial hospital | Sheikhupura | To follow up with NGO and reach screening decision | 2010-05-11 | Omar Biabani | 2010-07-31
| KDO | Khangiri Development Organization | 7647 | Water supply scheme in Balakot (next to Mansehra) | Mansehra | To follow up with NGO and reach screening decision | 2010-06-09 | Shaharyar Ahmed | 2010-07-31
| CDF | Country Development Foundation | 9411 | Technical education & Vocational training to 150 beneficiaries in Khanewal | Khanewal | To follow up with NGO and reach screening decision | 2010-06-17 | Ali Farid | 2010-07-31
| AHD | Agency for Human Development | 10393 | Women's vocational training center imparting trade skills training to women in Mardan | Mardan | To follow up with NGO and reach screening decision | 2010-06-28 | Rameez Dossa | 2010-07-31
| GCO | Green Circle Organization | 9000 | Six month long skills training for 50 local trainees (girls & boys) in Jaranwala - Faisalabad | Faisalabad | To follow up with NGO and reach screening decision | 2010-07-02 | Qasim Ashraf | 2010-08-07
|  | Current Month | Previous Month
| Early Stage | 10 | 10
| Approved | 2 | 2
| Total | 12 | 12

## Under Review
Association for the Development of Pakistan | [12 empty] | June 2010
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage | Potential Disbursement (Y/ N)
| SWS | Sahara Welfare Society | District Ghotki, Sindh | 9756 | Setup of a Computer Lab in Noor Lakhan School of Katcha Area | Ahmed Makani, Hajra Rizvi, Shireen Lakhani, Momin Ali Khan | Faris Rahman, Waleed Saraf | Site visit (conducted by a rep. from AIE) on the 18th of May- Project is approved by the team; PT/ EC finalizing monitoring and performance metrics which they will discuss on an internal call with the team this weekend | 2009-10-03 | May 2010 | End | -
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Farzal Dojki, Muneeb Irfan, Saira Chaudhry | Shahan Zafar, Janet Southern | Project stands approved by the EC. PT in the process of finalizing contract/ meeting pre-funding requirements- disbursement anticipated in mid-Aug | 2009-12-31 | May 2010 | End | -
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 10000 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Laterines in total) | Nabeel Hasnain, Najaf Shah, Nada Siddiqqi | Shuaib Siddiqui, Janet Southern, Tarim Wasim | Project stands approved by the EC. PT in the process of drafting contract/ meeting pre-funding requirements- disbursement expected in mid-Aug | 2010-02-17 | May 2010 | End | -
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Arifa Khandwala, Shehryar Khan, Sabeen Shahid, Butool Rizvi | Shuaib Siddiqui, Saad Hasan | PT conducting diligence and preliminary research to establish NGO's expertise around MF. Next project call being scheduled for first week of Aug | 2010-02-19 | July 2010 | Mid | -
| Amir Public School | Nia Ujala | Gujaranwala | 2409 | Development of a school in Gujranwala (set up of classroom's) | Tehniyet Kardar, Mughees Butt | Akbar Bhaidani, Khawaja Ali Farid | Site visit conducted on June 15th- 1st Project call held on 19th June 2010. We have a new volunteer involved in research on ground in Pakistan- PT to take a decision in mid-Aug | 2010-02-08 | July 2010 | Mid | -
| Hope | Health Orientation and Poverty Eradication (HOPE) Foundation | Bagh, AJK | 5791 | Water Supply Schemes in 4 locations in AJK | Waqas Satti, Saba Gul, Muhammad Bilal | Shahan Zafar, Rameez Dossa | Project kick off call held on 1st May 2010. Project call held on 23rd July- Follow up call scheduled for Aug1st. Site visit being planned for mid-Aug | 2010-02-09 | July 2010 | Mid | -
| FESF | Family Educational Services Foundation | Hyderabad | 9523 | Deaf Reach program: to set up a computer lab for a school in Hyderabad | Mustafa Naveed, Batool Aftab, Ali Khan, Khurram Jamali | Waleed Saraf, Qasim Ashraf | Kick off call held on July 10, 2010- PT conducting diligence | 2010-04-25 | 2010-08-01 | Early
| APS | Arshad Public School | AJK | 11619 | Water supply project- installation of water tanks, pipes, etc to provide the school with access to clean water | Being staffed | Mubarik Imam, Dawood Ahmed | Approved from screening - team staffing in progress. Project call being scheduled for Aug 07,2010 | 2010-06-15 | 2010-09-01 | Early
|  | Current Month | Previous Month
| Total Under Review | 9 | 9
Expected Disbursements
| Early Stage Diligence | 2
| Mid-Stage Diligence | 3
| Final Stage Diligence | 3

## In Progress
Association for the Development of Pakistan | [11 empty] | June 2010
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 3644 | 606 | Progress report to be submitted by AHD on 31st September 2009 | - | Third tranche of funding (Rs. 81,000) disbursed on June 17th, 2010- Final tranche to be disbursed on PT's instructions
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 3570 | 5576 | Additional funding to be released after compliance/ submission of detailed forms by NGO | Y | Site visit conducted by 2 ADP volunteers on 13th June. The site visit report has been submitted and assessed as satisfactory by the PT- We wired a second tranche of $2,350 to Al-Qasim in mid-July.
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | 2010-04-20 | TBC | 6854 | 0 | Approved | N | Signed contract received from NGO; Submission of equipment utilization report (quarterly) following the equipment set-up period.
| Projects In Progress | 3
| Remaining Funding | 6182

## Volunteers
Association for the Development of Pakistan | [6 empty] | May 2010
Volunteers
|  | Staffed |  | Openings |  | New Recruits (Staffed)
|  | This Month | Last Month | This Month | Last Month | This Month | Last Month
By Role
| Sourcing | 5 | 6 | Open | Open | 0 | 2
| Project Teams | 22 | 29 | 5 | 7 | 5 | 4 | (Includes site-visit volunteers)
| Evaluation Committee | 12 | 13 | 1 | 3 | 1 | 0
| Fundraising | 11 | 11 | Open | Open | 0 | 0
| Outreach | 6 | 9 | Open | Open | 0 | 2
| Web team | 5 | 4 | 1 | 1 | 1 | 0
|  | 61 | 72 | 7 | 11 | 7 | 8
| Sign-ups | 47
| Leads In Process* | 12
*Refers to leads who have been staffed or are currently in the onboarding process
Issues:
1. Salesforce customization
2. Streamline onboarding process with team leads (demand/supply)
3. Next volunteer introduction/general call

## Financial
Association for the Development of Pakistan | [5 empty] | June 2010
Financials
|  | Current Month | Previous Month | YTD | Notes (current month)
Donations (net)
| Recurring | 340 | 265 | 1875
| # donors | 10 | 9 | 11
| One-time | 1325 | 2475 | 11248.51 | Includes NY concert ticket sales
| # Donations | 33 | 1 | 86
| Total | 1665 | 2740 | 13123.51
| # donors | 43 | 10 | 97
Project Disbursements
| Children's Cancer Hospital |  |  | 6854
Al-Qasim Biogas
| Kharochan School | 957 |  | 957
| Total | 957 | 0 | 7811
Expenses
| Salaries | 735 | 990.0096 | 5685.0384
| Other | 50 | 25 | 422
| Total | 785 | 1015.0096 | 6107.0384
Available Funds
| General |  |  | 52.6
| Earthquake Redevelopment |  |  | 1.85

## Fundraising
Association for the Development of Pakistan |  |  |  |  | June 2010
Fundraising
| Initiatives | Description | Volunteers | Comments | Timeline
| Canadian Registration | Registering ADP as a non-profit organization in Canada to allow tax deductions to donors | Owais Rafiq and Ammar Ali | Application 95% completed. With the exception of a few small pieces of iformation, ready to be submitted. | Submission within 1-2 weeks. First response expected in ~3 months after that. Further information and clarification re-submission can take another 1 month+.
| APPNA conference | ADP had a table at this year's APPNA conference in Dallas, TX | Hassan Baweja | Good visibility among a conference of 5000 attendees. 100+ email addresses for people interested in receiving regular updates (Dastak) and announcements for new projects. Only $100 funds raised | Completed
| Applications to foundations for Al-Qasim project | Applications to WISIONS. Also applying for Ashden awards | Faraz Shakil, Steve Dimon | Applications completed and submitted, waiting for response | June / July
| Formalizing relationship with Uth-Oye (a t-shirt manufacturing company in Karachi) | Uth-Oye to provide funding to select ADP projects on an on-going basis. Uth-oye to build marketing material based on the project for their own CSR branding, and open to sharing this material/videos etc with ADP | Usman Hassan | First funding to come for one plant of Al-Qasim in the next tranche. | Formal MoU to be agreed upon between ADP and Uth-Oye in the next couple of weeks and then the first round of funds to be committed by Uth-Oye
| Boston doctor community presentation | Presentation to a small (~15 person) group of doctors in the Boston area. Being arranged by a volunteer close to ADP who is himself a Doctor, at his house | Usman Hassan and Mohammad Arif | Presentation prepared | Date TBD
| Middle East fundraising campaign | Team of 5 volunteers across Saudi Arabia, UAE and Qatar working on developing a fundraising and awareness campaign in their areas. | Sarmad Rizwan | Materials being put together by Sarmad and team tailored for this audience. The goal is to sign up a large number of individuals for a recurring stream of $20-30. This is what the team feels they can achieve best right now, and they are not shooting for big one off contributions right now. | August kick off. Campaign to continue over the next 3-4 months.

## Initiatives
Association for the Development of Pakistan |  |  |  |  | June 2010
Other Initiatives
| Initiatives | Description | Volunteers | Next Steps | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well has open up other opportunities in Pakistan | Mubarik Imam and Haleema Raheel | ADP registration certificate being revised by the ministry. Haleema to proceed with local bank a/c opening as soon as she has all the required documentation | 2010-07-01
| Sector Teams | To assign 5-6 people teams to research the following sectors/ subsectors: Energy, Empowerment, Education and Health | PEC + Sector Volunteers | We have kicked off our sector teams starting with a general orientation followed by launching our 'Health' and 'Education' sectors only | Ongoing
| Outreach Team | The outreach team shall assume overall responsibility for dissemination and promotion of activities and information. Key areas of development will be sourcing, volunteer strategy, overall awareness and fundraising | Leads: Naveed Ahmad Digital/ Social Media/ Blog: Umbreen Tapal, Nabeel Shakeel; Website/ Newsfeed: Morgan Robinson, Rafique Sheikh; Sourcing: Saira Chaudhry Photography: Asim Iqbal, Iffat Almas; Film: Faraz Ali | Digital media: Leveraging tools like facebook, twitter, linkedin and blogs to get the word out about ADP; Sourcing:Tapping into NGO networks, targeting our niche NGO's Website: Updating newsfeed and fundraising content writing | Ongoing
| Volunteer Onboarding | New process for thorougher evaluation of volunteers prior to staffing. | Khurram Owais, Naveed Ahmed | New process outline emailed to leadership team Next step: Finalize and implement | Ongoing
| New VM Recruitment | NEW VM (Hiring) | Khurram Owais | Naima Hasan - new VM recruited | 2010-07-01
| New OD Recruitment | NEW OD (Hiring) | Haleema Raheel | OD Job Announcement e-mail sent out to ADP network in June. We have shortlisted 5 applicants after our 1st Phase screening- Finalization of new OD expected at the end of August. | 2010-08-01