## Cover
Association for the Development of Pakistan
Monthly Report
2011-04-11

## Proposals
Association for the Development of Pakistan | [8 empty] | April 2011
New Proposals
Approved from screening
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Project looks good on paper. Naima doing some more research to make sure it's worth staffing. | 2011-03-03 | Naima Hasan | Mid May 2011
| YRC | Youth Resource Center | 11764 | Water Supply Scheme (Installation of hand-pumps) | Nowshera | Project looks good on paper. Mehreen doing some more research to make sure it's worth staffing. | 2011-03-17 | Mehreen Siddiqi | Mid May 2011
| KWES | Kohsar Welfare and Educational Society | 11717 | Water Supply Scheme | Sardari Katkair Village, Muzaffarabad, AK | Rejected. Concerns with regards to critical need - some infrastructure already exists. Needs assessment not done by the NGO. | 2011-03-21 | Naima Hasan | End Apr. 2011
| LS | Lifeline Society | 10235 | Water Supply Scheme (Installation of hand pumps) | Near Multan and Muzaffargarh | Checklist complete. Decision to be made by Shahan and Asad. | 2011-03-25 | Asad Mawjee | Mid May 2011
| SS | Sudhaar Society | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Kasur | Approved from screening. Project team to be staffed. | 2011-03-25 | Umbreen Tapal | End Apr. 2011
| SFL (Health) | Sahara for Life Trust | 14647 | Equipment for existing hospital | Sialkot | Checklist complete. Decision to be made by Shahan and Khurram. | 2011-03-25 | Khurram Jamali | Mid May 2011
| SIDO | Social Integrated Development Organization | 10674 | Water Supply Scheme (Installation of hand pumps) | Charsadda | Checklist complete. Decision to be made by Shahan and Qasim. | 2011-03-30 | Qasim Ashraf | Mid May 2011
| AMWS | Al-Rehman Medical Welfare Society | 8823 | Upgrade of existing medical center | Karachi | Pending screening | 2011-04-04 | Dawood Ahmed | End May 2011
| SHATAC | Shehri Ijtamati Taraqiati Council | 11764 | Purchase of Ultrasound machine and installation of incinerator | Mandi Bahauddin | Pending screening | 2011-04-13 | Haleema Raheel | End May 2011
| ABKT | Association for Behavior and Knowledge Transformation | 11032 | Installation of hand pumps | Lower Dir | Rejected. Lower Dir is quite far from Peshawar and a site visit might be difficult to arrange. Also, NGO does not have a lot of experience in water projects. | 2011-04-14 |  | Early May 2011
| HEED | Health Education Environment Development Association | 16470 | Rehabilitation of flood affected schools | Neelum Valley, AK | Pending screening | 2011-04-17 | Jazib Zahir | End May 2011
| WAFA | Welfare Awareness & Facilitation Association | 9345 | Rehabilitation of flood affected schools | Nowshera | To be assigned to screener | 2011-04-20 |  | End May 2011
|  | Current Month | Previous Month
| Early Stage | 9 | 7
| Approved | 1 | 3
| Rejected | 2 | 2
| On hold | 0 | 0
| Total | 12 | 12

## Under Review
Association for the Development of Pakistan | [11 empty] | April 2011
Projects Under Review
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| APS | Arshad Public School | AJK | 11619 | Water supply project-installation of water tanks, pipes etc to provide the school with access to clean water | Uzaib Saya, Habiya Beg, Mariam Haqqie | Mubarik Imam, Dawood Ahmed | PRCS has recently built a pipeline in the area and installed a tap in the school. According to Basharat, this is not sufficient for the needs of the children. Raja to send Project Completion Report to Mehreen. Team to make a decision soon. | 2010-06-15 | 2011-05-01 | End
| SSVDO | Shama Social Village Development Organization. | Charsadda | 8029 | Drinking Water Supply Schemes for Flood Affected Families through Installation of 65 Hand Pumps | Jazib Zahir, Danish Iqbal, Jawad Hasan | Syed Shahan Zafar, Janet Southern | Rejected. Site visit revealed that the targeted area already had several hand-pumps that were being used by the villagers and hence the need wasn't critical. | 2010-08-29 | Apr. 2011 | End
| DLG Construction | De Laas Gul Welfare Program | Charsadda and Nowshera | 9412 | Reconstruction of houses in Charsadda and Nowshera | Saba Gul, Laraib Mahar, Shammi Quddus | Rameez Dossa, Arifa Khandawalla | Site visit conducted in mid April and report submitted. Team to make a decision based on the report. Probability of getting rejected. | 2010-11-05 | 2011-05-01 | End
| DLG Water | De Laas Gul Welfare Program | Charsadda and Nowshera | 9647 | Installation of hand-pumps | Naveed Alam, Ayesha Rabbani, Butool Rizvi | Shahan Zafar, Mehreen Siddiqi | Site visit conducted in mid April and report submitted. Team to make a decision based on the report. Probability of getting rejected. | 2010-11-04 | Apr. 2011 | End
| SDO | Saibaan Development Organization | Mansehra | 7294 | Setting up of a water filtration plant | Bilal Hussain, Sadia Ahmed, Ammar Naqvi | Rameez Dossa, Dawood Ahmed | Project in mid stage of evaluation | 2010-12-24 | 2011-05-11 | Mid
| PLC | Punjnad Lions Club | Muzaffargarh | 20000 | Re-construction of houses | Uzaib Saya, Shehryar Khan, Najiyeh Akbar | Mubarik Imam, Minhaj Patel | Project in mid stage of evaluation | 2010-11-11 | 2011-05-01 | Mid
| RWO | Rabita Welfare Organization | Layyah | 11765 | Construction of latrines | Waqas Satti, Mariam Haqqie, Saad Khan | Waleed Saraf, Khurram Jamali | Project in mid stage of evaluation. Probability of getting rejected. | 2010-11-20 | 2011-05-01 | Mid
| CCFP | Child Care Foundation of Pakistan | Nankana; Sheikhupura | 11765 | Setting up computer labs in 3 existing schools | Nabeel Hasnain, Minza Zahid, Arsalan Mushtaq | Akbar Bhaidani, Hasham Mehmood | Project in mid stage of evaluation | 2010-11-20 | May/June 2011 | Mid
| Kachho | Kachho Foundation | Bahawalpure, Dadu | 18747 | Re-construction of houses | Owais Rafiq, Ali Taufeeq, Ahsan Hussain | Saad Hasan, Aized Rabbani | Team generally in favor of project. Site visit to be conducted in mid May, Team to confirm deicison after the visit. | 2010-11-11 | 2011-05-11 | End
| HOPE | HOPE Foundation | AK | 9009 | Rural Water Supply Project | Najaf Ali Shah, Mehreen Iqbal, Ruqaiya Ramzan | Shahan Zafar, Mehreen Siddiqi | Project in mid stage of evaluation. Project team has contacted Mr. Mubshir to determine feasibility of the project. Site visit to be conducted soon. | 2011-01-22 | 2011-06-01 | Mid
| CAP | Community Advance Program | Lahore | 7859 | Computers and furniture for existing schools | Jawad Hasan, Meher Makda, Mahira Kalim | Natasha Qureshi, Qasim Ashraf | Project in early stages of evaluation | 2011-01-29 | 2011-06-11 | Early
| ARBAN | Association for Realization of Basic Needs (ARBAN) | Karachi | 11747 | Drinking Water, Hand Washing, Sanitation Facility Renovation & Maintenance work in 2 schools | Adnan Pathan, Bilal Sarfaraz, Shiza Shahid | Tarim Wasim, Asad Mawjee | Project in early stages of evaluation. Probability of getting rejected. | 2011-01-12 | 2011-05-11 | Mid
| KRT | Karachi Relief Trust | Sujawal District, Sindh | 14705 | Reconstruction of homes for flood victims | Adeel Qaiser, Hadia Raheel, Alexis Saba | Shahan Zafar, Jazib Zahir | Approved from screening. Project kick off call scheduled for May 8, 2011 | 2011-02-17 | Jun/Jul-11 | Early
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Adnan Pathan, Adeel Naeem, Taha Mashhadi | Waleed Saraf, Dawood Ahmed | Approved from screening. Project kick off call scheduled for May 14, 2011 | 2011-02-01 | 2011-07-11 | Early
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 11764 | Mishtimba Village family latrines | Danish Iqbal, Abdullah Hasan, Habiya Beg | Tarim Wasim, Nabeel Hasnain | Approved from screening. Project kick off call scheduled for May 15, 2011 | 2011-04-09 | 2011-07-11 | Early
|  | Current Month | Previous Month
| Early Stage Diligence | 4
| Mid-Stage Diligence | 6
| Final Stage Diligence | 4
| Rejected | 1
| Total | 15 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | April 2011
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 3644 | 606 | Mr. Yaseen to confirm further funding needs | Y | Third tranche of funding (Rs. 81,000) disbursed on June 17th, 2010. School is operational with 74 students enrolled currently. Enrollment has gone down because people migrated in anticipation of the floods and because families are not keen on sending older girls to school. School might need remaining amount for maintenance and repair (no response from Mr. Yaseen yet). School also applying for govt. funds .
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 6511 | 2635 | End May, 2011 (End of Phase III) | Y | Al Qasim received a third tranche of $2,941 on Feb 27, 2011. Work on Phase III to be completed by the end of May, 2011. 4 biogas plants have been constructed and will be functional in another 2 weeks. 5th plant is under construction.
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | 2010-04-20 | TBC | 6854 | 0 | Next quarterly Report to be submitted in July/Aug. 2011 | N | Signed contract received from NGO. First Equipment Utilization Report submitted in Aug. 2010. Site visit conducted by Umbreen Tapal on Oct. 16, 2010. Another visit conducted by Saad Halim in Feb., 2011. Second Equipment Utilization Report submitted in Apr., 2011.
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Aug. 2010 | TBC | 4957 | 0 | Early 2011 (Completion of at least 4 installations) | N | Report A and B submitted. 4 pumps have been installed. Problems with regards to 5th. Site visit conducted by Imad Rashid in Feb., 2011. According to site visit report, 3 pumps are functioning fine whereas one is pumping muddy water which is being used for feeding animals. Need for better identification of locations for hand-pump installation has also been mentioned. Team has decided to put the project on hold for now. MGPO has ADP's money that was sent for the installation of the 5th pump - need to contact MGPO and discuss the issue.
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 11308 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Latrines in total) | Oct. 2010 | TBC | 11308 | 0 | May, 2011 (Report on completion of project) | N | Project has come to an end with construction of all latrines complete. HEED held its last Hygiene Promotion session in early Apr., 2011. HEED team intends to monitor the project according to the agreed upon monitoring mechanism and will undertake a survey 12 months from completion of the project. Potential site visit to be arranged to confirm HEED update. Draft Completion Report submitted.
| NEEDS (flood relief) | Network for Education and Economic Development Services | Charsadda | 5000 | Installation of handpumps to provide clean drinking water | Sep./Oct. 2010 | TBC | 5000 | 0 |  | N | Project has come to an end with all 12 hand-pumps constructed and functioning well. Project Completion Report has been received. Potential site visit to be arranged to confirm NEEDS update.
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School in Katch area | Jan. 2011 | TBC | 4705 | 4705 | Report to be submitted by SWS on completion of Phase I | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. Construction of computer lab is complete. Finishing/electrification is in the process and will be completed by May 15, 2011. Security Agreement between School Management and Village elders has been signed.
| Amir Public School | Nia Ujala | Gujranawala | 7032 | Development of a school in Gujranwala (setting up of classrooms | Jan. 2011 | TBC | 5506 | 1526 | Report A to be submitted when classroom becomes functional | Y | ADP wired first tranche of $2,706 to Amir Public School in late Jan., 2011 and then second tranche of $2,800 in Mar., 2011. Site visit to APS conducted by Arsalan Mushtaq on Mar. 21, 2011. Construction will be completed by mid May, 2011. APS to share the following soon: (i) Details of the Teaher and the Assistant Teacher who have been hired (ii) Information on the 30 students (50% girls) who have been admitted (iii) Details of Teachers Training Plan.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 2600 | 5753 | Mr. Humayun to inform ADP when women have been registered and hens are to be purchased | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. Mr. Humayun to confirm receipt. According to Mr. Humayun, women will be identified and registered for the project in the next couple of months and hens will be provided after that (once the price of hens comes down).
| Projects In Progress | 9
| Remaining Funding | 15225

## Volunteers
Association for the Development of Pakistan | [9 empty] | April 2011
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 8 | 3 | 1 |  | 0 | 0 | 0 | 8 PECs are staffed presently, Shahan, Rameez, Mubarik, Tarim & Waleed are on 2 projects each simultaneously. Rameez has said he can take one more after a couple of weeks when the DLG project reaches a decision
| Evaluation Committee | 11 | 3 | 0 |  | 2 | 1 | 1 | 11 ECs are staffed, Mehreen is on 2 projects and Dawood is on 3 projects. Asad Mawjee is a new EC, he is on his first project right now. Muhammad Waqar and Waqar Ghani need to be assesed by a PEC to determine whether they can take on a EC role. Have reached out to Ahmed Makani to find out if he can take up a project
| Project Team Leads | 12 | 3 | 3 |  | 0 | 2 | 0 | Asma Panjwani and Supriya Balsekar need to be trained as PTLs. Farzal Dhojki is available; Danish Iqbal and Adnan Pathan have capacity to take on multiple projects. The DLG Projects and Kachho are close to a decision so those team members may have capacity in a few weeks time
| Project Team | 28 | 6 | 8 |  | 14 | 6 | 6 | There is a sufficient pipeline of PT volunteers who can be staffed on new projects
| Site Visits | 2 | 3 | 5 |  | 8 | 3 | 3 | Muhammad Ishaq conducted visits for both DLG projects. A site visit volunteer Ali Raza is available for the Kachho project; the visit will be conducted in mid May. Khizr Sb has agreed to conduct the visit for the HOPE Water project in mid May. Site visits will also be needed for the NEEDS water pumps project to verify the report of the installation of 12 pumps and to confirm the completion of the HEED project
| Sourcing | 3 | 0 | 0 |  | 16 | 0 | 0 | The sourcing strategy has undergone some change in view of the alteration in organizational policy of taking up stronger, low risk projects. Sourcing will still be managed by Mehreen, Naima and Umbreen
| Fundraising | 8 | 4 | 3 |  | 11 | 2 | 0 | The fundraising team roles will be put up on the website to increase outreach. Adeel Naeem (new volunteer who is keen on fundraising) is on a project team currently to understand the organization and its processes better, he can set up a chapter then in Singapore. Hadya Raheel is interested in taking up the role developing partnerships. She is also on a project team right now for the same purpose. Adnan Pathan is willing to get more involved on this front as well
| Media | 5 | 0 | 4 |  | 16 | 1 | 1 | Ayesha Shahid, Ayesha Sarfraz, Natalia Bokhari, Sanaa Qureshi & Nabeel Ahmed are actively involved. Fizza Shah is interested in helping create some visibility for ADP in the print and visual media
| Web team | 2 | 2 | 1 |  | 2 | 0 | 0 | Need salesforce volunteer - will post on current opportunities page on the website
| Legal | 3 | 1 | 0 |  | 1 | 0 | 0 | Need pro bono legal help in Pakistan.
| Marketing | 0 | 3 | 3 |  | 6 | 2 | 0 | The search for volunteers for the marketing team continues, Sara Kamal will get in touch with us after a few weeks due to some professional commitments. The roles will be posted on the website as well.
| Other | 2 | 2 | 0 |  | 4 | 2 | 2 | Adnan Iqbal and Junaid Tahir have joined as part of the KM team and will be leading this initiative, its at an initial stage right now. PMI - Karachi has also agreed to provide assistance/support for this initiative
| Total | 84 | 30 | 28 |  | 80 | 19 | 13
| Total signups | 20
| New projects launched | 4
| New projects expected | 3 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
EC training and availability
Tech/Marketing/Media/Legal/Fundraising teams need new members
Salesforce Volunteer needed
Initiatives:
Upcoming volunteer activities will be posted on the 'current opportunities' page on the website
Through collaborations with Engro Corp., SCB and PMI Pakistan, new volunteers will be recruited and these organizations have agreed to assist in creating visibility for ADP within their networks
Corporate presentations will be set up through our existing volunteers to increase visibility, Phillip Morris - Pakistan, HBL & PMI Karachi have shown interest

## Financial
Association for the Development of Pakistan |  |  |  |  | April 2011
Financials
|  | Current Month | YTD | Notes (current month)
Donations (net) |  | 2825 | 10348
Project Disbursements
| Microfinance for Poultry |  | 2600
| Sokar Village Latrines |  | 8800
| Amir Public School |  | 5512
| Al Qasim Biogas Plants |  | 2943
| SWS Computer Lab |  | 4729
| Total |  | 24584
Expenses
| Salaries | 1490 | 6196
| Other | 3626 | 4306 | Includes fundraising expenses and filing penalty
| Total | 5116 | 10502
Available Funds
| General |  | $19K
| Flood Redevelopment |  | $30K

## Fundraising
Association for the Development of Pakistan |  |  |  |  | April 2011
Fundraising
| Initiatives | Description | Volunteers | Comments | Timeline
| Utilizing causes as an approach to social media based fundraising for a project | ADP is set up on causes and we can create a project page for a specific ADP project and raise funds through this channel | Usman Hassan | It will be a trial for a project to see how useful and effective it is for our purposes. Helps spread the word and hopefully get more people to follow ADP | April-May 2011
| Planning for summer fundraising campaign | Building a team of volunteers for the core central positions and city/region specific teams, in preparation for a summer fundraising campaign once we have 2-3 projects and a target for at least $10k of fundraising | Usman Hassan | Some discussion on fundraising opportunities within their environment (Tufts) or through other channels. | May-June 2011

## Initiatives
Association for the Development of Pakistan |  |  |  |  | April 2011
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Mubarik Imam | Moved to a new lawyer. Will try to register as "Association for Development" or "ADP". In the process of building a rapport with the Registrar - will apply for registration by the end of May/early June, 2011 | NA
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz | Constantly updating projects pages on the website. Annual Report released. Next issue of Dastak to go out soon. Volunteer Opportunities now open. Working on the Wikipedia page | Ongoing
| Volunteer Review | Group to review ADP's Volunteer Management Processes (recruiting, orientation, screening, training, staffing, feedback) with the aim of improving them. | Naima Hasan; Mehreen Siddiqi; Tarim Wasim; Mubarik Imam | Naima to draft a document detailing processes related to volunteers. Team to discuss issues like Volunteer retention, feedback, recruitment, training and recognition. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Adnan Iqbal, Junaid Tahir (Team Leads) | Team Leads have been identified and briefed of our requirements. Tarim, Naima and Mehreen to provide support to them as they initiate the process and on an ongoing basis. To add tech support (volunteers) to the team. | Ongoing
| Volunteer Manager (VM) position | To hire a new full time VM |  | VM spec has been circulated. Waiting to receive resumes | 2011-06-01
| Partnerships Development | To develop relationships with instituitions/organizations as volunteer & funding partners to increase visibility and out reach | Nabeel Ahmed/Usman Hassan | Hadia Raheel is interested in taking this up in Toronto, Nabeel Ahmed will meet with her to determine suitability/capability. We need volunteers engaged in this initiative in multiple cities | Ongoing