## Cover
Association for the Development of Pakistan
Monthly Report
2011-05-01

## Proposals
Association for the Development of Pakistan | [8 empty] | May 2011
New Proposals
Approved from screening
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Project approved. Team to be staffed | 2011-03-03 | Naima Hasan | Mid May 2011
| YRC | Youth Resource Center | 11764 | Water Supply Scheme (Installation of hand-pumps) | Nowshera | Project approved. Team to be staffed | 2011-03-17 | Mehreen Siddiqi | Mid May 2011
| LS | Lifeline Society | 10235 | Water Supply Scheme (Installation of hand pumps) | Near Multan and Muzaffargarh | Project approved. Team to be staffed | 2011-03-25 | Asad Mawjee | Mid June 2011
| SFL (Health) | Sahara for Life Trust | 14647 | Equipment for existing hospital | Sialkot | Rejected. SFL is a big organization that has a lot of access to capital. | 2011-03-25 | Khurram Jamali | End May 2011
| SIDO | Social Integrated Development Organization | 10674 | Water Supply Scheme (Installation of hand pumps) | Charsadda | Project discussed on May's screening call. Some more research to be done before decision is made | 2011-03-30 | Qasim Ashraf | 2011-06-01
| AMWS | Al-Rehman Medical Welfare Society | 8823 | Upgrade of existing medical center | Karachi | Proposal to be revised and sent again | 2011-04-04 | Dawood Ahmed | End May 2011
| SHATAC | Shehri Ijtamati Taraqiati Council | 11764 | Purchase of Ultrasound machine and installation of incinerator | Mandi Bahauddin | Proposal rejected. The project was really big and ADP's share was going to be a very small percentage of the entire project | 2011-04-13 | Haleema Raheel | End May 2011
| HEED | Health Education Environment Development Association | 16470 | Rehabilitation of flood affected schools | Neelum Valley, AK | Project approved. Team to be staffed | 2011-04-17 | Jazib Zahir | Early June 2011
| WAFA | Welfare Awareness & Facilitation Association | 9345 | Rehabilitation of flood affected schools | Nowshera | Pending screening | 2011-04-20 | Mehreen Siddiqi | End June 2011
| UDO | UFAQ Development Organization | 16329 | Installation of hand-pumps | Kot Addu, Muzaffargarh | Pending screening | 2011-05-03 | Naima Hasan | End June 2011
| RDO | Rural Development Organization | 11543 | Upgrade/extension of existing medical center | Faisalabad | Pending screening | 2011-05-14 | Haleema Raheel | End June 2011
| FIDA | Foundation for Integrated Development Action | 11761 | Setting up bio-gas plants | D.I.Khan | Pending screening | 2011-05-16 | Khurram Jamali | End June 2011
| YDO | Youth Development Organization | 11764 | Installation of hand-pumps | Rajanpur, Punjab | Pending screening | 2011-05-18 | Dawood Ahmed | End June 2011
| MBB | Muhammadi Blood Bank | 11764 | Equipment for Thalassemia center | Karachi | To be assigned to screener | 2011-05-26
| MHSF | M.H. Sufi Foundation | 11764 | Expansion of School - Kaseese Branch | Hafizabad | Pending screening | 2011-05-26 | Naima Hasan | End June 2011
|  | Current Month | Previous Month
| Early Stage | 8 | 9
| Approved | 4 | 1
| Rejected | 3 | 2
| On hold | 0 | 0
| Total | 15 | 12

## Under Review
Association for the Development of Pakistan | [11 empty] | May 2011
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| APS | Arshad Public School | AJK | 11619 | Water supply project-installation of water tanks, pipes etc to provide the school with access to clean water | Uzaib Saya, Habiya Beg, Mariam Haqqie | Mubarik Imam, Dawood Ahmed | Site visit to be conducted by Khizr saab in the middle of June. Team to make a decision based on the site visit report. | 2010-06-15 | 2011-06-11 | End
| DLG Construction | De Laas Gul Welfare Program | Charsadda and Nowshera | 9412 | Reconstruction of houses in Charsadda and Nowshera | Saba Gul, Laraib Mahar, Shammi Quddus | Rameez Dossa, Arifa Khandawalla | Rejected. DLG did not have the required experience and the ability to carry out a construction project. Also, DLG's credibility in question since they asked the site visit volunteer to keep certain things to himself. | 2010-11-05 | 2011-05-01 | End
| DLG Water | De Laas Gul Welfare Program | Charsadda and Nowshera | 9647 | Installation of hand-pumps | Naveed Alam, Ayesha Rabbani, Butool Rizvi | Shahan Zafar, Mehreen Siddiqi | Rejected. Site visit revealed that DLG did not have the required ability to install hand-pumps . | 2010-11-04 | 2011-05-11 | End
| SDO | Saibaan Development Organization | Mansehra | 7294 | Setting up of a water filtration plant | Bilal Hussain, Sadia Ahmed, Ammar Naqvi | Rameez Dossa, Dawood Ahmed | Approved. Project in execution stage. | 2010-12-24 | 2011-06-11 | End
| PLC | Punjnad Lions Club | Muzaffargarh | 20000 | Re-construction of houses | Uzaib Saya, Shehryar Khan, Najiyeh Akbar | Mubarik Imam, Minhaj Patel | Project in mid stage of evaluation. | 2010-11-11 | Jun/Jul-11 | Mid
| RWO | Rabita Welfare Organization | Layyah | 11765 | Construction of latrines | Waqas Satti, Mariam Haqqie, Saad Khan | Waleed Saraf, Khurram Jamali | Project in mid stage of evaluation. | 2010-11-20 | Jun/Jul-11 | Mid
| CCFP | Child Care Foundation of Pakistan | Nankana; Sheikhupura | 11765 | Setting up computer labs in 3 existing schools | Nabeel Hasnain, Minza Zahid, Arsalan Mushtaq | Akbar Bhaidani, Hasham Mehmood | Project in mid stage of evaluation. | 2010-11-20 | Jun/Jul-11 | Mid
| Kachho | Kachho Foundation | Bahawalpure, Dadu | 18747 | Re-construction of houses | Owais Rafiq, Ali Taufeeq, Ahsan Hussain | Saad Hasan, Aized Rabbani | The site visit report raised concerns around Kachho's ability to undertake the project. Probability of getting rejected. | 2010-11-11 | 2011-06-11 | End
| HOPE | HOPE Foundation | AK | 9009 | Rural Water Supply Project | Najaf Ali Shah, Mehreen Iqbal, Ruqaiya Ramzan | Shahan Zafar, Mehreen Siddiqi | Project in mid stage of evaluation. Site visit to be conducted soon. | 2011-01-22 | 2011-06-01 | Mid
| CAP | Community Advance Program | Lahore | 7859 | Computers and furniture for existing schools | Jawad Hasan, Meher Makda, Mahira Kalim | Natasha Qureshi, Qasim Ashraf | Project in mid stage of evaluation. Site visit has been conducted and has revealed several positive aspects of the project. | 2011-01-29 | 2011-06-11 | Mid
| ARBAN | Association for Realization of Basic Needs (ARBAN) | Karachi | 11747 | Drinking Water, Hand Washing, Sanitation Facility Renovation & Maintenance work in 2 schools | Adnan Pathan, Bilal Sarfaraz, Shiza Shahid | Tarim Wasim, Asad Mawjee | Rejected. Doubts as to NGO's ability to execute the project. Conversations with the school principal revealed other critical needs not identified by the NGO. | 2011-01-12 | 2011-05-11 | End
| KRT | Karachi Relief Trust | Sujawal District, Sindh | 14705 | Reconstruction of homes for flood victims | Adeel Qaiser, Hadia Raheel, Alexis Saba | Shahan Zafar, Jazib Zahir | Project in initial stage of evaluation. | 2011-02-17 | Jul-Aug-11 | Early
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Adnan Pathan, Adeel Naeem, Taha Mashhadi | Waleed Saraf, Dawood Ahmed | Early-Mid stage of evaluation. Team generally in support of the project. Site visit to be conducted | 2011-02-01 | 2011-07-11 | Mid
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 11764 | Mishtimba Village family latrines | Danish Iqbal, Abdullah Hasan, Habiya Beg | Tarim Wasim, Nabeel Hasnain | Initial stage of evaluation | 2011-04-09 | 2011-08-11 | Early
| SS | Sudhaar Society | Kasur | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Farzal Dhojki, Babar Khan, Muzammal Ashraf | Ramwwz Dossa, Ahmed Makani | Initial stage of evaluation | 2011-03-25 | 2011-08-11 | Early
|  | Current Month | Previous Month
| Early Stage Diligence | 3
| Mid-Stage Diligence | 6
| Final Stage Diligence | 3
| Rejected | 3
| Total | 15 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | May 2011
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 3644 | 606 | Mr. Yaseen to confirm further funding needs | Y | Third tranche of funding (Rs. 81,000) disbursed on June 17th, 2010. School is operational with 74 students enrolled currently. Enrollment has gone down because people migrated in anticipation of the floods and because families are not keen on sending older girls to school. School might need remaining amount for maintenance and repair (no response from Mr. Yaseen yet). School also applying for govt. funds .
| Al-Qasim | Al Qasim Foundation | District Khushab | 9146 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 6511 | 2635 | June 2011 (End of Phase III) | Y | Al Qasim received a third tranche of $2,941 on Feb 27, 2011. Phase III (construction of 5 plants) completed in May, 2011). AQF to submit: (i) Pictures of all 5 bio-gas plants with each plant identified by a plant number on the dome (ii) Completed list of beneficiaries document along with the contact number for the head of each household. Last tranche to be released after AQF submits these details.
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | 2010-04-20 | TBC | 6854 | 0 | Next quarterly Report to be submitted in July/Aug. 2011 | N | Signed contract received from NGO. First Equipment Utilization Report submitted in Aug. 2010. Site visit conducted by Umbreen Tapal on Oct. 16, 2010. Another visit conducted by Saad Halim in Feb., 2011. Second Equipment Utilization Report submitted in Apr., 2011.
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Aug. 2010 | TBC | 4957 | 0 | July 2011 (after 5th pump has been installed) | N | Report A and B submitted. 4 pumps have been installed. Problems with regards to 5th. Site visit conducted by Imad Rashid in Feb., 2011. According to site visit report, 3 pumps are functioning fine whereas one is pumping muddy water which is being used for feeding animals. Team has decided to get the 5th pump installed by MGPO and then cancel the remaining funding. MGPO in the process of identifying a suitable location for the installation of the 5th pump.
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 11308 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Latrines in total) | Oct. 2010 | TBC | 11308 | 0 | June 2011 (Report B) | N | Project has come to an end with construction of all latrines complete. HEED held its last Hygiene Promotion session in early Apr., 2011. HEED team intends to monitor the project according to the agreed upon monitoring mechanism and will undertake a survey 12 months from completion of the project. Potential site visit to be arranged to confirm HEED update. Report B to be submitted after an initial survey is carried out.
| NEEDS (flood relief) | Network for Education and Economic Development Services | Charsadda | 5000 | Installation of handpumps to provide clean drinking water | Sep./Oct. 2010 | TBC | 5000 | 0 | N/A | N | Project has come to an end with all 12 hand-pumps constructed and functioning well. Project Completion Report has been received. Potential site visit to be arranged to confirm NEEDS update.
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School in Katch area | Jan. 2011 | TBC | 4705 | 4705 | Report to be submitted by SWS on completion of Phase I | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. Construction of computer lab is complete. Finishing/electrification is in the process and will be completed by May 15, 2011. Security Agreement between School Management and Village elders has been signed.
| Amir Public School | Nia Ujala | Gujranawala | 7032 | Development of a school in Gujranwala (setting up of classrooms | Jan. 2011 | TBC | 6106 | 926 | Report A to be submitted when classroom becomes functional | Y | ADP wired first tranche of $2,706 to APS in late Jan., 2011 and then second tranche of $2,800 in Mar., 2011. Third tranche of $600 received by APS in May, 2011. Room construction and furnishing complete. APS has sent over pictures of children in the classroom.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 2600 | 5753 | Mr. Humayun to inform ADP when women have been registered and hens are to be purchased | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. Preliminary work (drafting a simple Excel sheet for keeping records) has been completed. NEEDS is holding regular community meetings to create awareness and to register potential women for the credit scheme. 20 women have submitted applications - once decisions are made and the women are selected, poultry will be provided to them. Progress has been slow because of the heat.
| Projects In Progress | 9
| Remaining Funding | 14625

## Volunteers
Association for the Development of Pakistan | [9 empty] | May 2011
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 8 | 4 | 0 |  | 0 | 0 | 0 | 8 PECs are staffed presently, Shahan, Rameez, Mubarik & Waleed are on 2 projects each simultaneously. Saad will have capacity in July - Aug, Natasha is travelling until mid June so will not be able to take on anything new right now.
| Evaluation Committee | 10 | 4 | 4 |  | 0 | 1 | 1 | 10 ECs are staffed, Dawood is on 3 projects. Mehreen and Khurram Jamali have capacity to take on a project each. Asad Mawjee is not on a project currently so can potentially take one on as well. The Kachho project is almost at an end so Aized Rabbani may be available then. Nabeel Hasnain is now an EC and is on the HEED (M) project
| Project Team Leads | 11 | 4 | 4 |  | 0 | 2 | 2 | 11 PTLs are staffed on projects right now. Supriya Balsekar and Saman Nizami were trained as new PTLs last week and are available to take on a project. Saba Gul is available, Adnan Pathan can also take on one more project. Isfandiyar Shaheen had said that he would have capacity in June so he can probably take on a project as well.
| Project Team | 23 | 8 | 10 |  | 16 | 6 | 6 | KRT,SFL, Sudhaar and HEED (M) were staffed in May, the rest are all on going projects. There have been a lot of new sign ups and 8 new project team volunteers have been onboarded and trained. 2 of them have also been staffed on projects. Volunteers from the existing pool are also available
| Site Visits | 4 | 2 | 6 |  | 15 | 3 | 3 | Ali Raza conducted the site visit for the Kachho project; the team will be taking a decision on it now. Waqas Sajjad conducted the visit for Saibaan and the project has been approved for funding. Khizr Sb is supposed to conduct the visit for APS water pipeline and Jazib Zahir conducted the site visit for CAP. One volunteer is needed to visit the SFL site and we may need 1 more for the HOPE water project
| Sourcing | 3 | 0 | 0 |  | 16 | 0 | 0 | The sourcing strategy has undergone some change in view of the alteration in organizational policy of taking up stronger, low risk projects.
| Fundraising | 8 | 4 | 3 |  | 14 | 2 | 2 | Hayat Khan will be coming on board for fundraising. Adnan Pathan is available to be more involved on this. Adeel Naeem (new volunteer who is keen on fundraising) is on a project team currently to understand the organization and its processes better, he can set up a chapter then in Singapore. Muhammad Waqas is helping organizing a gathering in NY with Usman to discuss the next fundraising event. PDF holding a BBQ in Toronto to raise funds for the NEEDS Poultry project.
| Media | 4 | 0 | 4 |  | 10 | 0 | 0 | Ayesha Shahid, Natalia Bokhari, Sanaa Qureshi & Nabeel Ahmed are actively involved.
| Web team | 2 | 5 | 0 |  | 0 | 0 | 0 | Need a volunteer for salesforce . Azhar has asked for more volunteers on the Tech team, will post the opportunities for that
| Legal | 3 | 1 | 0 |  | 2 | 0 | 0
| Marketing | 1 | 4 | 3 |  | 6 | 1 | 1 | 4 new resumes have come through for the marketing team and seem promising. I have set up a conversation with the candidates next week to find out more.Hadia Raheel has come on board for the partnership development role.
| Other | 3 | 2 | 0 |  | 0 | 2 | 2 | Adnan Iqbal, Junaid Tahir and Hasan Karahan have joined as part of the KMS team. There are 3 volunteers available to come on board for the Eco Energy project, the initiative will be led by Mubarik.
| Total | 80 | 38 | 34 |  | 79 | 17 | 17
| Total signups | 30
| New projects launched | 4
| New projects expected | 4 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
PEC availability
Tech/Marketing/Media/Legal/Fundraising teams need new members
Initiatives:
Upcoming volunteer activities are being posted on the 'current opportunities' page on the website
Recruitment for the new VM is underway. 2 candidates are in the third phase of the process
VM User Manual is being compiled to ensure maximum information is available to the new VM
Information for all active volunteers has been consolidated on one google spreadsheet

## Fundraising
Association for the Development of Pakistan |  |  |  |  | May 2011
Fundraising
| Initiatives | Description | Volunteers | Comments | Timeline
| HBS charity auction | ADP was selected as one of the beneficiary organizations for a charity auction at Harvard Business School | Shahan Zafar | Raised a total of $10k | April-May
| Partnerships management volunteer on-board and oriented | This volunteer would help manage relationships with existing partner organizations, providing information, seeking funding on projects and maintaining a certain level of communication. Volunteer will also build new partnerships with relevant organizations | Hadia Raheel | Next step: Pro-actively looking at organization to partner with and build relationships with | May-June
| Summer fundraising campaign | Building a team of volunteers for the city/region specific teams, in preparation for a summer fundraising campaign once we have 2-3 projects and a target for at least $10k of fundraising | Usman Hassan | Planning an event in New York city in August / September - Muhammad Waqas taking lead in New York, as Ahmad Sheikh is looking to transition out of his role. | June-August

## Initiatives
Association for the Development of Pakistan |  |  |  |  | May 2011
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Mubarik Imam | Moved to a new lawyer. Will try to register as "Association for Development" or "ADP". In the process of building a rapport with the Registrar - will apply for registration by the end of May/early June, 2011 | NA
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz; Vajiha Sipra | Constantly updating projects pages on the website. April's issue of Dastak was published. Vajiha Sipra is a new addition to the team. ADP doing well on social media. As a result of Nabeel's presentation to PDF, they're hosting a BBQ - the proceeds of which will go to the NEEDS Poultry project. | Ongoing
| Volunteer Review | Group to review ADP's Volunteer Management Processes (recruiting, orientation, screening, training, staffing, feedback) with the aim of improving them. | Naima Hasan; Mehreen Siddiqi; Tarim Wasim; Mubarik Imam | Naima to draft a document detailing processes related to volunteers. Team to discuss issues like Volunteer retention, feedback, recruitment, training and recognition. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Adnan Iqbal, Junaid Tahir (Team Leads) Hasan Karahan | Team Leads have been identified and briefed of our requirements. Tarim, Naima and Mehreen to provide support to them as they initiate the process and on an ongoing basis. To add tech support (volunteers) to the team. | Ongoing
| Volunteer Manager (VM) position | To hire a new full time VM |  | 2 candidates have been shortlisted so far. | 2011-06-01
| Partnerships Development | To develop relationships with instituitions/organizations as volunteer & funding partners to increase visibility and out reach | Nabeel Ahmed/Usman Hassan | Hadia Raheel is interested in taking this up in Toronto, Nabeel Ahmed will meet with her to determine suitability/capability. We need volunteers engaged in this initiative in multiple cities. | Ongoing