## Cover
Association for the Development of Pakistan
Monthly Report
2011-07-01

## Proposals
Association for the Development of Pakistan | [8 empty] | July 2011
New Proposals
Approved from screening
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Project approved. Team to be staffed - on hold because several water and sanitation projects are already being evaluated. | 2011-03-03 | Naima Hasan | Mid May 2011
| WAFA | Welfare Awareness & Facilitation Association | 9345 | Rehabilitation of flood affected schools | Nowshera | Checklist complete. Decision to be made by Mubarik and Mehreen. | 2011-04-20 | Mehreen Siddiqi | 2011-08-11
| RDO | Rural Development Organization | 11543 | Upgrade/extension of existing medical center | Faisalabad | Checklist complete. Decision to be made on next screening call. | 2011-05-14 | Haleema Raheel/ Mehreen Siddiqi | 2011-08-11
| FIDA | Foundation for Integrated Development Action | 11761 | Setting up bio-gas plants | D.I.Khan | Pending screening. | 2011-05-16 | Khurram Jamali | 2011-08-11
| YDO | Youth Development Organization | 11764 | Water suuply scheme (Installation of hand-pumps) | Rajanpur, Punjab | Checklist complete. Decision to be made after some more research is done. | 2011-05-18 | Dawood Ahmed | 2011-08-11
| MBB | Muhammadi Blood Bank | 11764 | Equipment for Thalassemia center | Karachi | Rejected. Concerns with regards to NGO's plans to run the Center. Also, MBB not willing to send over financials. | 2011-05-26 | Jazib Zahir | 2011-07-01
| MHSF | M.H. Sufi Foundation | 11764 | Expansion of School - Kaseese Branch | Hafizabad | Approved. Team to be staffed. | 2011-05-26 | Naima Hasan | 2011-07-01
| WCDO | Women and Children Development Organization | 11552 | Installation of hand-pumps | Charsadda | Checklist complete. Decision to be made by Mubarik and Hasham. Probability of getting rejected. | 2011-06-06 | Hasham Mehmood | 2011-08-11
| SADDA | SADDA Welfare and Development Organization | 11647 | School improvement Program | Tehsil Dargai, Malakand | Checklist complete. Decision to be made by Asad and Mubarik. | 2011-06-06 | Asad Mawjee | 2011-08-11
| SHATAC | Shehri Ijtamai Taraqiati Council | 11764 | Incineration plant at a Hospital | Mandi Bahauddin | To be assigned to screener. | 2011-07-03
| HDO | Humdard Development Organization | 11529 | Installation of hand-pumps | Charsadda | Pending screening. | 2011-06-10 | Mehreen Siddiqi | 2011-08-11
| ART | A.R.T. ( Access, Research, Training) Foundation | 8678 | Upgrade of a medical center | Lahore | Pending screening. | 2011-06-08 | Naima Hasan | 2011-08-11
| UYWO | United youth welfare organization | 11470 | Strengthening the Health Monitoring system (Basic Health Units) | Charsadda | Pending screening. | 2011-06-13 | Jazib Zahir | 2011-08-11
| ABKT | Association for Behavior & Knowledge Transformation | 11720 | Construction of latrines | Charsadda | Pending screening. | 2011-06-22 | Naima Hasan | 2011-08-11
| MWO | Memona Welfare Organization | 10837 | Construction of a health center | Bahawalpur | To be assigned to screener. | 2011-07-22
| OHRA | Organization for Human Resources Allocation (recommended by Mr. Mubashir at HEED) | 11759 | Water supply scheme | Nathiagali | Pending screening. | 2011-07-27 | Umbreen Tapal | 2011-08-11
|  | Current Month | Previous Month
| Early Stage | 13 | 14
| Approved | 1 | 2
| Rejected | 1 | 1
| On hold | 1 | 0
| Total | 16 | 17

## Under Review
Association for the Development of Pakistan | [11 empty] | July 2011
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| APS | Arshad Public School | AJK | 11619 | Water supply project-installation of water tanks, pipes etc to provide the school with access to clean water | Uzaib Saya, Habiya Beg, Mariam Haqqie | Mubarik Imam, Dawood Ahmed | Project approved. ADP to partner with HEED to construct water pipeline for the school. HEED to submit project proposal within Aug., 2011 | 2010-06-15 | 2011-07-11 | End
| CCFP | Child Care Foundation of Pakistan | Nankana; Sheikhupura | 11765 | Setting up computer labs in 3 existing schools | Nabeel Hasnain, Minza Zahid, Arsalan Mushtaq | Akbar Bhaidani, Hasham Mehmood | Site visit to be conducted on Aug. 17, 2011. Team to reach a decision after the site visit report is received. | 2010-12-20 | 2011-08-11 | End
| CAP | Community Advance Program | Lahore | 7859 | Computers and furniture for existing schools | Jawad Hasan, Meher Makda, Mahira Kalim | Natasha Qureshi, Qasim Ashraf | Approved. Project undergoing legal screening. Meanwhile, the team is in the process of drafting the contract. | 2011-01-29 | 2011-07-11 | End
| KRT | Karachi Relief Trust | Sujawal District, Sindh | 14705 | Reconstruction of homes for flood victims | Adeel Qaiser, Hadia Raheel, Alexis Saba | Shahan Zafar, Jazib Zahir | Rejected. KRT got funding from elsewhere and constructed the houses. | 2011-02-17 | 2011-07-11 | End
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Adnan Pathan, Adeel Naeem, Taha Mashhadi | Waleed Saraf, Dawood Ahmed | Team very supportive of project. Final decision to be based on site visit report. Team to have a final call on Aug. 14, 2011 | 2011-02-01 | 2011-08-11 | End
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 11764 | Mishtimba Village family latrines | Danish Iqbal, Abdullah Hasan, Habiya Beg | Tarim Wasim, Nabeel Hasnain | On hold until HEED figures out post project issues that have arisen in the Sokar project. | 2011-04-09 |  | Early
| SS | Sudhaar Society | Kasur | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Farzal Dhojki, Babar Khan, Muzammal Ashraf | Rameez Dossa, Ahmed Makani | Site visit has been conducted. Team to make a decision based on site visit report. | 2011-03-25 | Aug/Sep-11 | Mid
| HEED(edu) | Health Education Environment Development Association | Neelum Valley, AK | 16470 | Rehabilitation of flood affected schools | Danish Iqbal, Naveed Alam, Alizay Saeed | Tarim Wasim, Jazib Zahir | Early stage of evaluation. Project kick off call held on July 17, 2011. | 2011-04-17 | 2011-10-11 | Early
| LS | Lifeline Society | Near Multan and Muzaffargarh | 10235 | Water Supply Scheme (Installation of hand pumps) | Saman Nizami, Maryam Jillani, Shiza Shahid | Mubarik Imam, Asad Mawjee | Early stage of evaluation. Project kick off call held on July 23, 2011. | 2011-03-25 | 2011-10-11 | Early
| YRC | Youth Resource Center | Nowshera | 11764 | Water Supply Scheme (Installation of hand-pumps) | Saba Gul, Ali Taufeeq, Kamran Ali | Waleed Saraf, Mehreen Siddiqi | Early stage of evaluation. Project kick off call held on Aug. 7, 2011 | 2011-03-17 | 2011-10-11 | Early
| SIDO | Social Integrated Development Organization | Charsadda | 10674 | Water Supply Scheme (Installation of hand pumps) | Mughees Butt, Talal Butt, Hadia Raheel, Ruqaiya Ramzan | Mehreen Siddiqi, Qasim Ashraf | Project kick off call scheduled for Aug. 14, 2011 | 2011-03-30 | 2011-10-11 | Early
|  | Current Month | Previous Month
| Early Stage Diligence | 5
| Mid-Stage Diligence | 1
| Final Stage Diligence | 4
| Rejected | 1
| Total | 11 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | July 2011
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Kharo Chann | Action for Humanitarian Development | Thatta | 4250 | School for remote fishing village communities | 2009-05-01 | TBC | 3644 | 606 | Mr. Yaseen to confirm further funding needs | Y | Third tranche of funding (Rs. 81,000) disbursed on June 17th, 2010. School is operational with 74 students enrolled currently. Enrollment has gone down because people migrated in anticipation of the floods and because families are not keen on sending older girls to school. School might need remaining amount for maintenance and repair (no response from Mr. Yaseen yet). School also applying for govt. funds .
| Al-Qasim | Al Qasim Foundation | District Khushab | 8841 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 8841 | 0 | End of Phase IV (Sep.-Oct. 2011) | N | Phase III (construction of 5 plants) completed in May, 2011. AQF submitted pictures, list of beneficiaries and copies of agreements executed between AQF and landlords. Last tranche of $2,330 released on July 15, 2011. Once construction of the last 4 bio-gas plants is complete, a site visit will be conducted to verify the construction and functioning of all plants.
| CCF | Children Cancer Foundation Pakistan | Karachi | 7058 | To establish pediatric ICU for infection control in a Cancer Hospital in Karachi | 2010-04-20 | TBC | 6854 | 0 | N/A | N | First Equipment Utilization Report submitted in Aug. 2010. Second Equipment Utilization Report submitted in Apr. 2011. Third and last Report submitted in Aug. 2011. Reports reveal utilization of equipment of an average of over 70%. Project completed successfully.
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Aug. 2010 | TBC | 4957 | 0 | N/A | N | Site visit conducted by Imad Rashid in Feb., 2011. According to the site visit report, 3 pumps are functioning fine whereas one is pumping muddy water which is being used for feeding animals. Project team has decided to cancel the project. MGPO has sent over a report with relation to the existing 4 pumps and will return the remaining amount which was not used for the 5th pump to ADP.
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 11308 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Latrines in total) | Oct. 2010 | TBC | 11308 | 0 | Report C (1 year after completion of project) | N | Project has come to an end with construction of all latrines complete. HEED held its last Hygiene Promotion session in early Apr., 2011. Report B submitted. Certain issues were identified by HEED when it conducted its 3 month post project completion survey and these have been highligted in the Report. HEED has stayed in touch with ADP and has been taking steps to rectify the situation. A revised Report B has been submitted to ADP.
| NEEDS (flood relief) | Network for Education and Economic Development Services | Charsadda | 5000 | Installation of handpumps to provide clean drinking water | Sep./Oct. 2010 | TBC | 5000 | 0 | N/A | N | Project has come to an end with all 12 hand-pumps constructed and functioning well. Project Completion Report has been received. Potential site visit to be arranged to confirm NEEDS update.
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School in Katch area | Jan. 2011 | TBC | 4705 | 4705 | Report on completion of Phase I (Aug. 2011) | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. Phase I: (i) Construction of computer lab is complete. (ii) Electrical work has been completed. (iii) Furniture and air conditioner for lab have been purchased. (iv) Installation of windows and door is in progress. (v) Newly hired computer teacher has been trained - training was supposed to end by Aug. 10, 2011. (vi) Watchman has been identified. Lesson plans being developed by the computer teacher will be sent to ADP by Aug. 15, 2011.
| Amir Public School | Nia Ujala | Gujranawala | 7032 | Development of a school in Gujranwala (setting up of classrooms) | Jan. 2011 | TBC | 6106 | 926 | Report A to be submitted when classroom becomes functional | Y | ADP wired first tranche of $2,706 to APS in late Jan., 2011 and then second tranche of $2,800 in Mar., 2011. Third tranche of $600 received by APS in June, 2011. Room construction and furnishing complete. APS has sent over pictures of children in the classroom. Teacher training has been completed successfully with great feedback from all participants. APS sent over photographs of the Training as well as the Instructor's Training Schedule and his Recommendations.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 2600 | 5753 | Mr. Humayun to inform ADP when women have been registered and hens are to be purchased | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. 16 loans (ranging from Rs. 2000 - Rs. 5000) were disbursed in the 2nd week of July. Chickens to start laying eggs in 2.5 months from then. NEEDS is planning to disburse more loans during Ramadan. Due to instability in the availability and the fluctuating prices of chickens, NEEDS wants to introduce some other options into the project - loans for other small but viable businesses. ADP to discuss further options with NEEDS and make a decision.
| SDO | Saibaan Development Organization | Mansehra | 7294 | Setting up of a water filtration plant | Jul. 2011 | TBC | 0 | 7294 | SDO to inform ADP when preliminary requirements have been met | Y | SDO to send executed landlord agreement and finish the boring process in order to find an adequate water supply. The boring process could not be started because of heavy rains but in the mean time, SDO has been holding meetings for Water User Committees and has also met with an Islamabad based organization that has experience in the installation of water filtration plants. SDO has also held Awareness Sessions in different communities to inform them of the construction of the plant and to emphasize the importance of Health and Hygiene. Funds will be disbursed once the above mentioned requirements have been met.
| Projects In Progress | 10
| Remaining Funding | 19284

## Volunteers
Association for the Development of Pakistan | [9 empty] | July 2011
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 6 | 3 | 2 |  | 0 | 0 | 0 | 6 PECs are staffed presently. Saad and Natasha can potentially take on new projects. Mehreen has also taken on a project as PEC.
| Evaluation Committee | 7 | 3 | 2 |  | 0 | 3 | 1 | 7 ECs are staffed. Khurram Jamali and Minhaj Patel have capacity to take on a project each. Syeda Masood was added to the EC pool this month. Owais Rafiq and Uzaib Saya need to be trained as ECs since they were recommended to be moved up to the EC pool.
| Project Team Leads | 7 | 3 | 3 |  | 0 | 1 | 0 | 7 PTLs are staffed on projects right now. Ahmad Chaudhary, Najaf Ali, and Owais Rafiq can potentially be staffed on new projects. Ali Taufeeq will be added to the PTL pool after he has been trained this weekend. A new volunteer Bilal Noor may also be added to the PTL group - to be decided after talking to him.
| Project Team | 16 | 6 | 10 |  |  | 8 | 8 | 3 new projects were staffed in July (Lifeline, YRC and SIDO). 1 project is up for staffing right now. Around 2 - 3 projects are still pending decisions so they will be staffed accordingly. There have been a lot of new sign ups but not too many have bee trained as many new volunteers have been waiting to be staffed on projects.
| Site Visits | 3 | 2 | 7 |  |  | 2 | 2 | Site Visits for SFL and Sudhaar were conducted this month. SFL will have a decision this weekend and the Sudhaar team will be deciding on next steps based on the visit. Ali Raza will be conducting the visit for the CCFP project. New volunteers have been found in the Multan and AJK area where we had previously faced some problems in locating good quality volunteers. We now have a number of good quality site visit volunteers. Visit for the HEED project may be next
| Sourcing | 3 | 0 | 0 |  |  | 0 | 0 | Sourcing has been a little slow since we need to make decisions on several pending projects. Pace will be renewed in August.
| Fundraising | 8 | 2 | 3 |  |  | 0 | 0 | Omar Bilal and Shahan Zafar presented to a small group of interested volunteers in NUS, Singapore. I will be contacting those volunteers and following up with getting them on board. The plan is to set up a chapter once there are enough volunteers. There are about 15 right now who have shown interest.
| Media | 4 | 0 | 0 |  |  | 1 | 0 | Ayesha Shahid, Natalia Bokhari, Sanaa Qureshi,Vajiha Sipra & Nabeel Ahmed are actively involved. Shemrez Khan is a new volunteer who is interested in coming on board for social media and I will be connecting him with Nabeel.
| Web team | 2 | 4 | 3 |  |  | 2 | 0 | Need a volunteer for salesforce. Karim Jindani, Sibtain Jawed, Ali Shahid are all interested in coming on board for the tech team but need feedback on them for the next steps. Resumes have been sent for review.
| Legal | 3 | 1 | 0 |  | 0 | 0 | 0 | Ongoing work on registering ADP in Pakistan.
| Marketing | 2 | 4 | 4 |  |  | 0 | 0 | Najia Khan and Saman Malik will be taking up the lead roles for the marketing team acting as co - coordinators. Nabeel and Usman will be discussing marketing strategy with them. Hadia Raheel is looking after the partnerships development role.
| Other | 3 | 2 | 0 |  | 0 | 2 | 2 | Adnan Iqbal, Junaid Tahir and Hasan Karahan have joined as part of the KMS team. Hasan Riaz may also be coming on board for this as well as Madeeha Ansari (for the content part).
| Total | 64 | 30 | 34 |  | 0 | 19 | 13
| Total signups | 15
| New projects launched | 3
| New projects expected | 3 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed on projects
Tech/Fundraising teams need new members
Initiatives:
Upcoming volunteer activities are being posted on the 'current opportunities' page on the website
Recruitment for the new VM is underway. 2 candidates are in the third phase of the process
VM User Manual is being compiled to ensure maximum information is available to the new VM
Information for all active volunteers has been consolidated on one google spreadsheet

## Initiatives
Association for the Development of Pakistan |  |  |  |  | July 2011
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Mubarik Imam | Moved to a new lawyer who is in the process of building a rapport with the Registrar. Lawyer has sent over a list of documents that need to be sent to her before she can file for registration - in process. | NA
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz; Vajiha Sipra | Constantly updating projects pages on the website. Next issue of Dastak to go out on Aug. 14, 2011 | Ongoing
| Volunteer Review | Group to review ADP's Volunteer Management Processes (recruiting, orientation, screening, training, staffing, feedback) with the aim of improving them. | Naima Hasan; Mehreen Siddiqi; Tarim Wasim; Mubarik Imam | Naima to draft a document detailing processes related to volunteers. Team to discuss issues like Volunteer retention, feedback, recruitment, training and recognition. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Adnan Iqbal, Junaid Tahir (Team Leads) Hasan Karahan | Team Leads have been identified and briefed of our requirements. Tarim, Naima and Mehreen to provide support to them as they initiate the process and on an ongoing basis. To add tech support (volunteers) to the team. | Ongoing
| Volunteer Manager (VM) position | To hire a new full time VM |  | 3 candidates have been shortlisted so far. | Ongoing
| Partnerships Development | To develop relationships with instituitions/organizations as volunteer & funding partners to increase visibility and out reach | Nabeel Ahmed/Usman Hassan | Hadia Raheel is interested in taking this up in Toronto, Nabeel Ahmed will meet with her to determine suitability/capability. We need volunteers engaged in this initiative in multiple cities. | Ongoing