## Cover
Association for the Development of Pakistan
Monthly Report
2011-08-01

## Proposals
Association for the Development of Pakistan | [8 empty] | August 2011
New Proposals
Approved from screening
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Project approved. Team to be staffed - on hold because several water and sanitation projects are already being evaluated. | 2011-03-03 | Naima Hasan | Mid May 2011
| WAFA | Welfare Awareness & Facilitation Association | 9345 | Rehabilitation of flood affected school | Nowshera | Rejected. School was functional - concerns around critical need and WAFA's ability to execute the project. | 2011-04-20 | Mehreen Siddiqi | 2011-08-11
| RDO | Rural Development Organization | 11543 | Upgrade/extension of existing medical center | Faisalabad | Approved. Team to be staffed. | 2011-05-14 | Haleema Raheel/ Mehreen Siddiqi | 2011-09-11
| FIDA | Foundation for Integrated Development Action | 11761 | Setting up bio-gas plants | D.I.Khan | Approved. Team to be staffed. | 2011-05-16 | Khurram Jamali | 2011-09-11
| YDO | Youth Development Organization | 11764 | Water suuply scheme (Installation of hand-pumps) | Rajanpur, Punjab | Approved. Team to be staffed. | 2011-05-18 | Dawood Ahmed | 2011-08-11
| WCDO | Women and Children Development Organization | 11552 | Installation of hand-pumps | Charsadda | Rejected. WCDO does not have a good reputation of having executed successful projects in the past. | 2011-06-06 | Hasham Mehmood | 2011-08-11
| SADDA | SADDA Welfare and Development Organization | 11647 | School improvement Program | Tehsil Dargai, Malakand | Checklist complete. Mubarik to share concerns with Naima and Mehreen. | 2011-06-06 | Asad Mawjee | 2011-09-11
| SHATAC | Shehri Ijtamai Taraqiati Council | 11764 | Incineration plant at a Hospital | Mandi Bahauddin | Pending screening. | 2011-07-03 | Naima Hasan | 2011-09-11
| HDO | Humdard Development Organization | 11529 | Installation of hand-pumps | Charsadda | Pending screening. | 2011-06-10 | Mehreen Siddiqi | 2011-09-11
| ART | A.R.T. ( Access, Research, Training) Foundation | 8678 | Upgrade of a medical center | Lahore | Rejected. Concerns with regards to measurability. | 2011-06-08 | Naima Hasan | 2011-09-11
| UYWO | United youth welfare organization | 11470 | Strengthening the Health Monitoring system (Basic Health Units) | Charsadda | Rejected. Concerns with regards to measurability. | 2011-06-13 | Jazib Zahir | 2011-08-11
| ABKT | Association for Behavior & Knowledge Transformation | 11720 | Construction of latrines | Charsadda | Discussed on August's screening call. More research to be done before decision is made. | 2011-06-22 | Naima Hasan | 2011-08-11
| MWO | Memona Welfare Organization | 10837 | Construction of a health center | Bahawalpur | Pending screening. | 2011-07-22 | Khurram Jamali | 2011-09-11
| OHRA | Organization for Human Resources Allocation (recommended by Mr. Mubashir at HEED) | 11759 | Water supply scheme | Nathiagali | Discussed on August's screening call. More research to be done before decision is made. | 2011-07-27 | Umbreen Tapal | 2011-08-11
| RF | Roshni Foundation | 11741 | Roshni Model Primary School Project | Chinglai, Swabi | Pending screening. | 2011-08-22 | Dawood Ahmed | 2011-09-11
|  | Current Month | Previous Month
| Early Stage | 7 | 13
| Approved | 3 | 1
| Rejected | 4 | 1
| On hold | 1 | 1
| Total | 15 | 16

## Under Review
Association for the Development of Pakistan | [11 empty] | August 2011
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| APS | Arshad Public School | AJK | 11619 | Water supply project-installation of water tanks, pipes etc to provide the school with access to clean water | Uzaib Saya, Habiya Beg, Mariam Haqqie | Mubarik Imam, Dawood Ahmed | Project approved. ADP to partner with HEED to construct water pipeline for the school. Due diligence being conducted on HEED's proposal. | 2010-06-15 | 2011-09-11 | End
| CCFP | Child Care Foundation of Pakistan | Nankana; Sheikhupura | 11765 | Setting up computer labs in 3 existing schools | Nabeel Hasnain, Minza Zahid, Arsalan Mushtaq | Akbar Bhaidani, Hasham Mehmood | Rejected. Concerns with regards to the need for computer labs in the area. | 2010-12-20 | 2011-08-11 | End
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Adnan Pathan, Adeel Naeem, Taha Mashhadi | Waleed Saraf, Dawood Ahmed | Approved. Project in execution stage. | 2011-02-01 | 2011-08-11 | End
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 11764 | Mishtimba Village family latrines | Danish Iqbal, Abdullah Hasan, Habiya Beg | Tarim Wasim, Nabeel Hasnain | Mid stage of evaluation. Site visit to be conducted soon. | 2011-04-09 | Oct./Nov. 2011 | Mid
| SS | Sudhaar Society | Kasur | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Farzal Dhojki, Babar Khan, Muzammal Ashraf | Rameez Dossa, Ahmed Makani | Site visit has been conducted. Team to make a decision based on site visit report. Next team call scheduled for Sep. 11, 2011. | 2011-03-25 | Aug/Sep-11 | End
| HEED(edu) | Health Education Environment Development Association | Neelum Valley, AK | 16470 | Rehabilitation of flood affected schools | Danish Iqbal, Naveed Alam, Alizay Saeed | Tarim Wasim, Jazib Zahir | Mid stage of evaluation. | 2011-04-17 | Oct./Nov. 2011 | Mid
| LS | Lifeline Society | Near Multan and Muzaffargarh | 10235 | Water Supply Scheme (Installation of hand pumps) | Saman Nizami, Maryam Jillani, Shiza Shahid | Mubarik Imam, Asad Mawjee | Mid stage of evaluation. | 2011-03-25 | Oct./Nov. 2011 | Mid
| YRC | Youth Resource Center | Nowshera | 11764 | Water Supply Scheme (Installation of hand-pumps) | Saba Gul, Ali Taufeeq, Kamran Ali | Waleed Saraf, Mehreen Siddiqi | Mid stage of evaluation. Next project team call on Sep. 11, 2011. Site visit to be conducted soon. | 2011-03-17 | 2011-10-11 | Mid
| SIDO | Social Integrated Development Organization | Charsadda | 10674 | Water Supply Scheme (Installation of hand pumps) | Mughees Butt, Talal Butt, Hadia Raheel, Ruqaiya Ramzan | Mehreen Siddiqi, Qasim Ashraf | Mid stage of evaluation. Site visit to be conducted soon. | 2011-03-30 | 2011-10-11 | Mid
| MHSF | M.H. Sufi Foundation | Hafizabad | 11764 | Expansion of School - Kaseese Branch | Adeel Qaiser, Imran Siddiqui, Alexis Saba | Tarim, Wasim, Syeda Quratulain Masood | Project in mid stage of evaluation. Sitel visit to be conducted soon | 2011-05-26 | 2011-07-01 | Mid
|  | Current Month | Previous Month
| Early Stage Diligence | 0
| Mid-Stage Diligence | 6
| Final Stage Diligence | 3
| Rejected | 1
| Total | 10 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | August 2011
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Al-Qasim | Al Qasim Foundation | District Khushab | 8841 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 8841 | 0 | End of 2011 (completion of project) | N | Last tranche of $2,330 released on July 15, 2011. Once construction of the last 4 bio-gas plants is complete, a site visit will be conducted to verify the construction and functioning of all plants.
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Aug. 2010 | Summer 2011 | 4957 | 0 | N/A | N | Site visit conducted by Imad Rashid in Feb., 2011. According to the site visit report, 3 pumps are functioning fine whereas one is pumping muddy water which is being used for feeding animals. Project team has decided to cancel the project. MGPO has sent over a report with relation to the existing 4 pumps and will return the remaining amount which was not used for the 5th pump to ADP. Mehreen to send Authority Letter to MGPO so funds can be transferred.
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 11308 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Latrines in total) | Oct. 2010 | TBC | 11308 | 0 | Report C (1 year after completion of project) | N | Project has come to an end with construction of all latrines complete. HEED held its last Hygiene Promotion session in early Apr., 2011. Report B submitted. Issues identified by HEED in its 3 month post project completion survey are being dealth with. A revised Report B has been submitted to ADP.
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School in Katch area | Jan. 2011 | TBC | 4705 | 4705 | Report on completion of Phase I (Aug. 2011) | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. Phase I: (i) Construction of computer lab is complete. (ii) Electrical work has been completed. (iii) Furniture and air conditioner for lab have been purchased. (iv) Installation of windows and door is in progress. (v) Newly hired computer teacher has been trained - training was supposed to end by Aug. 10, 2011. (vi) Watchman has been identified. Earlier, Lesson plans being developed by the computer teacher were tol be sent to ADP by Aug. 15, 2011. After a lot of follow up, SWS has responded by saying that they will now submit the above documents by mid-September.
| Amir Public School | Nia Ujala | Gujranawala | 7032 | Development of a school in Gujranwala (setting up of classrooms) | Jan. 2011 | TBC | 6106 | 926 | Report A to be submitted when classroom becomes functional | Y | ADP wired first tranche of $2,706 to APS in late Jan., 2011 and then second tranche of $2,800 in Mar., 2011. Third tranche of $600 received by APS in June, 2011. Room construction and furnishing complete. APS has sent over pictures of children in the classroom. Teacher training has been completed successfully with great feedback from all participants. APS sent over photographs of the Training as well as the Instructor's Training Schedule and his Recommendations.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 2600 | 5753 |  | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. 16 loans (ranging from Rs. 2000 - Rs. 5000) were disbursed in the 2nd week of July. Chickens to start laying eggs in 2.5 months from then. NEEDS is planning to disburse more loans during Ramadan. Due to instability in the availability and the fluctuating prices of chickens, NEEDS wants to introduce some other options into the project - loans for other small but viable businesses. ADP to discuss further options with NEEDS and make a decision.
| SDO | Saibaan Development Organization | Mansehra | 8823 | Setting up of a water filtration plant | Jul. 2011 | TBC | 0 | 8823 | SDO to inform ADP when preliminary requirements have been met | Y | SDO to send executed landlord agreement and finish the boring process in order to find an adequate water supply. The boring process could not be started because of heavy rains but in the mean time, SDO has been holding meetings for Water User Committees and has also met with an Islamabad based organization that has experience in the installation of water filtration plants. SDO has also held Awareness Sessions in different communities to inform them of the construction of the plant and to emphasize the importance of Health and Hygiene. Funds will be disbursed once the above mentioned requirements have been met (expected time frame: Oct. 2011).
| CAP | Community Advance Program | Lahore | 8717 | Computers and furniture for existing schools | Oct.2011 | TBC | 0 | 8717 | Submission of Project Metrics Form on completion of Phase I | Y | Contract has been finalized and signed by CAP. ADP to raise funds for the project and disburse 1st tranche in early Oct. 2011.
| Projects In Progress | 7
| Remaining Funding | 28924

## Volunteers
Association for the Development of Pakistan | [9 empty] | August 2011
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 5 | 4 | 3 |  | 0 | 0 | 0 | 5 PECs are staffed presently. Saad, Natasha and Shahan can potentially take on new projects. Khurram Jamali will be starting his first project as PEC this month.
| Evaluation Committee | 7 | 0 | 0 |  | 0 | 0 | 0 | 7 ECs are staffed on projects currently. The Ec structure has been changed to only have PECs on projects. Existing ECs will either be groomed to take on the PEC role or remain as part of the PTL pool until they are ready to be PECs. Those with weak past records will be observed on their current projects and kept as PTLs on future projects or rotated out.
| Project Team Leads | 6 | 4 | 3 |  | 0 | 3 | 1 | 6 PTLs are staffed on projects right now. Ahmad Chaudary, Najaf Ali, Tehniyat Kardar and Owais Rafiq can potentially be staffed on new projects. Ali Taufeeq has been trained as a PTL. Bilal Noor and Sabah Khan will be trained as PTLs next week. Tehniyat will probably be staffed as a PT member since she has been out of touch for nearly a year and is not familiar with new processes.
| Project Team | 15 | 8 | 9 |  | 12 | 7 | 5 | 2 new projects were staffed in August (MH.Sufi and SIDO). Around 2-3 projects are up for staffing right now and will have their kick offs this month. There are a number of new volunteers waiting to be staffed right now and will be put on the upcoming projects.
| Site Visits | 3 | 5 | 8 |  | 10 | 5 | 2 | Site Visits for MH Sufi, NEEDS, both HEED projects are to be conducted in the month of September. There are a number of volunteers available for this and it will be finalized by next week. Visits for the Sudhaar and CCFP projects were done last month.
| Sourcing | 2 | 0 | 0 |  | 7 | 0 | 0 | Projects with more established NGOs with relevant past experience are being focused on right now since there is a greater probablility of approval of a project if the NGO has prior experience in a sector.
| Fundraising | 8 |  |  |  | 4 | 0 | 0 | The fundraising team will be raising the funds for the recently approved projects (SDO, CAP)
| Media | 4 | 0 | 0 |  | 5 | 1 | 0 | Ayesha Shahid, Natalia Bokhari, Sanaa Qureshi,Vajiha Sipra & Nabeel Ahmed are actively involved. Shemrez Khan is a new volunteer who is interested in coming on board for social media, Nabeel has connected with him and they will be talking about his involvement.
| Web team | 2 |  |  |  | 4 |  | 0
| Legal | 3 | 1 | 0 |  | 0 | 0 | 0 | on going work on registering ADP in Pakistan. Dawood Ahmed who is currently an EC may be moved on to the legal team.
| Marketing | 2 | 4 | 4 |  |  | 0 | 0 | Najia Khan and Saman Malik will be taking up the lead roles for the marketing team acting as co - coordinators. Hadia Raheel is looking after the partnerships development role.
| Other | 3 | 8 | 5 |  | 0 |  |  | Adnan Iqbal, Junaid Tahir and Hasan Karahan have joined as part of the KMS team. Hasan Riaz may also be coming on board for this as well as Madeeha Ansari (for the content part). The search for new volunteers that will help populate the KMS is underway, PECs will be sent volunteers that will be researching their assigned sector.
| Total | 60 | 34 | 32 |  | 42 | 16 | 8
| Total signups | 22
| New projects launched | 2
| New projects expected | 4 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed on projects
KMS volunteers needed to populate the database
Initiatives:
KMS volunteers are being recruited
Recruiment for the new VM is underway
Site visit volunteers are being staffed and briefed

## Initiatives
Association for the Development of Pakistan |  |  |  |  | August 2011
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Mubarik Imam | Moved to a new lawyer who is in the process of building a rapport with the Registrar. Lawyer has sent over a list of documents that need to be sent to her before she can file for registration - in process. | NA
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz; Vajiha Sipra | Constantly updating projects pages on the website. Last issue of Dastak went out on Aug. 14, 2011 | Ongoing
| Volunteer Review | Group to review ADP's Volunteer Management Processes (recruiting, orientation, screening, training, staffing, feedback) with the aim of improving them. | Naima Hasan; Mehreen Siddiqi; Tarim Wasim; Mubarik Imam | Naima to draft a document detailing processes related to volunteers. Team to discuss issues like Volunteer retention, feedback, recruitment, training and recognition. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Adnan Iqbal, Junaid Tahir (Team Leads) Hasan Karahan | Team Leads have been identified and briefed of our requirements. Tarim, Naima and Mehreen to provide support to them as they initiate the process and on an ongoing basis. To add tech support (volunteers) to the team. | Ongoing
| Volunteer Manager (VM) position | To hire a new full time VM |  | Need to discuss strategy going forward. | Ongoing
| Partnerships Development | To develop relationships with instituitions/organizations as volunteer & funding partners to increase visibility and out reach | Nabeel Ahmed/Usman Hassan | Hadia Raheel is interested in taking this up in Toronto, Nabeel Ahmed will meet with her to determine suitability/capability. We need volunteers engaged in this initiative in multiple cities. | Ongoing