## Cover
Association for the Development of Pakistan
Monthly Report
2011-09-11

## Proposals
Association for the Development of Pakistan | [8 empty] | September 2011
New Proposals
Approved from screening
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Project approved. Team to be staffed - on hold because several water and sanitation projects are already being evaluated. | 2011-03-03 | Naima Hasan | Mid May 2011
| YDO | Youth Development Organization | 11764 | Water suuply scheme (Installation of hand-pumps) | Rajanpur, Punjab | Approved. Team to be staffed. | 2011-05-18 | Dawood Ahmed | 2011-08-11
| SADDA | SADDA Welfare and Development Organization | 11647 | School improvement Program | Tehsil Dargai, Malakand | Rejected. Though the NGO has been involved in the education sector, it does not have experience undertaking similar projects in the past. Additionally, there were concerns around measurability. | 2011-06-06 | Asad Mawjee | 2011-09-11
| SHATAC | Shehri Ijtamai Taraqiati Council | 11764 | Incineration plant at a Hospital | Mandi Bahauddin | Pending screening. | 2011-07-03 | Naima Hasan | 2011-10-11
| HDO | Humdard Development Organization | 11529 | Installation of hand-pumps | Charsadda | Rejected. NGO's annual revenues are much lower than the funding amount requested. Also, ADP would prefer to limit the amount of proposals from within the same target area. | 2011-06-10 | Mehreen Siddiqi | 2011-09-11
| ABKT | Association for Behavior & Knowledge Transformation | 11720 | Construction of latrines | Charsadda | Checklist complete. Decision to be made. | 2011-06-22 | Naima Hasan | 2011-10-11
| MWO | Memona Welfare Organization | 10837 | Construction of a health center | Bahawalpur | Pending screening. | 2011-07-22 | Ahmed Makani | 2011-10-11
| OHRA | Organization for Human Resources Allocation (recommended by Mr. Mubashir at HEED) | 11759 | Water supply scheme | Nathiagali | Approved. Team to be staffed. | 2011-07-27 | Umbreen Tapal | 2011-09-11
| RF | Roshni Foundation | 11741 | Roshni Model Primary School Project | Chinglai, Swabi | Pending screening. | 2011-08-22 | Dawood Ahmed | 2011-10-11
| YMS | Young Man Society | 10882 | Rehabilitation of water supply system | Rahim Yar Khan | Pending screening. | 2011-09-06 | Mehreen Siddiqi | 2011-10-11
| QSET | Qurban and Surraya Educational Trust | 11647 | Computer lab for existing school | Lahore | Pending screening. | 2011-09-13 | Qasim Ashraf | 2011-10-11
| AWHES | Aman Welfare Health and Education Society | 11776 | Upgrade of existing medical center | Muzaffarabad | Pending screening. | 2011-09-18 | Bilal Hussain | 2011-10-11
| SOS | SOS Children's Village | 11764 | Construction of classrooms in existing school | Kasur | Pending screening. | 2011-09-19 | Hasham Mehmood | 2011-10-11
| AHMMT | Ali Hasan Mangi Memorial Trust | 10250 | Low cost housing scheme | Larkana | Pending screening. | 2011-09-19 | Jawad Hasan | 2011-10-11
| SRS | Sindhica Reforms Society | 11536 | Construction of latrines | District Shaheed Benazirabad, Sindh | To be assigned to screener. | 2011-09-26
|  | Current Month | Previous Month
| Early Stage | 10 | 7
| Approved | 2 | 3
| Rejected | 2 | 4
| On hold | 1 | 1
| Total | 15 | 15

## Under Review
Association for the Development of Pakistan | [11 empty] | September 2011
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| APS | Arshad Public School | AJK | 11619 | Water supply project-installation of water tanks, pipes etc to provide the school with access to clean water | Uzaib Saya, Habiya Beg, Mariam Haqqie | Mubarik Imam, Dawood Ahmed | ADP to partner with HEED to construct water pipeline for the school. Due diligence being conducted on HEED's proposal. | 2010-06-15 | 2011-10-11 | End
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 11764 | Mishtimba Village family latrines | Danish Iqbal, Abdullah Hasan, Habiya Beg | Tarim Wasim, Nabeel Hasnain | Mid stage of evaluation. Site visit to be conducted soon. | 2011-04-09 | Oct./Nov. 2011 | Mid
| SS | Sudhaar Society | Kasur | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Farzal Dhojki, Babar Khan, Muzammal Ashraf | Rameez Dossa, Ahmed Makani | Site visit has been conducted. Team is in the process of making a decision. | 2011-03-25 | 2011-10-11 | End
| HEED(edu) | Health Education Environment Development Association | Neelum Valley, AK | 16470 | Rehabilitation of flood affected schools | Danish Iqbal, Naveed Alam, Alizay Saeed | Tarim Wasim, Jazib Zahir | Mid stage of evaluation. | 2011-04-17 | Oct./Nov.2011 | Mid
| LS | Lifeline Society | Near Multan and Muzaffargarh | 10235 | Water Supply Scheme (Installation of hand pumps) | Saman Nizami, Maryam Jillani, Shiza Shahid | Mubarik Imam | Mid stage of evaluation. | 2011-03-25 | Oct./Nov. 2011 | Mid
| YRC | Youth Resource Center | Nowshera | 11764 | Water Supply Scheme (Installation of hand-pumps) | Saba Gul, Ali Taufeeq, Kamran Ali | Waleed Saraf, Mehreen Siddiqi | Mid stage of evaluation. | 2011-03-17 | Oct./Nov. 2011 | Mid
| SIDO | Social Integrated Development Organization | Charsadda | 10674 | Water Supply Scheme (Installation of hand pumps) | Mughees Butt, Talal Butt, Hadia Raheel, Ruqaiya Ramzan | Mehreen Siddiqi, Qasim Ashraf | Site visit to be conducted in October so team can make a decision. | 2011-03-30 | Oct./Nov. 2011 | End
| MHSF | M.H. Sufi Foundation | Hafizabad | 11764 | Expansion of School - Kaseese Branch | Adeel Qaiser, Imran Siddiqui, Alexis Saba | Tarim, Wasim, Syeda Quratulain Masood | Site visit has been conducted. Team to make a decision based on site visit report. | 2011-05-26 | 2011-10-11 | End
| RDO | Rural Development Organization | Faisalabad | 11543 | Upgrade/extension of existing medical center | Ali Taufeeq, Sobia Nusrat, Taha Mashhadi | Syed Shahan Zafar | Initial stage of evaluation | 2011-05-14 | 2011-12-11 | Early
| FIDA | Foundation for Integrated Development Action | D.I. Khan | 11761 | Setting up bio-gas plants | Owais Rafiq, Shammi Quddus, Omar Bilal | Khurram Jamali | Initial stage of evaluation | 2011-05-16 | 2011-12-11 | Early
|  | Current Month | Previous Month
| Early Stage Diligence | 2
| Mid-Stage Diligence | 4
| Final Stage Diligence | 4
| Rejected | 0
| Total | 10 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | September 2011
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Al-Qasim | Al Qasim Foundation | District Khushab | 8841 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 8841 | 0 | End of 2011 (completion of project) | N | Last tranche of $2,330 released on July 15, 2011. Once construction of the last 4 bio-gas plants is complete, a site visit will be conducted to verify the construction and functioning of all plants. (Soon Valley experiencing 20 hours of load shedding a day so progress has been a bit slow.) To receive update from AQF soon.
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Aug. 2010 | Summer 2011 | 4957 | 0 | N/A | N | Site visit conducted by Imad Rashid in Feb., 2011. According to the site visit report, 3 pumps are functioning fine whereas one is pumping muddy water which is being used for feeding animals. Project team has decided to cancel the project. MGPO has sent over a report with relation to the existing 4 pumps and will return the remaining amount which was not used for the 5th pump to ADP. Mehreen to send Authority Letter to MGPO so funds can be transferred.
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 11308 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Latrines in total) | Oct. 2010 | TBC | 11308 | 0 | Report C (1 year after completion of project) | N | Project has come to an end with construction of all latrines complete. HEED held its last Hygiene Promotion session in early Apr., 2011. Report B submitted. Issues identified by HEED in its 3 month post project completion survey have been dealth with. A revised Report B has been submitted to ADP.
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School in Katch area | Jan. 2011 | TBC | 4705 | 4705 | Report on completion of Phase I (Aug. 2011) | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. Phase I: (i) Construction of computer lab is complete. (ii) Electrical work has been completed. (iii) Furniture and air conditioner for lab have been purchased. (iv) Installation of windows and door is in progress. (v) Newly hired computer teacher has been trained - training was supposed to end by Aug. 10, 2011. (vi) Watchman has been identified. Team waiting to receive photographs from SWS so that last tranche can be sent over.
| Amir Public School | Nia Ujala | Gujranawala | 7006 | Development of a school in Gujranwala (setting up of classrooms) | Jan. 2011 | TBC | 7006 | 0 | Report to be submitted when project comes to an end | Y | ADP wired first tranche of $2,706 to APS in late Jan., 2011 and then second tranche of $2,800 in Mar., 2011. Third tranche of $600 received by APS in June, 2011. Room construction and furnishing complete. Teacher training has been completed successfully with great feedback from all participants. APS sent over photographs of the Training as well as the Instructor's Training Schedule and his Recommendations. Last tranche sent over in Sep., 2011.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 2600 | 5753 |  | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. 16 loans (ranging from Rs. 2000 - Rs. 5000) were disbursed in the 2nd week of July. 2nd installments received from all 16 families. 21 others are registered but loans have not been disbursed yet. Due to instability in the availability and the fluctuating prices of chickens, NEEDS wants to introduce some other options into the project - loans for other small but viable businesses. ADP to discuss further options with NEEDS and make a decision.
| SDO | Saibaan Development Organization | Mansehra | 8823 | Setting up of a water filtration plant | Jul. 2011 | TBC | 0 | 8823 | SDO to inform ADP when preliminary requirements have been met | Y | SDO to send executed landlord agreement and finish the boring process in order to find an adequate water supply. The boring process could not be started because of heavy rains but in the mean time, SDO has been holding meetings for Water User Committees and has also met with an Islamabad based organization that has experience in the installation of water filtration plants. SDO has also held Awareness Sessions in different communities to inform them of the construction of the plant and to emphasize the importance of Health and Hygiene. Funds will be disbursed once the above mentioned requirements have been met (expected time frame: Oct. 2011).
| CAP | Community Advance Program | Lahore | 8717 | Computers and furniture for existing schools | Oct.2011 | TBC | 3485 | 5232 | Submission of Project Metrics Form on completion of Phase I | Y | Contract has been finalized and signed by CAP. 1st tranche transferred in Sep., 2011.
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Oct. 2011 | TBC | 0 | 15529 | To be based on final contract | Y | Approved from legal screening. Team in the process of finalizing contract.
| Projects In Progress | 8
| Remaining Funding | 40042

## Financials
Association for the Development of Pakistan |  |  |  |  | Q3 2011
Financials
|  | Q3 | YTD | Notes
Donations (net) |  | 18975 | 70334
Project Disbursements
| Microfinance for Poultry | 0 | 2600
| Sokar Village Latrines | 0 | 8800
| Amir Public School | 900 | 7012
| Al-Qasim Biogas Plants | 2330 | 5272.5
| CAP Computer Lab | 3485 | 3485
| SWS Computer Lab | 0 | 4729
| Total | 6715 | 31898.5
Expenses
| Salaries | 4308 | 13555
| Fundraising | 0 | 2031
| Other | 352 | 2752
| Total | 4660 | 18338
Available Funds
| General |  | 70.3
| Flood Redevelopment |  | 27

## Volunteers
Association for the Development of Pakistan | [9 empty] | September 2011
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 7 | 3 | 2 |  | 0 | 1 | 1 | 7 PECs are staffed presently. Khurram Jamali and Hasham Mehmood are on their first projects as a PECs. Saad Hasan and Natasha can be staffed on new projects.
| Evaluation Committee | 7 | 0 | 0 |  | 0 | 0 | 0 | 7 ECs are staffed on projects currently. The EC structure has been changed to only have PECs on projects. Existing ECs will either be groomed to take on the PEC role or remain as part of the PTL pool until they are ready to be PECs. Those with weak past records will be observed on their current projects and kept as PTLs on future projects or rotated out.
| Project Team Leads | 6 | 4 | 3 |  | 0 | 2 | 1 | 9 PTLs are staffed on projects right now. Ahmad Chaudary is available to take on a new project if its near or in Lahore. Bilal Hussain is also available. Bilal Noor has connected with Nabeel Hasnain to get trained as a PTL.
| Project Team | 20 | 6 | 9 |  | 8 | 5 | 5 | 2 new projects were staffed (YDO and FIDA). Ohra will also be staffed this week. 2 - 3 new projects are lined up for staffing after that.
| Site Visits | 3 | 1 | 8 |  | 6 | 5 | 2 | Site Visit for MH Sufi was conducted by Salman Naveed Khan, Ammar Ali will be conducting visits for both HEED projects once the teams have briefed him. Waseef Jamal will be conducting the visit for th SIDO project as well in the upcoming week. All site visit volunteers have also been connected to the media team so that they can take relevant pictures and get some material for human interest stories.
| Sourcing | 1 | 0 | 0 |  | 11 | 0 | 0 | Projects with more established NGOs with relevant past experience are being focused on right now since there is a greater probablility of approval of a project if the NGO has prior experience in a sector.
| Fundraising | 8 |  |  |  | 4 | 0 | 0 | The fundraising team will be raising the funds for the recently approved projects (SFL, CAP)
| Media | 4 | 0 | 0 |  | 4 | 0 | 0 | Ayesha Shahid, Natalia Bokhari, Sanaa Qureshi,Vajiha Sipra & Nabeel Ahmed are actively involved. Shemrez Khan is a new volunteer who is interested in coming on board for social media. Nabeel has connected with him and they will be talking about his involvement.
| Web team | 2 |  |  |  | 1 |  | 0
| Legal | 3 | 1 | 0 |  | 1 | 0 | 0 | Ongoing work on registering ADP in Pakistan. Dawood Ahmed who is currently an EC may be moved on to the legal team
| Marketing | 2 | 4 | 4 |  | 2 | 0 | 0 | Najia Khan and Saman Malik will be taking up the lead roles for the marketing team acting as co - coordinators. Hadia Raheel is looking after the partnerships development role.
| Other | 11 | 8 | 5 |  | 0 | 8 | 8 | Adnan Iqbal, Junaid Tahir and Hasan Karahan have joined as part of the KMS team. Hasan Riaz may also be coming on board for this as well as Madeeha Ansari (for the content part). 8 new volunteers have been assigned to PECs to help them in research and data compilation. These include Said Ali, Harris Abbasi, Maryam Hafeez, Omair Khalid, Sidra Hameed, Bilal Azhar, Saffaan Qadir, Khurram Afzal
| Total | 74 | 27 | 31 |  | 37 | 21 | 17
| Total signups | 14
| New projects launched | 2
| New projects expected | 3 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed
Initiatives:
KMS volunteers have been staffed
Salman Naveed Khan has been hired as the new VM

## Initiatives
Association for the Development of Pakistan |  |  |  |  | September 2011
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Mubarik Imam | Moved to a new lawyer who is in the process of building a rapport with the Registrar. Lawyer has sent over a list of documents that need to be sent to her before she can file for registration - in process. | NA
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz; Vajiha Sipra | Constantly updating projects pages on the website. Last issue of Dastak went out on Aug. 14, 2011. Next issue to go out in November, 2011. | Ongoing
| Volunteer Review | Group to review ADP's Volunteer Management Processes (recruiting, orientation, screening, training, staffing, feedback) with the aim of improving them. | Naima Hasan; Mehreen Siddiqi; Tarim Wasim; Mubarik Imam | Naima to draft a document detailing processes related to volunteers. Team to discuss issues like Volunteer retention, feedback, recruitment, training and recognition. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Adnan Iqbal, Junaid Tahir (Team Leads) Hasan Karahan | Team Leads have been identified and briefed of requirements. Tarim, Naima and Mehreen to provide support to them as they initiate the process and on an ongoing basis. Tech support volunteers have been connected with respective PECs. | Ongoing
| Volunteer Manager (VM) position | To hire a new full time VM |  | Salman Naveed Khan has been hired and will start from Oct. 11, 2011. Will be trained by Naima. | Complete (Oct. 2011)
| Partnerships Development | To develop relationships with instituitions/organizations as volunteer & funding partners to increase visibility and out reach | Nabeel Ahmed/Usman Hassan | Hadia Raheel is now involved in this initiative. We need volunteers engaged in this initiative in multiple cities. | Ongoing