## Cover
Association for the Development of Pakistan
Monthly Report
2011-11-11

## Proposals
Association for the Development of Pakistan | [8 empty] | November 2011
New Proposals
Approved from screening/On hold
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Project approved. Team to be staffed - on hold because several water and sanitation projects are already being evaluated. | 2011-03-03 | Naima Hasan | Mid May 2011
| SHATAC | Shehri Ijtamai Taraqiati Council | 11764 | Incineration plant at a Hospital | Mandi Bahauddin | Pending screening. | 2011-07-03 | Naima Hasan | 2011-12-11
| ABKT | Association for Behavior & Knowledge Transformation | 11720 | Construction of latrines | Charsadda | Checklist complete. Decision to be made. | 2011-06-22 | Naima Hasan | 2011-12-11
| RF | Roshni Foundation | 11741 | Roshni Model Primary School Project | Chinglai, Swabi | Rejected. Though this may be a promising project in the future, the school is very new and only has a few children at this time. Concerns with regards to sustainability. | 2011-08-22 | Dawood Ahmed | 2011-12-11
| YMS | Young Man Society | 10882 | Rehabilitation of water supply system | Rahim Yar Khan | Approved. Team to be staffed. | 2011-09-06 | Mehreen Siddiqi | 2011-11-11
| SRS | Sindhica Reforms Society | 11536 | Construction of latrines | District Shaheed Benazirabad, Sindh | Checklist complete. Decision to be made after some follow up. | 2011-09-26 | Salman Naveed Khan | 2011-12-11
| DUH | Darul Hikmat Society | 9952 | Computer labs for 3 existing schools | Youhannabad, Lahore | Checklist complete. Decision to be made after some follow up. | 2011-10-01 | Mughees Butt | 2011-12-11
| REED | Rural Education and Educational Development Society | 11645 | Installation of hand pumps | Sadiqabad, Rahimyar Khan | Pending screening. | 2011-11-15 | Mehreen Siddiqi | 2011-12-11
| BDS | Beer Development Society (Haripur) | 10233 | Installation of water filtration plants in government schools | Haripur, KPK | Pending screening. | 2011-11-18 | Bilal Hussain | 2011-12-11
| MW | Merit Witness | 8823 | Installation of hand pumps | Ijara, Charsadda | Pending screening. | 2011-11-29 | Salman Naveed Khan | 2011-12-11
| NLM | New Life Ministry | 10196 | Construction of free dispensary for women and the disabled | Youhannabad, Lahore | Pending screening. | 2011-11-29 | Khurram Jamali | 2011-12-11
|  | Current Month | Previous Month
| Early Stage | 8 | 6
| Approved | 1 | 3
| Rejected | 1 | 2
| On hold | 1 | 1
| Total | 11 | 12

## Under Review
Association for the Development of Pakistan | [11 empty] | November 2011
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| APS | Arshad Public School | AJK | 11619 | Water supply project-installation of water tanks, pipes etc to provide the school with access to clean water | Uzaib Saya, Habiya Beg, Mariam Haqqie | Mubarik Imam, Dawood Ahmed | Rejected. Though this would have been an important project for the children of APS, it's not possible for ADP to partner with APS again at this point. | 2010-06-15 | 2011-11-11 | End
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 11764 | Mishtimba Village family latrines | Danish Iqbal, Abdullah Hasan, Habiya Beg | Tarim Wasim, Nabeel Hasnain | Approved. Project in execution. | 2011-04-09 | 2011-11-11 | End
| SS | Sudhaar Society | Kasur | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Farzal Dhojki, Babar Khan, Muzammal Ashraf | Rameez Dossa, Ahmed Makani | Revised proposal submitted by Sudhaar being evaluated by the team. | 2011-03-25 | 2011-12-11 | End
| HEED(edu) | Health Education Environment Development Association | Neelum Valley, AK | 16470 | Rehabilitation of flood affected schools | Danish Iqbal, Alizay Saeed, Danyaal Farooqui | Tarim Wasim, Syeda Quratulain Masood | Mid stage of evaluation. Project evaluation has re-commenced after a break. | 2011-04-17 | 2011-01-11 | Mid
| LS | Lifeline Society | Near Multan and Muzaffargarh | 10235 | Water Supply Scheme (Installation of hand pumps) | Maryam Jillani, Syeda Quratulain Masood, Amreena Jaffar Diwan | Mubarik Imam | Mid stage of evaluation. Project evaluation has re-commenced after a break. | 2011-03-25 | 2011-01-11 | Mid
| YRC | Youth Resource Center | Nowshera | 11764 | Water Supply Scheme (Installation of hand-pumps) | Saba Gul, Ali Taufeeq, Kamran Ali | Mehreen Siddiqi | Site visit to be conducted on Dec. 10, 2011. Team to make a decision based on Report. | 2011-03-17 | 2011-12-11 | End
| SIDO | Social Integrated Development Organization | Charsadda | 5141 | Water Supply Scheme (Installation of hand pumps) | Mughees Butt, Talal Butt, Hadia Raheel, Ruqaiya Ramzan | Mehreen Siddiqi, Qasim Ashraf | Approved. Project has been cleared from legal screening. Draft version of contract being drawn up. | 2011-03-30 | 2011-11-11 | End
| RDO | Rural Development Organization | Faisalabad | 11543 | Upgrade/extension of existing medical center | Ali Taufeeq, Sobia Nusrat, Taha Mashhadi | Syed Shahan Zafar | Mid stage of evaluation. Site visit scheduled for Dec. 11, 2011. | 2011-05-14 | 2011-01-11 | Mid
| FIDA | Foundation for Integrated Development Action | D.I. Khan | 11761 | Setting up bio-gas plants | Owais Rafiq, Shammi Quddus, Omar Bilal | Khurram Jamali | Site visit to be conducted in Dec. 2010. Team to make a decision based on Report. | 2011-05-16 | 2011-01-11 | End
| YDO | Youth Development Organization | Rajanpur, Punjab | 11764 | Water suuply scheme (Installation of hand- pumps) | Ahmad Chaudhary, Meher Makda, Sofia Ahmad | Hasham Mehmood | Mid stage of evaluation | 2011-05-18 | 2012-01-12 | Mid
| OHRA | Organization for Human Resources Allocation | Nathiagali | 11759 | Water supply scheme | Jawad Hasan, Imran Siddiqui Sameed Imran | Natasha Qureshi | Mid stage of evaluation | 2011-07-27 | 2012-01-12 | Mid
| AWHES | Aman Welfare Health and Education Society | Muzaffarabad | 11776 | Upgrade of existing medical center | Najaf Shah, Babar Khan, Sajjad Jafri, Amena Mian | Akbar Bhaidani | Initial stage of evaluation (project kick off call held on Nov. 19, 2011) | 2011-09-18 | 2011-02-12 | Early
| QSET | Qurban and Surraya Educational Trust | Lahore | 11647 | Computer lab for existing school | Adeel Qaiser, Abdullah Hasan, Farhan Mumtaz | Waleed Saraf | Initial stage of evaluation (project kick off call held on Nov. 20, 2011) | 2011-09-13 | 2011-02-11 | Early
| SOS | SOS Children's Village | Kasur | 11764 | Construction of classrooms in existing school | Taha Mashhadi, Elisa Dunn, Alexis Saba, Rania Hamid | Salman Naveed Khan | Initial stage of evaluation (project kick off call held on Nov. 27, 2011) | 2011-09-19 | Feb=11 | Early
|  | Current Month | Previous Month
| Early Stage Diligence | 3
| Mid-Stage Diligence | 5
| Final Stage Diligence | 5
| Rejected | 1
| Total | 14 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | November 2011
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| Al-Qasim | Al Qasim Foundation | District Khushab | 8841 | Sustainable Energy - Biogas plants for Soon Valley community | 2009-02-27 | TBC | 8841 | 0 | Project Completion Report (End of 2011) | N | Last tranche of $2,330 released on July 15, 2011. Project is complete and the Completion Report is expected soon. Once the Report is received, a site visit will be conducted to verify the construction and functioning of all plants.
| MGPO | Mountain and Glacier Protection Organization | Mansehra | 9523 | Water Supply Scheme for Shamdarah and Chajhar, Mansehra district (140km from Islamabad) | Aug. 2010 | Summer 2011 | 3557 | 0 | N/A | N | Site visit conducted by Imad Rashid in Feb., 2011. According to the site visit report, 3 pumps were functioning fine whereas one was pumping muddy water which was being used for feeding animals. Project team has decided to cancel the project. MGPO has returned the remaining money that was to be used for the installation of the 5th hand-pump. Project update needs to be published on ADP's website.
| HEED | Health, Education, Environment & Sustainable Development | Sokar, AJK | 11308 | Sanitation Coverage for Sokar Village in Kashmir (target 60 Family Latrines in total) | Oct. 2010 | TBC | 11308 | 0 | Report C (1 year after completion of project) | N | Project has come to an end with construction of all latrines complete. HEED held its last Hygiene Promotion session in early Apr., 2011. Report B submitted. Issues identified by HEED in its 3 month post project completion survey have been dealt with. A revised Report B has been submitted to ADP.
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School | Jan. 2011 | TBC | 8193 | 1217 | Report on completion of Phase II | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. According to SWS, Phase I has been completed. Photographs of the lab have also been received by ADP. Next tranche of Rs. 300,000 ($3,488) was sent to SWS on Nov. 15, 2011. Phase II to begin after SWS receives the money.
| Amir Public School | Nia Ujala | Gujranawala | 7006 | Development of a school in Gujranwala (setting up of classrooms) | Jan. 2011 | TBC | 7006 | 0 | Report to be submitted when project comes to an end | N | ADP wired first tranche of $2,706 to APS in late Jan., 2011 and then second tranche of $2,800 in Mar., 2011. Third tranche of $600 received by APS in June, 2011. Room construction and furnishing complete. 1st Teacher Training was completed successfully with great feedback from all participants. APS sent over photographs of the Training as well as the Instructor's Training Schedule and his Recommendations. Last tranche sent over in Sep., 2011. Next Teacher Training Session to be held soon - APS to send over update.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 2600 | 5753 | Loan Report Form Household Survey Form Monthly Household Master Form (to be maintained regularly) | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. As of now, 44 loans have been given out. Recovery of monthly installments is under way with several loans having been completely re-paid. Demand for these loans is increasing and NEEDS has received 20 more applications for 200 chicks. Site visit to be conducted in Dec. 2011 before decision to send over next tranche is made.
| SDO | Saibaan Development Organization | Mansehra | 8700 | Setting up of a water filtration plant | Jul. 2011 | TBC | 8700 | 0 | Report A (1st day of each quarter) | N | The entire amount of funding was disbursed to SDO in mid-October, 2011. Construction work is almost complete. Work on water filtration plant to be started once construction commences.
| CAP | Community Advance Program | Lahore | 8485 | Computers and furniture for existing schools | Oct.2011 | TBC | 8485 | 0 | Submission of Project Metrics Form on completion of Phase II | N | 1s tranche of $3,485 transferred in Sep., 2011. CAP has sent over the following documents: (i) Scanned bill (ii) Computer syllabus form classes 1-8 (iii) Worksheets for all classes (iv) Short course details (v) Report on completion of Phase I Last tranche of $5,000 sent over in November, 2011. Natasha Qureshi (the PEC on the project) to visit the CAP schools in December, 2011.
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Oct. 2011 | TBC | 3070 | 12459 | Attested copies of all beneficiary land ownsership documents within 2 weeks of receiving 1st disbursement. | Y | 1st tranche of $3,070 sent over to SFL in November, 2011. Since there was some problem with the recipient bank, SFL provided another account and money has now been wired to the 2nd account. Project to commence once 1st tranche has been received by SFL.
| MHSF | M.H. Sufi Foundation | Hafizabad | 11764 | Expansion of School | Nov. 2011 | TBC | 5800 | 5964 | Report A on the 10th of every month while construction is in progress | Y | 1st tranche of Rs. 500,000 sent over to MHSF in November, 2011.
| Projects In Progress | 9
| Remaining Funding | 25393

## Volunteers
Association for the Development of Pakistan | [9 empty] | November 2011
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 12 | 2 | 1 |  | 0 | 2 | 0 | Akbar Bhaidani was staffed on the AWHES Project while Salman Naveed Khan and Haleema Raheel were added to the PEC pool. Salman and Haleema have been assigned the SOS and YMS projects respectively.
| Evaluation Committee | 7 | 0 | 0 |  | 0 | 0 | 0 | 5 ECs are staffed on active projects. Of the projects under review, only 2 have ECs as part of the PTMs (Ahmed Makani, Sudhaar, and Syeda Masood, HEED-edu.).
| Project Team Leads | 11 | 2 | 1 |  | 0 | 0 | 0 | 11 PTLs are staffed on projects right now. Maryam Jillani is the acting PTL on the LS project. Taha Mashhadi, who was nominated by Waleed as a PTL, has been staffed on the SOS Project. Najaf Shah has been staffed as the PTL on the AWHES Project while Adeel Qaiser is the PTL for the QSET project team. Bilal Noor (who was inducted in ADP as a PTL) is available and waiting to be staffed on his first project.
| Project Team | 25 | 3 | 5 |  | 16 | 6 | 5 | 3 new peojects were staffed in November, 2011 - QSET, AWHES, and SOS. The new inductees (as PTMs) include Sajjad Jafri/Amena Mian (AWHES), Farhan Mumtaz (QSET), and Elisa Dun/Rania Hamid (SOS). Apart from the ones inducted on project teams, 12 new volunteers also registered with ADP - Connected: 2, Awaiting response: 8, Not contacted: 2.
| Site Visits | 5 | 6 | 0 |  | 3 | 3 | 2 | Site Visits for FIDA and YRC still pending. The SVVs were inducted but the YRC visit was postponed and FIDA SVV/PTL have yet to connect. LS, RDO and NEEDS SVVs selected - dates for the visits yet to be finalized.
| Sourcing | 1 | 0 | 0 |  | 0 | 0 | 0 | Projects with more established NGOs with relevant past experience are being focused on right now since there is a greater probablility of approval of a project if the NGO has prior experience in a sector.
| Fundraising | 8 | 0 | 0 |  | 1 | 1 | 0 | Usman to identify potential ADP hubs/chapters so that a concerted effort to focus on fundraising activities within and outside the US can be made. Dec./Jan. volunteer meet-ups part of the plan to identify volunteers who may be interested in the fundraising mantle in their geographical locations.
| Media | 6 | 10 | 0 |  | 2 | 2 | 1 | Sanaa Qureshi,Vajiha Sipra, Najia Khan, Nabeel Ahmed and Ayesha Shahid are actively involved. Natalia Bokhari is temporarily unavailable. New volunteers shall be added to the Media Team in November for on-going activities, videography project (if approved), and the interactive map project (if approved). Nabeel has also inducted Marium Sheikh as a new volunteer for graphic design work. Elisa Dun (also a PTM) shall also be coming on-board the Media Team as a blogger/writer. 2 videographers and one HTML5/Javascript expert required for the Videos project and the volunteer interactive map initiative respectively.
| Web team | 2 | 0 | 0 |  | 0 | 0 | 0 | No updates for November, 2011.
| Legal | 3 | 1 | 1 |  | 0 | 0 | 0 | Ongoing work on registering ADP in Pakistan. Mehreen introduced both Dawood Ahmed and Amit to each other via email - Dawood has recently joined the legal team.
| Marketing | 2 | 4 | 2 |  | 0 | 0 | 0 | No progress on this front. Nabeel has identified the need to recruit a Marketing Lead, but no profiles (from the current volunteers) have been shortlisted as yet.
| Other | 11 | 0 | 0 |  | 1 | 1 | 1 | 1 new volunteer has been added to the KMS team for Waleed. The previously appointed volunteer had connectivity issues (skype) and Waleed felt that the volume of work required could not be covered without significant hassle via only email communication.
| Total | 93 | 28 | 10 |  | 23 | 15 | 9
| Total signups | 23
| New projects launched | 3
| New projects expected | 1 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed for the Media / Fundraising teams
Initiatives:
KMS volunteers have been staffed

## Initiatives
Association for the Development of Pakistan |  |  |  |  | November 2011
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Lead: Mubarik Imam Volunteer: Mehreen Siddiqi | The List of ADP's Executive Committee Members and copies of their ID cards have been sent to the lawyer. Next steps: A utility bill/lease agreement for ADP's address in Lahore to be sent to the lawyer. | Ongoing
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz, and Vajiha Sipra | Constantly updating projects pages on the website. Next issue of Dastak to go out in December, 2011. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Leads: Adnan Iqbal, Junaid Tahir Volunteer: Hasan Karahan | Team Leads have been identified and briefed of requirements. Tech support volunteers have been connected with respective PECs. Work on populating the KMS is underway. | Ongoing
| Partnerships Development | To develop relationships with instituitions/organizations as volunteer & funding partners to increase visibility and outreach | Leads: Nabeel Ahmed and Usman Hassan Volunteer: Hadia Raheel | Hadia Raheel is now involved in this initiative. We need volunteers engaged in this initiative in multiple cities. | Ongoing
| ADP Project Videos | To identify past completed projects and get volunteers to visit sites and make videos | Leads: Nabeel Shakeel and Salman Naveed Khan Volunteer: Najia Khan | Of the completed projects, the media team has selected the Al Qasim Biogas, NEEDS (Water), NEEDS (Poultry), Amir Public School, HEED (Sokar), and Arshad Public School Projects for developing one-minute documentaries. The responsibility of this initiative rests with Najia Khan. | Ongoing
|  | To obtain usable content from site visit volunteers for the projects under evaluation | Lead: Nabeel Shakeel Volunteers: Ayesha Sarfaraz, Vajiha Sipra and Sanaa Qureshi | Nabeel Shakeel came up with a plan to assign one media team volunteer for every project under evaluation. The volunteer shall liaise with the site visit volunteer to obtain photographs/videos collected at each site visit so that project documentaries can be developed once a project is funded.
| Technical Advisors | To have a permanent panel of experts that teams can reach out to during project evaluations | Lead: Salman Naveed Khan | In the process of identifying and talking to experts in various fields of development. Discussions ongoing with SNV World for biogas (www.snvworld.org) and IRSP for WASH (www.irsp.org.pk). | Ongoing
| Interactive Volunteer Map | To develop and make available an interactive map on the ADP website detailing the presence of volunteers in various countries/cities | Lead: Salman Naveed Khan | Have interacted with Farhan Ahmed (who had been ADP's webmaster in the past) on this. He has developed this demo (http://macbonsai.com/map/). He has also provided a detailed document on how the application should be developed and interfaced with the website. Further progress on this initiative will be based on Farhan's interest in taking this forward from Jan. 2012 or ADP recruiting another volunteer to complete the assignment. | Ongoing
| Volunteer get-together/events | To increase interaction and help develop a stronger bond between volunteers based in various locations across the world. | Lead: Salman Naveed Khan | Volunteer events are planned in Dec. 2011 / Jan. 2012 in Washington DC, Boston, New York, San Francisco, Toronto, Singapore, Lahore, Islamabad and Karachi. Jawad Hasan shall be taking the lead in Boston; Hasham Mehmood in DC; Tarim Wasim in San Francisco; Waleed Saraf in Islamabad; Salman Naveed in Lahore and Usman Hassan in New York. | 2012-01-31