## Cover
Association for the Development of Pakistan
Monthly Report
2012-03-12

## Proposals
Association for the Development of Pakistan | [8 empty] | March 2012
New Proposals
Approved from screening/On hold
Rejected
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| AHD | Agency for Human Development | 13886 | Water and Sanitation Facilities | Charsadda | Approved. Team to be staffed (not on hold any more) | 2011-03-03 | Naima Hasan | 2011-05-01
| SHATAC | Shehri Ijtamai Taraqiati Council | 11764 | Incineration plant at a Hospital | Mandi Bahauddin | Rejected. NGO has been encouraged to submit a proposal more in line with ADP criteria. | 2011-07-03 | Salman Naveed Khan | 2012-03-12
| SRS | Sindhica Reforms Society | 11536 | Construction of latrines | District Shaheed Benazirabad, Sindh | Approved. Team to be staffed. | 2011-09-26 | Salman Naveed Khan | 2012-02-12
| BDS | Beer Development Society (Haripur) | 10233 | Installation of water filtration plants in government schools | Haripur, KPK | Approved. Team to be staffed. | 2011-11-18 | Bilal Hussain | 2012-01-12
| BAP | Behbud Association of Pakistan | 10406 | Equipment for laboratory | Rawalpindi | Approved. Team to be staffed. | 2011-12-14 | Minhaj Patel | 2012-01-11
| CAUSE | Community Assistance Under Sustainable Environment | 9255 | Construction of classrooms and furniture for existing schools | Charsadda | Pending screening. | 2011-12-14 | Dawood Ahmed | 2012-05-12
| RI | Resettling the Indus | 11111 | Reconstruction of flood affected houses | Muzaffargarh | RI withdrew its proposal stating that it felt it was not possible for them to undergo ADP's evaluation process due to their emergency needs. | 2012-01-11 | Salman Naveed Khan | 2012-03-12
| SF | Saif Foundation | 11111 | Water supply project | D G Khan | Pending screening. | 2012-01-19 | Qasim Ashraf | 2012-05-12
| EHDF | Education Health & Development Foundation | 8889 | Provision of furniture to informal schools in/around Islamabad. | Islamabad | Pending screening. | 2012-02-01 | Salman Naveed Khan | 2012-04-12
| TRDP | Thardeep Rural Development Program | 11111 | Govt-school renovation + provision of furniture | Jamshoro | Pending screening. | 2012-02-28 | Salman Naveed Khan | 2012-04-12
| ADO | Area Development Organization | 10886 | Water supply project | Muzaffarbad | Pending screening. | 2012-02-29 | Salman Naveed Khan | 2012-05-12
| FTS | Faroog-e-Taleem Society | 8800 | Provision of equipment for an MCH clinic | Mianwali | Pending screening. | 2012-03-01 | Salman Naveed Khan | 2012-05-12
| AFB | Anjuman Falah-o-Bahbud | 11111 | Computer lab in a govt. high school | Muzaffarabad | Pending screening. | 2012-03-14 | Salman Naveed Khan | 2012-04-12
| TGS | The Garage School | 8484 | Sponsorship of 35 students enrolled in an Adult Literacy Program for a year | Karachi | Pending screening. | 2012-03-20 | Salman Naveed Khan | 2012-04-12
|  | Current Month | Previous Month
| Early Stage | 8 | 7
| Approved | 4 | 4
| Rejected | 2 | 2
| On hold | 0 | 0
| Total | 14 | 13

## Under Review
Association for the Development of Pakistan | [11 empty] | March 2012
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| SS | Sudhaar Society | Kasur | 11765 | Sanitation and Health (Construction of latrines and installation of hand-pumps in 15 schools) | Babar Khan, Muzammal Ashraf | Rameez Dossa | Revised proposal submitted by Sudhaar being evaluated by the team. Site visit planned for April. Decision expected soon after the visit. | 2011-03-25 | 2012-04-12 | End
| HEED(edu) | Health Education Environment Development Association | Neelum Valley, AK | 16470 | Rehabilitation of flood affected schools | Danish Iqbal, Alizay Saeed, Danyaal Farooqui | Tarim Wasim, Syeda Quratulain Masood | Rejected. | 2011-04-17 | 2012-03-12 | End
| YDO | Youth Development Organization | Rajanpur, Punjab | 11764 | Water suuply scheme (Installation of hand- pumps) | Adnan Pathan Meher Makda, Sofia Ahmad | Hasham Mehmood | Mid stage of evaluation. Site visit to be conducted soon. | 2011-05-18 | 2012-05-12 | Mid
| OHRA | Organization for Human Resources Allocation | Nathiagali | 11759 | Water supply scheme | Jawad Hasan, Imran Siddiqui Sameed Imran | Salman Naveed Khan | Initial stage of evaluation. | 2011-07-27 | 2012-06-12 | Early
| AWHES | Aman Welfare Health and Education Society | Muzaffarabad | 11776 | Upgrade of existing medical center | Najaf Shah, Babar Khan, Sajjad Jafri, Amena Mian | Mehreen Siddiqi | Initial stage of evaluation. | 2011-09-18 | 2012-06-12 | Early
| SOS | SOS Children's Village | Kasur | 11764 | Construction of classrooms in existing school | Taha Mashhadi, Elisa Dunn, Alexis Saba, Rania Hamid | Salman Naveed Khan | Approved. Legal screening pending. | 2011-09-19 | 2012-02-12 | End
| YMS | Young Man Society | Rahimyar Khan | 10882 | Rehabilitation of water supply system | Bilal Hussain, Habiya Beg, Noorya Hayat | Haleema Raheel | Rejected. Team had concerns with regards to the quality of the hand pumps, the budget and the post project monitoring. | 2011-09-06 | 2012-03-12 | End
| DUH | Darul Hikmat Society | Lahore | 9952 | Computer labs for 3 existing schools | Mughees Butt, Bilal Noor, Rabia Hussain | Mubarik Imam | Mid stage of evaluation. Site visit to be conducted soon. | 2011-10-01 | 2012-05-12 | Mid
| CFC | Concern for Children | Karachi | 12311 | Upgrade of existing medical center | Nabeel Hasnain, Javeria Chaudhry, Farhan Mumtaz | Mehreen Siddiqi | Mid stage of evaluation. | 2012-03-06 | 2012-05-12 | Mid
| JAQ | JAQ Education Trust | Islamabad | 11055 | Infrastructure for an informal school system | Danyaal Farooqui, Ruqaiya Ramzan, Asim Butt | Tarim Wasim | Mid stage of evaluation. | 2012-03-04 | 2012-05-12 | Mid
|  | Current Month | Previous Month
| Early Stage Diligence | 2
| Mid-Stage Diligence | 4
| Final Stage Diligence | 2
| Rejected | 2
| Total | 10 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | March 2012
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School | Jan. 2011 | TBC | 8193 | 1218 | Report on completion of Phase II | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. According to SWS, Phase I has been completed. Photographs of the lab have also been received by ADP. Next tranche of Rs. 300,000 ($3,488) was sent to SWS in Dec., 2011. Phase II in progress. Before disbursing the last tranche, site visit to be conducted in early May, 2012.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7725 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 5075 | 2650 | Loan Report Form Household Survey Form Monthly Household Master Form (to be maintained regularly) | Y | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. Site visit conducted by Sadia Ijaz in Dec., 2011 confirmed the progress and demand for the project. 2nd tranche of $2,475 sent over in Dec., 2011. As of mid Dec., 2011, 62 loans had been disbursed. Next report expected soon.
| SDO | Saibaan Development Organization | Mansehra | 8700 | Setting up of a water filtration plant | Jul. 2011 | TBC | 8700 | 0 | Report A (1st day of each quarter) | N | The entire amount of funding was disbursed to SDO in mid-October, 2011. Construction work is complete and water filtration plant has been installed. Plant to become functional from mid-Jan., 2012. Pictures received from SDO.
| CAP | Community Advance Program | Lahore | 8485 | Computers and furniture for existing schools | Oct.2011 | TBC | 8485 | 0 | Submission of Project Metrics Form on completion of Phase II | N | 1s tranche of $3,485 transferred in Sep., 2011. CAP has sent over the following documents: (i) Scanned bill (ii) Computer syllabus form classes 1-8 (iii) Worksheets for all classes (iv) Short course details (v) Report on completion of Phase I Last tranche of $5,000 sent over in November, 2011. Phase II in progress. To receive detailed report.
| SFL | Sahara for Life Trust | Muzaffargarh | 15529 | Reconstruction of homes for flood victims | Oct. 2011 | TBC | 12603 | 2926 | Progress Reports (every 2 weeks) and Monthly Budget Reports | Y | 1st tranche of $3,070 received by SFL in Dec., 2011. List of finalized beneficiaries and Project Initiation Report submitted. Second tranche of $9,533 sent over in Jan., 2012. Report after completion of houses expected soon.
| MHSF | M.H. Sufi Foundation | Hafizabad | 11764 | Expansion of School | Nov. 2011 | TBC | 11764 | 0 | Report A (pictures and receipts) on the 10th of every month while construction is in progress | N | 1st tranche of Rs. 500,000 sent over to MHSF in Nov., 2011. 1st batch of Construction pictures and receipts received by ADP. Second tranche wired in Mar. 2012. Update expected soon.
| SIDO | Social Integrated Development Organization | Charsadda | 5040 | Water Supply Scheme (Installation of hand pumps) | Jan. 2012 | TBC | 2711 | 2329 | Report B (3 weeks after receiving the 2nd tranche) | Y | 2nd tranche wired in Mar. 2012. 3rd (and last tranche) expected to be released in May 2012 after Report B has been received.
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 14200 | Mishtimba Village family latrines | Jan. 2012 | TBC | 14200 | 0 | Reports A and B (to be submitted at the end of every month) | N | All funding released in Jan., 2012. Project in progress.
| RDO | Rural Development Organization | Faisalabad | 5888 | Upgrade/extension of existing medical center | 2012-05-01 | TBC | 0 | 5888 | Report A (1 month after receiving 1st tranche) | Y | Contract signed by RDO and ADP. 1st tranche to go out in early May 2012.
| FIDA | Foundation for Integrated Development Action | D.I. Khan | 8826 | Setting up bio-gas plants | 2012-05-12 | TBC | 0 | 8826 | Status Report (1 month after receipt of funding) | Y | Contract signed by FIDA and ADP. 1st tranche to go out in early May 2012
| Projects In Progress | 10
| Remaining Funding | 23837

## Financials
Association for the Development of Pakistan |  |  |  | 2012
Financials
|  | Q1 | YTD
Donations (net) |  | 8742 | 8742
Project Disbursements
| Shenky/Cheena Hand Pumps | 2690 | 2690
| Kot Addu Model Village | 9575 | 9575
| Mishtimba Sanitation | 14200 | 14200
| Total | 26465 | 26465
Expenses
| Salaries | 3618 | 3618
| Fundraising | 3725 | 3725
| Other | 345 | 345
| Total | 7688 | 7688
Available Funds
| General |  | 36.9
| Flood Redevelopment |  | 4.6

## Volunteers
Association for the Development of Pakistan | [9 empty] | March 2012
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 13 | 6 | 0 |  | 0 | 0 | 0 | To ensure regular evaluations, need to add more PECs to the existing pool.
| Evaluation Committee | 5 | 0 | 0 |  | 0 | 0 | 0 | 5 ECs are staffed on active projects. Of the projects under review, only 1 has an active EC (Syeda Masood, HEED).
| Project Team Leads | 11 | 4 | 4 |  | 0 | 0 | 0 | 11 PTLs are staffed on projects right now, with 04 more needed for the to-be-staffed-project-teams.
| Project Team | 26 | 9 | 18 |  | 13 | 4 | 5 | 2 new project evaluation teams have been staffed in March '12 (CFC and JAQ).
| Site Visits | 4 | 2 | 3 |  | 2 | 2 | 0 | Site visits planned for Sudhaar and YDO projects.
| Sourcing | 1 | 1 | 0 |  | 2 | 0 | 0 | Projects with more established NGOs with relevant past experience are being focused on right now since there is a greater probablility of approval of a project if the NGO has prior experience in a sector. Organizations are being requested not to submit proposals till such time that we have evaluated their strengths and capabilities.
| Fundraising | 8 | 2 | 0 |  | 4 | 0 | 0 | One voluteer attached with Usman to go through and compile requirements of USAID and assess how ADP can benefit from the funding programs. One additional volunteer required to work with Usman to set up and coordinate the work-place donation/matching grants initiative.
| Media | 6 | 10 | 0 |  | 6 | 4 | 0 | 4 new recruits in the Media team. Training of the new members of the media team to commence in Apr '12.
| Web team | 2 | 0 | 0 |  | 0 | 0 | 0 | No updates.
| Legal | 3 | 1 | 1 |  | 0 | 0 | 0 | No updates.
| Marketing | 2 | 4 | 2 |  | 1 | 0 | 0 | No updates.
| Other | 11 | 0 | 0 |  | 0 | 0 | 0 | These are the volunteers working on the KMS.
| Total | 92 | 39 | 28 |  | 28 | 10 | 5
| Total signups | 18
| New projects launched | 2
| New projects expected | 3 |  |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed for the Media / Fundraising teams
PEC pool needs to grow
Initiatives:
KMS volunteers have been staffed

## Initiatives
Association for the Development of Pakistan |  |  |  |  | March 2012
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Lead: Mubarik Imam Volunteer: Mehreen Siddiqi | The List of ADP's Executive Committee Members and copies of their ID cards have been sent to the lawyer. Next steps: A utility bill/lease agreement for ADP's address in Lahore to be sent to the lawyer. | Ongoing
| Media Team | The Media Team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz, Vajiha Sipra, Afshin Khan, Rabiah Hussain, and Najia Khan | In addition to its work on adding content to the website, the Media Team is working on multiple projects and initiatives at this time (Project Videos, Annual Report, Dastak). | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Leads: Adnan Iqbal, Junaid Tahir Volunteer: Hasan Karahan | Team Leads have been identified and briefed of requirements. Tech support volunteers have been connected with respective PECs. Work on populating the KMS is underway. | Ongoing
| ADP Project Videos | To identify past completed projects and get volunteers to visit sites and make videos | Leads: Nabeel Shakeel and Salman Naveed Khan Volunteer: Najia Khan | Of the completed projects, the Media Team has selected Al Qasim Biogas, NEEDS (Water), NEEDS (Poultry), Amir Public School, HEED (Sokar) and Arshad Public School Projects for developing one-minute documentaries. Videographer to be finalized so the formal initiative can be launched in May, 2012. | Ongoing
|  | To obtain usable content from site visit volunteers for the projects under evaluation | Lead: Nabeel Shakeel Volunteers: Ayesha Sarfaraz, Vajiha Sipra and Sanaa Qureshi | The initiative has been formally made part of the project cycle.
| Technical Advisors | To have a permanent panel of experts that teams can reach out to during project evaluations | Lead: Salman Naveed Khan | Technical advice was sought by the FIDA team for the biogas project (RSPN), YDO team for the handpumps project (Abdul Qadir), and YRC team for the handpumps project (IRSP). FAQs to be developed and made part of the respective KMS sections. | Ongoing
| Interactive Volunteer Map | To develop and make available an interactive map on the ADP website detailing the presence of volunteers in various countries/cities | Lead: Salman Naveed Khan | The initiative has been put on the back-burner for now. Will be taken up once work on the Annual Report has been completed. | 2012-06-01
| Volunteer get-together/events | To increase interaction and help develop a stronger bond between volunteers based in various locations across the world | Lead: Salman Naveed Khan | After volunteer get togethers at the end of 2011/beginning 2012, events now being planned for summer 2012. | Jul/Aug-12
| Annual Report 2011 | To publish ADP's Annual Report for 2011 | Lead: Nabeel Ahmed Volunteers: Media Team members, Mehreen Siddiqi and Salman Naveed Khan | Need to accelerate pace on this project and get final Report published in May 2012 | 2012-05-01
| Fundraising | To actively raise funds to meet the funding needs of projects approved in 2012 | Lead: Usman Hasan | (i) Improve communication with donors: in the process of selecting a volunteer to assist Usman (ii) Corporate donation matching set- up (iii) Plan fundraising events (iv) Foundation Fundraising | Ongoing