## Cover
Association for the Development of Pakistan
Monthly Report
2012-08-12

## Proposals
Association for the Development of Pakistan | [8 empty] | August 2012
New Proposals
Approved from screening
Rejected
On Hold
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| SDO | Sustainable Development Organization | $10,526 (50% of project budget) | Micro Hydro power project | Neelum Valley, AK | Approved from screening. On hold since it is best to start construction in the area in April. Project team will be staffed in Jan., 2013. | 2012-05-25 | Mehreen Siddiqi | 2012-06-12
| ADO | Area Development Organization | 10886 | Water supply project | Muzaffarbad | Approved. Team to be staffed. | 2012-02-29 | Salman Naveed Khan | 2012-07-12
| SWO | Shama Welfare Organization | 9179 | Water supply project | Charsadda | Rejected. NGO does not have enough experience in installing hand pumps. | 2012-06-06 | Mehreen Siddiqi | 2012-08-12
| IWA | Indus Welfare Association | 8865 | Expansion of an existing school | Sanghar, Sindh | Pending screening. | 2012-06-27 | Hasham Mehmood | 2012-09-12
| JAT | Jannat Aziz Trust | 11111 | Eye equipment for an existing clinic | Burewala, Vehari | Approved. Team to be staffed. | 2012-07-04 | Salman Naveed Khan | 2012-08-12
| SFL (health) | Sahara for Life Trust | 15526 | Expansion of an existing clinic | Pasroor, Sialkot | Pending screening. | 2012-08-31 | Mehreen Siddiqi | 2012-09-12
|  | Current Month | Previous Month
| Early Stage | 2 | 3
| Approved | 2 | 2
| Rejected | 1 | 0
| On hold | 1 | 1
| Total | 6 | 6

## Under Review
Association for the Development of Pakistan | [11 empty] | August 2012
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| YDO | Youth Development Organization | Rajanpur, Punjab | 11764 | Installation of hand pumps | Adnan Pathan Meher Makda, Sofia Ahmad | Hasham Mehmood | Approved. In execution. | 2011-05-18 | 2012-08-12 | End
| DUH | Darul Hikmat Society | Lahore | 9952 | Computer labs for 3 existing schools | Mughees Butt, Bilal Noor, Rabia Hussain | Salman Naveed Khan | Approved. In execution. | 2011-10-01 | 2012-09-12 | End
| AHD | Agency for Human Development | Charsadda | 13886 | Water and Sanitation Facilities | Saman Nizami, Mehrunissa Hamid, Ahsan Siddiqui | Salman Naveed Khan | Mid stage of evaluation. | 2011-03-03 | 2012-09-12 | Mid
| BAP | Behbud Association of Pakistan | Rawalpindi | 10406 | Equipment for an existing laboratory | Danish Iqbal, Hashir Sultan, Habiya Beg, Farhan Bandukda | No official PEC. Mehreen Siddiqi shadowing the project | Mid stage of evaluation. Site visit to be conducted soon. | 2011-12-14 | 2012-09-12 | Mid
| BDS | Beer Development Society (Haripur) | Haripur, KPK | 10233 | Installation of water filtration plants in 4 government schools | Abdullah Hasan, Maheen Hassan, Mashal Awais, Rahul Shaikh | Mehreen Siddiqi | Mid stage of evaluation. Site visit to be conducted soon. | 2011-11-18 | 2012-09-12 | Mid
| AQF | Al Qasim Foundation | Khushab | 16866 | Construction of bio gas plants (expansion of previous ADP project) | Ali Taufeeq, Nabeel Ahmed, Shozab Naqvi, Mahum Shere | Khurram Jamali | Mid stage of evaluation | 2012-04-23 | 2012-10-12 | Mid
| APS | Amir Public School | Gujranwala | 15837 | Expansion of existing school | Alexis Saba, Maha Rehman, Muzammal Ashraf | Akbar Bhaidani | Mid stage of evaluation. Site visit to be conducted soon. | 2012-05-03 | 2012-09-12 | Mid
| MET | Mianwali Education Trust | Mianwali | 12200 | Expansion of an existing school | Bilal Noor, Mariam Zameer, Sameed Imran, Farid Madhani | Jawad Hasan | Mid stage of evaluation. | 2012-06-29 | 2012-10-12 | Mid
|  | Current Month | Previous Month
| Early Stage Diligence | 0
| Mid-Stage Diligence | 6
| Final Stage Diligence | 0
| Rejected | 0
| Approved | 2
| Total | 8 | 0

## In Progress
Association for the Development of Pakistan | [11 empty] | August 2012
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Expected End Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School | Jan. 2011 | TBC | 8193 | 1218 | Project completion report expected soon | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. According to SWS, the project has been completed and the lab is functional. Last tranche (originally planned to be used for a generator) may or may not be used as SWS is trying to get funding for a solar panel for the lab.
| NEEDS - Poultry | Network for Education & Economic Development Services | Charsadda | 7950 | Sustainable livelihood creation through poultry/ microfinance option | Apr. 2011 | TBC | 7950 | 0 | Loan Report Form Household Survey Form Monthly Household Master Form (to be maintained regularly) | N | 1st tranche of $2,600 released by ADP on Mar. 23, 2011. Site visit conducted by Sadia Ijaz in Dec., 2011 confirmed the progress and demand for the project. 2nd tranche of $2,475 sent over in Dec., 2011. Details of recent loans sent over by NEEDS in April and June, 2012. Last tranche disbursed at the end of July, 2012. Update expected by mid-September, 2012.
| SDO | Saibaan Development Organization | Mansehra | 8700 | Setting up of a water filtration plant | Jul. 2011 | TBC | 8700 | 0 | Report A (1st day of each quarter) | N | The entire amount of funding was disbursed to SDO in mid-October, 2011. Construction work is complete and water filtration plant has been installed. Plant is now functional. Pictures have been received from SDO. Despite regular follow up, no formal report received. Project can, therefore, not be deemed complete.
| CAP | Community Advance Program | Lahore | 8485 | Computers and furniture for existing schools | Oct.2011 | TBC | 8485 | 0 | Submission of Project Metrics Form on completion of Phase II | N | 1s tranche of $3,485 transferred in Sep., 2011. CAP has sent over the following documents: (i) Scanned bill (ii) Computer syllabus form classes 1-8 (iii) Worksheets for all classes (iv) Short course details (v) Report on completion of Phase I Last tranche of $5,000 sent over in November, 2011. Despite regular follow up, no formal report received after the completion of the project. Project can, therefore, not be deeemd complete.
| SIDO | Social Integrated Development Organization | Charsadda | 5040 | Water Supply Scheme (Installation of hand pumps) | Jan. 2012 | TBC | 5040 | 0 | Report C (3 weeks after receiving the 3rd tranche) | N | 2nd tranche wired in Mar. 2012. Report B has been submitted. Last tranche sent out in early May, 2012 and received by SIDO in Aug., 2012. Last 4 hand pumps to be installed in Sep., 2012.
| HEED (M) | Health Education Environment Development Association | Mishtimba, AK | 14200 | Mishtimba Village family latrines | Jan. 2012 | TBC | 14200 | 0 | Reports A and B (to be submitted at the end of every month) | N | All funding released in Jan., 2012. Latrines construction in progress. Pictures and Progress Reports are being received on a regular basis.
| RDO | Rural Development Organization | Faisalabad | 5888 | Upgrade/extension of existing medical center | 2012-05-01 | TBC | 3500 | 2388 | Report B | Y | Contract signed by RDO and ADP. 1st tranche released in May, 2012. Report A has been received. Last tranche to be disbursed soon.
| FIDA | Foundation for Integrated Development Action | D.I. Khan | 8826 | Setting up bio-gas plants | 2012-05-01 | TBC | 6095 | 2801 | 2nd Status Report (1 month after receipt of 2nd tranche) | Y | Contract signed by FIDA and ADP. 1st tranche of $3,530 released in May, 2012. 1st Status Report received. 2nd tranche sent over in July, 2012. Update expected in mid-September.
| SOS | SOS Children's Village | Kasur | 11111 | Construction of classrooms in existing school | 2012-08-12 | TBC | 0 | 11111 | Report A (every month until constuction lasts) | Y | Contract signed by both parties. ADP to launch project soon.
| SS | Sudhaar Society | Kasur | 11111 | Installation of hand pumps | 2012-08-12 | TBC | 0 | 11111 | Report A (upon installation of hand pumps in 1st set of 10 schools) | Y | Contract signed by both parties. 1st tranche to be sent out soon.
| JAQ | JAQ Education Trust | Islamabad | 10815 | Infrastructure for an informal school system | 2012-07-12 | TBC | 10815 | 0 | Report A | N | Contract signed by both parties. All funding released in July, 2012. Update expected in mid September.
| CFC | Concern for Children | Karachi | 12700 | Upgrade of existing medical center | 2012-08-12 | TBC | 0 | 12700 | Report A (after construction is complete) | Y | Contracted signed by both parties. 1st tranche to be sent out soon.
| Projects In Progress | 12
| Remaining Funding | 41329

## Volunteers
Association for the Development of Pakistan | [9 empty] | May 2012
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 6 | 9 | 2 |  | 0 | 3 | 0 | Adeel Qaiser, Mughees Butt and Nabeel Hasnain (newly inducted PECs) are expected to be staffed as PECs during the July-round of evaluation-team staffing.
| Project Team Leads | 9 | 4 | 4 |  | 0 | 0 | 0 | 10 PTLs are staffed on projects right now. 1 (Danish Iqbal) has been staffed on the Behbud project in May with 2 PTLs expected to be staffed in June '12.
| Project Team | 33 | 3 | 22 |  | 14 | 2 | 3 | 1 project team (Behbud) was staffed in May '12 with 2 more teams scheduled to be staffed in June '12.
| Site Visits | 4 | 2 | 2 |  | 6 | 0 | 0 | Site visits of YDO, JAQ, and CFC projects were conducted in May '12. Site visit of the SWS project (as a precursor to the last tranche transfer) is still pending due to non-availability of a volunteer to visit the site.
| Sourcing | 2 | 0 | 0 |  | 3 | 0 | 0 | Organizations are being requested not to submit proposals till such time that we have evaluated their strengths and capabilities. Pre-screening and screening now being carried out directly by the OD/VM.
| Fundraising | 2 | 10 | 0 |  | 3 | 1 | 0 | One volunteer (Donor Management) is currently working, and efforts being made to schedule a call for a 10-person fundraising team in early June '12.
| Media | 10 | 2 | 9 |  | 5 | 0 | 0 | A videographer has been selected, and has visited the NEEDS (handpumps), AQF (biogas), SFL (flood rehab), and MHSF (school) projects, with one project visit scheduled for June '12. Media team volunteers are now being assigned to all projects as soon as the site visit date is finalized.
| Web team | 2 | 0 | 0 |  | 0 | 0 | 0 | No updates in May '12
| Legal | 3 | 1 | 1 |  | 0 | 0 | 0 | No updates in May '12
| Marketing | 2 | 4 | 2 |  | 2 | 0 | 0 | No updates in May '12
| Other | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 volunteers staffed (and active) on KMS. Efforts ongoing to on-board another volunteer who can manage all data upload/updation activities.
| Total | 75 | 35 | 42 |  | 33 | 6 | 3
| Total signups | 20
| New projects launched | 1
| New projects expected | 5 | 2 in June, 3 in July |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed for the Media / Fundraising teams
One dedicated resource needed to manage the KMS
Initiatives:
KMS volunteers have been staffed

## Initiatives
Association for the Development of Pakistan |  |  |  |  | August 2012
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Lead: Mubarik Imam Volunteer: Mehreen Siddiqi | The List of ADP's Executive Committee Members and copies of their ID cards have been sent to the lawyer. Next steps: A utility bill/lease agreement for ADP's address in Lahore to be sent to the lawyer. | Ongoing
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz, Vajiha Sipra, Afshin Khan, Rabiah Hussain, and Najia Khan | The media team is working on multiple projects and initiatives at this time (Project Videos, Annual Report) with details shared below. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Leads: Tarim Wasim, Salman Naveed Volunteer: Madeeha Ansari, Sidra Hameed | The 'schools' sub-sector has been completed while work is on-going on hand-pumps (water) and biogas (energy) sectors. | Ongoing
| ADP Project Videos | To identify past completed projects and get volunteers to visit sites and make videos | Leads: Nabeel Shakeel Volunteer: Rabiah Hussain and Afshin Khan | The Videographer has visited the Al Qasim Biogas, NEEDS (Water), MHSF (school), SFL (flood rehab) projects in May '12. Videos expected to be available by early Sep., 2012. | 2012-09-12
|  | To obtain usable content from site visit volunteers for the projects under evaluation | Lead: Nabeel Shakeel Volunteers: Ayesha Shahid, Nabeel Shakeel, and Sanaa Qureshi | The initiative has been formally made part of the project cycle.
| Technical Advisors | To have a permanent panel of experts that teams can reach out to during project evaluations | Lead: Salman Naveed Khan | List of questions to be shared with the TAs by Salman in June '12 and FAQs to be developed and made part of the respective KMS sections. | Ongoing
| Annual Report 2011 | To publish ADP's Annual Report for 2011 | Lead: Nabeel Ahmed Volunteers: Media Team members, Mehreen Siddiqi and Salman Naveed Khan | Need to accelerate pace on this project and complete it within Sep., 2012. | 2012-09-12
| Fundraising | To actively raise funds to meet the funding needs of projects approved in 2012 and to develop a more formal fundraising format for ADP | Leads: Usman Hasan and Tarim Wasim | (i) Improve communications with donors: in the process of selecting a volunteer to assist Usman (ii) Corporate donation matching set- up (iii) Plan fundraising events (iv) Foundation Fundraising | Ongoing