## Cover
Association for the Development of Pakistan
Monthly Report
2012-12-12

## Proposals
Association for the Development of Pakistan | [8 empty] | December 2012
New Proposals
Approved from screening
Rejected
On Hold
| Project Name | NGO | Budget | Description | Project location | Next Steps | Proposal Received | Screener | Screening Decision made/ expected?
| Expansion of skills training center | AHD | 10515 | Computers and furniture for existing center | Dadu | Rejected. | 2012-12-01 | Mehreen Siddiqi | Dec. 2012
| Bio gas plants | FIDA | 19578 | Scaling up ADP funded project in 2012 - increase the number of bio gas plants in the same village | D I Khan | Terms of proposal still being revised with the NGO. Once that is finalized, a team will be staffed on it. | 2012-12-17 | Mehreen Siddiqi/ Khurram Jamali | Jan. 2013
| Construction of a new primary school | MHSF | 26000 | Construction of a primary school | Hafizabad | Approved. Team to be staffed. | 2012-12-26 | Mehreen Siddiqi | Dec. 2012
|  | Current Month | Previous Month
| Early Stage | 1 | 0
| Approved | 1 | 1
| Rejected | 1 | 0
| On hold | 0 | 0
| Total | 3 | 1

## Under Review
Association for the Development of Pakistan | [11 empty] | December 2012
Projects Under Review | [9 empty] | Approved
Rejected
| Project Name | NGO | Location | Budget | Description | Project Team | Evaluation Committee | Next Steps | Proposal Received | Decision made/Expected | Diligence Stage
| DUH | Darul Hikmat Society | Lahore | 9952 | Computer labs for 3 existing schools | Mughees Butt, Bilal Noor, Rabia Hussain | Salman Naveed Khan | Though approved on evaluation, this project is being removed from the list of projects to be funded by ADP. It has been very difficult to maintain contact with the NGO for the past couple of months and this has raised significant concerns regarding credibility. | 2011-10-01 | 2012-09-12 | End
| BDS | Beer Development Society (Haripur) | Haripur, KPK | 10233 | Installation of water filtration plants in 4 government schools | Abdullah Hasan, Maheen Hassan, Mashal Awais, Rahul Shaikh | Mehreen Siddiqi | Approved. In execution. | 2011-11-18 | 2012-12-12 | End
| AQF | Al Qasim Foundation | Khushab | 16866 | Construction of bio gas plants (expansion of previous ADP project) | Ali Taufeeq, Nabeel Ahmed, Shozab Naqvi, Mahum Shere | Khurram Jamali | Mid stage of evaluation. Site visit to be conducted in Feb. 2013. | 2012-04-23 | 2013-02-13 | Mid
| MET | Mianwali Education Trust | Mianwali | 12200 | Expansion of an existing school | Bilal Noor, Mariam Zameer, Sameed Imran, Farid Madhani | Jawad Hasan | Approved. In execution. | 2012-06-29 | 2012-11-12 | End
| SFL (health) | Sahara for Life Trust | Pasroor, Sialkot | 15526 | Expansion of an existing clinic | Ruqaiya Ramzan, Junaid Tahir, Ahsan Husaain, Sarah Hadi | Rameez Dossa | Mid stage of evaluation. Site visit conducted in Dec. 2012. Another one required. Decision to be made thereafter. | 2012-08-31 | 2013-02-12 | Mid
| JAT | Jannat Aziz Trust | Burewala, Vehari | 11111 | Eye equipment for an existing clinic | Bilal Hussain, Umair Khalid, Maryam Jillani, Muhammad Bilal | Adeel Qaiser | Mid stage of evaluation. Site visit conducted in Dec. 2012. | 2012-07-04 | 2013-01-13 | End
| ADO | Area Development Organization | Muzaffarbad | 10886 | Water supply project | Babar Khan, Farhan Mumtaz, Shehryar Khan, Alizay Saeed | Natasha Qureshi | Mid stage of evaluation. Site visit to be conducted by Farhan Mumtaz (team member) in Jan. 2013. | 2012-02-29 | 2013-02-13 | Mid
| SDO | Sustainable Development Organization | Neelum Valley, AK | $10,526 (50% of project budget) | Micro Hydro power project | Syeda Masood, Erin Poeta, Ayesha Akbar, Mariam Rafique | Hasham Mehmood | Kick off call held on 12/09/2012. | 2012-05-25 | 2013-04-13 | Early
|  | Current Month | Previous Month
| Early Stage Diligence | 1
| Mid-Stage Diligence | 3
| Final Stage Diligence | 1
| Rejected | 1
| Approved | 2
| Total | 8 | 0

## In Progress
Association for the Development of Pakistan | [10 empty] | December 2012
Projects In Progress
| Project Name | NGO | Location | Budget | Description | Start Date | Funding To Date | Remaining Funding | Next Reporting Date | Potential Disbursement (Y/ N) | Notes (next milestone, issues etc.)
| SWS | Sahara Welfare Society | Ghotki, Sindh | 9411 | Set up a computer lab in Noor Lakhan School | Jan. 2011 | 8193 | 1218 | Project completion report expected soon | Y | ADP disbursed a total of $4,705 in Jan. and Feb., 2011 which have been received by SWS. Noor Lakhan School has been upgraded to a High School. According to SWS, the project has been completed and the lab is functional. Last tranche (originally planned to be used for a generator) may or may not be used as SWS is trying to get funding for a solar panel for the lab.
| SIDO | Social Integrated Development Organization | Charsadda | 5040 | Water Supply Scheme (Installation of hand pumps) | Jan. 2012 | 5040 | 0 | Final report to be submitted after the installation of 3 more pumps | N | Project complete. Some of the funding amount was left over so site visit was conducted in Dec. 2012. All installed hand pumps are functioning well and a large number of people now have access to clean drinking water. The remaining money is to be used for the installation of 3 more pumps.
| RDO | Rural Development Organization | Faisalabad | 5888 | Upgrade/extension of existing medical center | 2012-05-01 | 3500 | 2388 | Report B | Y | Contract signed by RDO and ADP. 1st tranche released in May, 2012. Site visit conducted in Dec. 2012. Site visit volunteer had very positive impressions of the NGO as well as the project. Remaining funding to be disbursed in Jan. 2013.
| SOS | SOS Children's Village | Kasur | 10526 | Construction of classrooms in existing school | 2012-08-12 | 5263 | 5263 | Report A (every month until constuction lasts) | Y | 1st tranche sent out in Nov. 2012. Construction started in mid December, 2012 and is expected to be completed in Feb., 2013. Site visit to be conducted in Feb. 2013 and remaining funding to be disbursed thereafter.
| SS | Sudhaar Society | Kasur | 10710 | Installation of hand pumps | 2012-08-12 | 10710 | 0 | Project Completion Report | N | Last tranche sent over to Sudhaar in Dec. 2012. Project has been completed. Site visit condcuted in Dec., 2012.
| JAQ | JAQ Education Trust | Islamabad | 10815 | Infrastructure for an informal school system | 2012-07-12 | 10815 | 0 | Report A | N | Progress being made. Update to be received soon.
| CFC | Concern for Children | Karachi | 12052 | Upgrade of existing medical center | 2012-08-12 | 5938 | 6114 | Report A (after construction is complete) | Y | Construction in progress; to be completed in Feb. 2013. Pictures received by ADP.
| YDO | Youth Development Organization | Rajanpur, Punjab | 3550 | Installation of hand pumps | 2012-11-12 | 3550 | 0 | Report A | N | All funding released. 1st set of hand pumps has been installed. Site visit to be conducted soon.
| BAP | Behbud Association of Pakistan | Rawalpindi | 10406 | Equipment for an existing laboratory | 2012-12-12 | 0 | 10406 | To be based on the drafted contract | Y | Approved. Contract being drafted.
| APS | Amir Public School | Gujranwala | 15250 | Expansion of existing school | 2012-12-12 | 15250 | 0 | Report A | N | All funding released in Dec. 2012. Construction to start in Jan. 2013.
| Projects In Progress | 10
| Remaining Funding | 25389

## Initiatives
Association for the Development of Pakistan |  |  |  |  | December 2012
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Lead: Mubarik Imam Volunteer: Mehreen Siddiqi | Registration to have been filed. Update expected soon. | Ongoing
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Leads: Nabeel Shakeel and Mehr Husain Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz, Vajiha Sipra, Afshin Khan, Rabiah Hussain, and Najia Khan | The Media Team is working on multiple projects and initiatives at this time. ADP Vision roll out being planned. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Lead: Tarim Wasim | The 'schools' sub-sector has been completed. To kick start things in January, 2013. | Ongoing
| Annual Report 2011 and 2012 | To publish ADP's Annual Report for 2011 and 2012 | Leads: Nabeel Ahmed/ Mehr Husain Volunteers: Media Team members and Mehreen Siddiqi | Need to accelerate pace on this project and complete it once ADP Vision Roll out is completed. | Ongoing
| Fundraising | To actively raise funds to meet the funding needs of approved projects and to develop a more formal fundraising format for ADP | Leads: Usman Hasan, Tarim Wasim and Mehr Husain | (i) Improve communications with donors. Duty of Communications Lead, Mehr Husain. (iii) Plan fundraising events (iv) Foundation Fundraising (v) Donor receipts and Thank you letters to be sent | Ongoing
| Hiring a Program Officer and an Operations Support person | Add to existing employee base so as to be able to achieve goals set forth for the next few years | Lead: Mehreen Siddiqi | Interviews being conducted | 1st quarter of 2013

## Financials
Association for the Development of Pakistan | [5 empty] | 2012
Financials
|  | Q1 | Q2 | Q3 | Q4 | FY
Donations (net) |  | 8742 | 6135 | 39949 | 51792 | 106618
Project Grants
| Hand Pumps (SIDO) | 2690 | 2275 |  |  | 4965
| Hafeezabad School Expansion (MHSF) |  | 5555 |  |  | 5555
| Microfinance for Poultry (NEEDS) |  |  | 2875 |  | 2875
| Kot Addu Model Village (SFLT) | 9575 | 2185 |  |  | 11760
| Mishtimba Sanitation (HEED) | 14200 |  |  |  | 14200
| Biogas Plants (FIDA) |  | 3530 | 5115 |  | 8645
| Al-Makkah Medical Center Expansion (RDO) |  | 3500 |  |  | 3500
| Water for Schools (Sudhaar) |  |  | 5320 | 5155 | 10475
| Expansion of School in Kasur (SOS) |  |  |  | 5350 | 5350
| Maternal Healthcare in Machar Colony (CFCT) |  |  | 6000 |  | 6000
| Hand Pumps (YDO) |  |  |  | 3550 | 3550
| Kalaske Middle School Expansion (Nia Ujala) |  |  |  | 15250 | 15250
| Pehli Kiran School Infrastructure (JAQ) |  |  | 10815 |  | 10815
| Total | 26465 | 17045 | 30125 | 29305 | 102940
SG&A
| Salaries | 3618 | 2555 | 5830 | 3026 | 15029
| Marketing / Fundraising | 500 | 1959 | 252 | 579 | 3290
| Other | 3550 | 250 | 421 | 200 | 4421
| Total | 7668 | 4764 | 6503 | 3805 | 22740
Available Funds
| General | 58.1
| Flood Redevelopment | 3.3