## Volunteers
Association for the Development of Pakistan | [9 empty] | April 2012
Volunteers
|  | Total |  |  |  | New (this month)
|  | Staffed(1) | Needed(2) | Available(3) |  | Signups(4) | Selected | Trained | Notes
| Permanent Evaluation Committee | 6 | 9 | 2 |  | 0 | 2 | 0 | Adeel Qaiser and Mughees Butt have been recommended to be upgraded as PECs. Both have expressed an interest in assuming the role, and shall be trained and staffed on new projects in June 2012.
| Evaluation Committee | 0 | 0 | 0 |  | 0 | 0 | 0 | 5 ECs are staffed on active projects. No EC is staffed on any proposals under-review.
| Project Team Leads | 9 | 4 | 4 |  | 0 | 0 | 0 | 9 PTLs are staffed on projects right now. 1 shall be staffed in May, while 4 more expected to be staffed on teams in June '12.
| Project Team | 33 | 3 | 22 |  | 17 | 2 | 3 | No new project teams have been staffed in April '12.
| Site Visits | 4 | 2 | 2 |  | 4 | 0 | 0 | Site visits of YDO and SWS have been postponed. Awaiting updates from the site visit volunteers on when the visits can be scheduled.
| Sourcing | 1 | 1 | 0 |  | 2 | 0 | 0 | Organizations are being requested not to submit proposals till such time that we have evaluated their strengths and capabilities. 2 proposals have been screened and approved for staffing, and 3 more shall be approved for staffing in May '12.
| Fundraising | 8 | 3 | 1 |  | 4 | 0 | 0 | One voluteer attached with Usman to go through and compile requirements of USAID and assess how ADP can benefit from the funding programs. One position has been advertized and a candidate shortlisted. Usman shall have a detailed discussion with him in the first week of May '12. One additional volunteer required to work with Usman to set up and coordinate the work-place donation/matching grants initiative.
| Media | 10 | 2 | 9 |  | 3 | 4 | 0 | 4 volunteers joined the media team this month, and were given an orientation by Nabeel. Tasks have also been delegated to individual team members. A videographer shall be added to the team to shoot/edit footage of 5 completed-projects in May '12.
| Web team | 2 | 0 | 0 |  | 0 | 0 | 0 | No updates in Apr '12
| Legal | 3 | 1 | 1 |  | 0 | 0 | 0 | No updates in Apr '12
| Marketing | 2 | 4 | 2 |  | 1 | 0 | 0 | No updates in Apr '12
| Other | 2 | 0 | 0 |  | 0 | 0 | 0 | 2 volunteers staffed (and active) on KMS
| Total | 80 | 29 | 43 |  | 31 | 8 | 3
| Total signups | 19
| New projects launched | 0
| New projects expected | 5 | One in May, and 4 in June |  | According to maximum numbers based on proposals approved and in the pipeline
(1) Actively engaged on a current project
(2) Number of current openings or expected near-term needs
(3) Qualified and trained volunteers that have available capacity (can include Staffed volunteers)
(4) Total adds up to more than actual signups since people indicate multiple interests
Issues:
More volunteers need to be staffed for the Media / Fundraising teams
Initiatives:
KMS volunteers have been staffed

## Initiatives
Association for the Development of Pakistan |  |  |  |  | April 2012
Other Initiatives
| Initiatives | Description | Volunteers | Updates | Expected Completion Date
| ADP Pakistan Registration | To locally register ADP as a non-profit within Pakistan. This will smoothen the fundraising process as well as open up other opportunities in Pakistan. | Lead: Mubarik Imam Volunteer: Mehreen Siddiqi | The List of ADP's Executive Committee Members and copies of their ID cards have been sent to the lawyer. Next steps: A utility bill/lease agreement for ADP's address in Lahore to be sent to the lawyer. | Ongoing
| Media Team | The media team has overall responsibility for dissemination and promotion of activities and information. | Lead: Nabeel Shakeel; Volunteers: Natalia Bokhari, Ayesha Shahid, Ayesha Sarfaraz, Vajiha Sipra, Afshin Khan, Rabiah Hussain, and Najia Khan | The media team is working on multiple projects and initiatives at this time (Project Videos, Annual Report, Funraising Appeal/Project launch communication) with details shared below. | Ongoing
| Knowledge Management System | To develop a tool that will capture and share key learnings from the projects evaluated by ADP every year | Leads: Tarim Wasim, Salman Naveed Volunteer: Madeeha Ansari, Sidra Hameed | The 'schools' sub-sector has been completed, while work is on-going on hand-pumps (water) and biogas (energy) sectors. | Ongoing
| ADP Project Videos | To identify past completed projects and get volunteers to visit sites and make videos | Leads: Nabeel Shakeel Volunteer: Rabiah Hussain and Afshin Khan | Of the completed projects, the Media Team has selected Al Qasim Biogas, NEEDS (Water), Amir Public School, HEED (Sokar), and Arshad Public School Projects for developing one-minute documentaries. The scripts have been finalized, and work-on-the-ground expected to start in May '12. | Ongoing
|  | To obtain usable content from site visit volunteers for the projects under evaluation | Lead: Nabeel Shakeel Volunteers: Ayesha Shahid, Nabeel Shakeel, and Sanaa Qureshi | The initiative has been formally made part of the project cycle.
| Technical Advisors | To have a permanent panel of experts that teams can reach out to during project evaluations | Lead: Salman Naveed Khan | List of questions to be shared with the TAs by Salman in May '12 and FAQs to be developed and made part of the respective KMS sections. | 2012-05-01
| Annual Report 2011 | To publish ADP's Annual Report for 2011 | Lead: Nabeel Ahmed Volunteers: Media Team members, Mehreen Siddiqi and Salman Naveed Khan | Working doc for the Annual Report has been created. Work to Salman and Mehreen has been delegated. Mehreen has submitted her sections, while information from Salman/Usman/Tarim is awaited. Rest has been delegated to members of the Media Team. | 2012-05-01